## Slide 1
Lionel Prost
PIP-II Risk Workshop
4/6-4/7/2017
PIP-II Project Risk: Warm Frontend

## Slide 2: Risks to be covered today
Beam properties at the exit of the ion source drift over long period of times
Unable to maintain proper vacuum between MEBT absorber and SRF
MEBT protection scheme with scrapers does not work

## Slide 3: Beam properties at the exit of the ion source drift over long period of times
Risk Owner: Lionel Prost
Choice of commercially available ion source (from D-Pace, Inc.) not specifically designed for PIP-II
  Otherwise satisfies PIP-II Ion Source FRS
Risk Cause:
  Observed drift of the beam properties at the end of the LEBT at PIP2IT
Risk Effect:
  Inability to maintain a high transport efficiency over the lifetime of a filament set may decrease the reliability/performance of the accelerator downstream

## Slide 4: Risk: Probability, Technical Impact
Probability
  90%
Technical Impact
  3 (H) – Significantly substandard
Risk Rank
  3 (High)
Cause or Trigger
  N/A

## Slide 5: Risk: Cost & Schedule Impact and Estimate
Cost Impact: (Single Point)
  $100k
Schedule Impact: (2-point – flat range)
  12-24 months
Estimate:
  Purchase another ion source
    Identification of a new source meeting PIP-II requirements and procurement effort + lead time
Quality of Risk Estimate
  2 - Reasonable estimate
  Based on purchase of D-Pace, Inc. ion source ~8 years ago

## Slide 6: Risk Mitigation
Several techniques involving a feedback algorithm will be tested at PIP2IT
  Impact of the ion source drift on the beam parameters downstream (e.g. in MEBT) will be measured
Start Date:
  In progress
End Date:
  2020 i.e. End of R&D Phase
Monitoring Required:
  ?

## Slide 7: Unable to maintain proper vacuum between MEBT absorber and SRF
Risk Owner: Lionel Prost
Secondary and/or reflected particles may escape the differential pumping section
Risk Cause:
  Reflected power larger than expected was observed on the absorber test bench
    Actual distribution of the secondary/reflected particles is unknown
Risk Effect:
  Poor vacuum and/or particles flying to the SRF section may jeopardize the performance and reliability of acceleration in the SRF accelerating structures

## Slide 8: Risk: Probability, Technical Impact
Probability
  50%
Technical Impact
  2 (M) – Moderately substandard
Risk Rank
  3 (High)
Cause or Trigger
  Does not meet specs at PIP2IT

## Slide 9: Risk: Cost & Schedule Impact and Estimate
Cost Impact:
  Probably small w.r.t. the rest of the project
Schedule Impact: (1-point – Single value)
  6 months
Estimate:
  Redesign of the differential pumping section
Quality of Risk Estimate
  1 – Rough guess
  If the current design of the MEBT beam line downstream of the absorber does perform as expected, it is not clear how it would be modified and the time and effort it would take to ensure the proper ‘protection’ at PIP-II

## Slide 10: Risk Mitigation
Differential pumping section design will be implemented at PIP2IT
Start Date:
  Design in progress
End Date:
  2020 i.e. End of R&D Phase
Monitoring Required:
  ?

## Slide 11: MEBT protection scheme with scrapers does not work
Risk Owner: Lionel Prost
Movable scrapers are not water-cooled and have several uses (e.g. beam size measurements with short pulses), making operation possibly a little bit more prone to mistakes
Risk Cause:
  Scrapers need to be integrated within the Machine Protection System while also being used as diagnostics depending on the machine status
    Radiation-cooled design limit the maximum power that the scrapers can withstand
Risk Effect:
  Failure of the scheme at PIP2IT would jeopardize completion of the R&D goals and trigger design changes

## Slide 12: Risk: Probability, Technical Impact
Probability
  25%
Technical Impact
  2 (M) – Moderately substandard
Risk Rank
  3 (High)
Cause or Trigger
  Failure of a major component(s) or of the scrapers themselves at PIP2IT

## Slide 13: Risk: Cost & Schedule Impact and Estimate
Cost Impact: (Single Point)
  $100k
Schedule Impact: (2-point – flat range)
  6-12 months
Estimate:
  Design new scraper paddles
    Associated effort with machine status reporting and machine protection system
Quality of Risk Estimate
  1 – Rough guess
  The most expensive parts of the scrapers are the actuators, which may not have to be replaced
    Redesign of the paddles with, for instance, water cooling may not be too costly

## Slide 14: Risk Mitigation
Scrapers and associated protection scheme will be tested at PIP2IT
Start Date:
  Q1FY18
End Date:
  2020 i.e. End of R&D Phase
Monitoring Required:
  ?