## Slide 1
Mohammed Elrafih
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
Risk Analysis Tool

## Slide 2: Mohammed Elrafih – Background
Current roles
Project Controls Specialist, “LBNF – Cryogenics Infrastructure”
Fermilab Risk Support
  Enterprise risk, Lab-standard project risk process, risk register, tools
  Risk workshops, risk analysis, MC modeling, reviews
Honors Business Administration (HBA)
  Richard Ivey School of Business
Project Coordinator & Project Controls Experience in:
  Major Oil & Gas Construction Projects
PMP Certified

## Slide 3: From the Risk Register to Primavera Risk Analysis
Data from the Risk Register which is used for the Monte Carlo

## Slide 4: Schedule Import into PRA (Full or Summary Schedule)

## Slide 5: Risks Entered into PRA Risk Register
Risk ID, Title, Probability, Impacts
  Lucas.Taylor@cern.ch

## Slide 6: Risks Linked to Schedule Activities
A risk is linked to a designated schedule activity which it directly impacts
Cost and Schedule Impacts are assigned to the activity
  Lucas.Taylor@cern.ch

## Slide 7: Impacted Risk Plan is Built and Monte Carlo Analysis is run
Risk plan is built to determine which Risks the PM wants to see included in the Monte Carlo
  Lucas.Taylor@cern.ch
The Monte Carlo Analysis is run 100,000 times

## Slide 8
Example - Risk Modeling Results

## Slide 9: Total DOE cost of 29 risks that affect FS-CF CD-3a
FS-CF CD-3a DOE risk cost contingency = 22.5 M$ (at 90% C.L.)
(not including burn rate)
22.5 M$

## Slide 10: FS-CF CD-3a DOE Cost Risk Drivers
Chart: % of Overall Risk Cost Impact @ 90%
| RT-131-CFFS-4850L-007 Far Site construction activities impact neighboring communities | RT-131-CFFS-4850L-101 Adverse conditions in far site underground excavations - High Prob Low Impact | RT-131-PM-101 Scope is missing due to poor interface definition at Far Site | RT-131-CFFS-4850L-1000 Cryogenics or FD changes impact layout/design of Far Site facilities | RT-131-PM-107 Installation of cryogenics or detector overlaps with excavation work | RT-131-PM-100 Multiple-party interfaces at SURF | RT-131-CFFS-4850L-010 Specialized construction labor is unavailable | RT-131-CFFS-4850L-018 CF FS -- escalation rate greater than predicted
Mean Cost Impact (k$)*P | 0.0061858 | 0.011919 | 0.037099 | 0.051649 | 0.059074 | 0.11545 | 0.1474 | 0.57122

## Slide 11: FS-CF CD-3a schedule risk – aggregation of 29 FS-CF risks
Milestone: FS-CF – Complete the excavation of CD-3a Scope
Base plan finish: 5 March 2021 (before 15 Mar 2022, at 90% C.L.)
12.3 months

## Slide 12: FS-CF CD-3a schedule risk drivers
Remove each risk in turn, then run full MC with all other (N-1) risks to see how much FS-CF completion date is advanced
  Many risks have no impact on the finish date as they are either not on the critical path or they are in the shadow of bigger impact risks
Chart: % of Total Schedule Impact
| RT-131-CFFS-4850L-101 Adverse conditions in far site underground excavations - High Prob Low Impact | RT-131-PM-100 Multiple-party interfaces at SURF | RT-131-PM-107 Installation of cryogenics or detector overlaps with excavation work | RT-131-CFFS-4850L-001 Adverse conditions in far site underground excavations - Low Prob High Impact | RT-131-CFFS-4850L-015 Old timber at Far Site combusts spontaneously | RT-131-CFFS-4850L-024 Blasting at Far Site causes damage or unacceptable distress to Sanford Lab | RT-131-CFFS-4850L-200 Unavailability of SURF-supplied systems and spaces | RT-131-CFFS-4850L-202 Oro Hondo shaft ventilation path is blocked | RT-131-CFFS-4850L-1000 Cryogenics or FD changes impact layout/design of Far Site facilities | RT-131-CFFS-4850L-010 Specialized construction labor is unavailable | RT-131-PM-013 Changes to the DOE funding profile before CD-2
Mean Cost Impact (k$)*P | 0.0026667 | 0.0026667 | 0.0026667 | 0.010667 | 0.010667 | 0.010667 | 0.013333 | 0.013333 | 0.066667 | 0.13067 | 0.496