## Feuil1
RI-ID | Title | Summary | Risk Mitigations
PD-DP-1 | Detector performance is affected by electrical noise | The detector needs good S/N ratio in order to be able to measure efficiently charge deposition at the level of minimum ionizing particles or even lower energy depositions. Noise conditions can be affected by environmental conditions related to grounding shielding and power distribution | Cryogenic electronics is used in order to limit the noise. For readout strips of 3m the measured noise is 1600 ENC. The dual-phase readout technology by augmenting the charge with tunable amplification in the gas phase is not critical with respect to noise conditions. A S/N ratio greater than 100:1 is expected with a gain of 20. The gain can be adjusted in order to optimise the S/N. Enironmental noise can never be totally controlled but is reduced with a careful grounding and shielding scheme implying the use of isolation transformers. The cryogenic front-end electronics installed in the signal chimneys are completely shielded with respect to the digital electronics and environmental EMI. Noise conditions using this configuration have been measured on the 3x1x1 prototype and meet expectations.
PD-DP-2 | Availability of the charge readout electronics for ProtoDUNE DP and DUNE far detector | Schedule for the availability of a coherent charge readout electronics design ensuring the performance of the analog front-end electronics and of the digital electronics | The design of the cryogenic ASIC amplifiers was completed in 2015. 700 chips were produced for the DP ProtoDUNE. All other electronic components (including e.g. the ADC) rely on commercial components. The design of the FE cards was completed in 2016 20 cards + spares were produced in order to equip the 3x1x1 detector. The design of the uTCA digital electronics was completed in 2016 and 20 cards were produced in order to equip the 3x1x1 detector. The production of the remaining 100 FE cards and 100 digital cards will be performed in between the fall of 2016 and the first months of 2017.
PD-DP-3 | Lifetime of the detector electronics | Detector electronics may be affected by the lifetime of the components used for its fabrication by HV sparks occurring inside the detector. | There is no active electronic component inside the cryostat. The F/E electronics is accessible and repleacable, including the cryogenic front-end electronics in the chimneys which may be extracted and replaced in case of malfunctioning even when the detector is filled with liquid argon. The FE electronics is protected with surge arrestors. The digital electronics is installed at warm and based on an industry standard (microTCA) which guarantees easy maintenance and replacement.
PD-DP-4 | Detector performance is affected by the liquid argon purity conditions | Electronegative impurities present in the liquid argon may affect the drift electron lifetime and bring to lower S/N ratio. | The purity requirements correspond to a lifetime of 3 ms, which is quite conservative: higher figures have been achieved in non evacuated detectors such as Microboone. Furthermore the dual-phase allows increasing the gain in order to recover with respect to non-optimal purity conditions.
PD-DP-5 | Availability and performance of the light detection system | The light detection system should provide good efficiency for the detection of low energy depositions, as in supernova neutrino interactions | The light readout system is based on standard cryogenic photomultipliers (Hamamatsu R5912-02) which have been already used in several installations. They do not imply any particular issue in the design of the LRO system and in its performance. In the FD 100% efficiency can be achieved at 200 MeV and >50% efficiency at 5 MeV. In order to have larger margins with respect to light scattering and UV absorption in LAr, this figure can be improved by simply increasing the coverage to 1 photomultiplier/M2, as it will be tested in the DualPhase ProtoDUNE.
PD-DP-6 | The drift HV cannot be reached | The dual-phase technology exploits long drifts (6 m in the DP ProtoDUNE and 12 m in the FD) which require, at an electric field of 0.5 kV/cm a HV of 300 kV in the ProtoDUNE DP and 600 kV in the Far Detector | The design of the HV system is performed in order to avoid high field regions, staying tipically below 50 kV/cm. The operation of the high voltage feedhtrough at 300 kV was recently demonstrated in September 2016. The DP ProtoDUNE will also test 600 kV in order to reproduce the nominal conditions of the FD. Microboone has shown that operation at 250V/cm is acceptable which would imply a maximum voltage of 150kV for ProtoDUNE DP and 300kV for the DUNE FD.
PD-DP-7 | Lack of the funding for the construction of the ProtoDUNE DP detector | Reduced funding may imply delays in the construction of the 6x6x6 DP ProtoDUNE detector | A MOU was signed in 2015 for the construction of the 6x6x6 covering its construction costs. A good part of this money has been already distributed and spent. No issues are expectd with the funding agencies for the contributions described and already agreed in the MOU
PD-DP-8 | Delay in the construction schedule of the ProtDUNE DP | A delay in the construction schedule may limit the period of beam data-taking of the 6x6x6 detector in 2018 | The DP ProtDUNE construction schedule is driven by the availability of the neutrino platform infrastructure at CERN: equipment of the EHN1 extension, cryostat and cryogenic system. The EHN1 schedule is confirmed and the civil engineering works for the EHN1 extension have been completed. The installation of the detector will start in April 2017 and it is expected to be completed by December. This schedule offers a long time of beam data taking froing from April to October 2018. In case of delays this period may be shortned still providing a satisfactory beam exposure.
PD-DP-9 | Delays in the construction of the DP protoDUNE related to prototyping and integration issues | Insufficient efforts in the prototyping of the different detector elements may generate delays at the time of their production or installation in the DP ProtoDUNE detector | The 3x1x1 detctor offered the possibility of performing a full prototypinng and integration exercize of the different detector elements in order to mitigate risks of delays in their procurement and installation for the 6x6x6