## Slide 1
Steve Holmes
PIP-II Project Management Group
20 April 2017
PIP-II Project Manager’s Report

## Slide 2: Outline
Goals
Financials
ES&H/NEPA
Technical/R&D
India Collaboration
Project Management
  CD-1 Status

## Slide 3: Project Goals (Unchanged since last month)
Funding profile as contained in the approved Mission Need Statement, adjusted for FY2017 actual
  Moved $4.3M from FY25 to FY19 per DOE guidance of 2/6/17
Corresponds to cost range upper bound
Milestone | Planned | Actual or Forecast
CD-0 | Q1 FY2016 | November 12, 2015 (A)
CD-1 | FY2017 | Q1FY2018
CD-2/3a | FY2019 | FY2019
CD-3 | FY2020 | FY2020
CD-4 | FY2026 | FY2026

## Slide 4: Goals for the Coming Year (Unchanged)
Primary goal is to achieve CD-1 by November 2017
  RLS
  ICR
  Documentation
Financial Goals
  Live within the provided budget: $21.03M (includes FY16 carryover)
  Cross the FY17/18 border with ~$0.75M unobligated (carryover)
ES&H Goals
  Be prepared to initiate Environmental Assessment on 10/1/17
R&D Goals
  Release CDR
  Complete PIP2IT MEBT
  Keep HWR and SSR1 on track for CY2018 delivery
India Collaboration Goals
  Meet 2017 deliverable milestones
  Establish confidence between the partners
Management Goals
  Complete all CD-1 documentation and successfully navigate required reviews
  Fill missing positions on organization chart

## Slide 5: Financials (inception through 3-31-17)
Spending since CD-0
  OPC/Project Office and SC Linac are only areas of activity to date
  4.2% complete
P6 WBS | Total Project | BAC | CTG | EAC | Contingency
 | TEC |  |  |  | 
121.2 | Project Office | 54.0 | 54.0 | 54.0 | 19.0
121.3 | SC Linac | 167.0 | 167.0 | 167.0 | 58.0
121.4/121.5 | Booster/RR/MI | 112.0 | 61.0 | 61.0 | 21.0
121.6 | Civil Construction | 61.0 | 13.7 | 112.0 | 39.0
 | OPC |  |  |  | 
121.2 | Project Office | 16.0 | 13.5 | 16.0 | 6.0
121.3 | SC Linac | 67.0 | 51.1 | 67.0 | 22.5
121.4/121.5 | Booster/RR/MI | 1.0 | 1.0 | 1.0 | 0.5
121.6 | Civil Construction | 4.0 | 3.6 | 4.0 | 2.0
 | TEC+OPC | 482.0 | 461.7 | 482.0 | 168.0

## Slide 6: Financials (FY17 through 3-31-17)
RIPs: $878K
Current Management Reserve: $322K
Demands against Management Reserve: $610K

## Slide 7: Financials/Management Reserve
Budgets adjusted following FY17 forecast-to-complete in January
Current Management Reserve: $322K
Unfunded Requests: $610K
  HB650 cavity dressing $133K
    Discussion with DOE/HEP on 4/17: Move uncosted obligation on Pavac contract into PIP-II budget in support of this work?
  PIP2IT RFQ Couplers + tuners $107K
    Operating in low duty factor mode with no spares
    New coupler design complete and reviewed – ready for procurement
  PIP2IT cryo $39K
  PIP2IT Instrumentation $26K
  LLRF $56K
    Partially funded
  Environmental Assessment $250K
    Delay to FY2018

## Slide 8: ES&H/NEPA
Teri Dykhuis appointed Associate Project Manager for ESH&Q
Wetlands Jurisdictional Determination
  Site-wide request for determination to USACE
    If accepted, the wetlands located in the PIP-II footprint would be designated non-jurisdictional
  Fermilab has submitted to FSO for transmission to USACE
    Some uncertainty as to whether non-jurisdictional determination would relieve Fermilab of obligation to create or procure mitigating acreage
  If denied, a new wetlands permit application would be submitted in FY2018 to allow USACE the 1 year review period in order to meet a PIP-II start work date of late FY2019/early FY2020.
Environmental Evaluation Notification Form (EENF) ready for submission to DOE/FSO
  Expect to forward to FSO this summer and initiate selection of PIP-II NEPA/EA contractor

## Slide 9: Technical/R&D Status
Conceptual Design Report
  Draft CDR reviewed by the P2MAC (April 10-12)
  Validated the concept as a basis for CD-1
  See V. Lebedev presentation
PIP2IT
  2017 goal to complete MEBT and commission with beam
    5 mA × 1 ms × 20 Hz to dump
    Measure kickers’ effects on the beam
  Successfully commissioned with
  beam following installation of LEBT
  dipole
  Shutting down wo/ 4/24 for MEBT
  installation following (partial) receipt
  of magnets from India
  Balance of magnets due to ship 4/30

## Slide 10: Technical/SRF R&D Status
HB650
  We have a cavity reprocessed and ready for testing at VTS
Couplers
  A new RFQ coupler design has been completed and reviewed
    Out for procurement once we are convinced we have funds
  HB650 couplers are being prepared for RFP
    Best value procurement with pre-qualified vendors

## Slide 11: India Collaboration
Joint R&D Project Document
  Addendum II: Documentation of Fermilab engineering deliverables.
    DAE comments received 3/20
    Mostly concern specific documents they are having difficulties locating
    Only real issue: They are assuming Fermilab is designing the LB650 He vessel, even though DAE is designing the cavity and cryomodule. We would like VECC to take the lead on this.
  Addendum I: Modification to DAE deliverable dates to reflect delays in R&D program to FY2020
    DAE to make Addendum I consistent with Addendum II
Visitors
  Attempting to get the visitors program restarted
  First cohort of long term visitors returns over Sept – Nov of this year
  Wish list for second round has been developed by DAE
Upcoming Visits
  Leonardo Ristori et al will be visiting BARC in July for:
    Witnessing of SSR1 He vessel welding
    Review of SSR2 cavity design

## Slide 12: Project Management/CD-1
Assumptions Document approved (3/9)
  Document #144 (docdb)
  Will lead to the Lab-Project MOU recommended by the DOE Review Committee
Functional Requirements Specification approved (3/17)
  ED0001222
Critical path is:
  RLS
  BOEs
Risk Management
  Risk Management Plan initial release
  Risk Workshop April 6-7
    See presentation (S. Mishra)
  Risk validation scheduled April 27

## Slide 13: CD-1 Timeline/Status

## Slide 14: RLS status
WBS for BOE
In P6
Detailed Plan
Close to ready/ready
Advanced
Preliminary

## Slide 15: Project Management
Personnel
  Project controls specialist started 3/21
  Designated Teri Dykhuis as Associate Project Manager for ESH&Q
    She will remain organizationally in ESHQ Section
  Close to publicly announcing the new Project Engineer/MechanicalSystems
    Don M will stay for a transition period
Continuing to suffer from lack of access to srf facilities and people
  LCLS-II monopolizing VTS
    Two (of four) HB650 cavities qualified.
    Third cavity is waiting for access
  Sub-optimal engineering support on HB650
    Tom N (Mu2e) and Chuck G (LCLS-II) have very minimal availability
    Much of the slack is being taken up by Vikas Jain (RRCAT visitor)
    He returns to India in October → need to identify a replacement
  Compensating somewhat by assigning RRCAT as design lead on LB650 Cryomodule
    VECC is already in lead on LB650 cavity design

## Slide 16: Summary
Moving toward CD-1, with a plan in place
  Assessment in mid-April (tomorrow) on viability of timeline
  Not progressing as fast as hoped for, but the opportunity to complete on schedule still remains
India collaboration is taking a lot of attention
  Improving interactions and information exchange
Need to add more staff prior to CD-1
  Essentially there

## Slide 17: Backups

## Slide 18: FY2017 Management Reserve

## Slide 19: R&D: PIP-II Injector Test
PIP2IT will address the address/measure the following:
  LEBT pre-chopping: Demonstrated
  Vacuum management in the LEBT/RFQ region: Demonstrated
  Validation of chopper performance
    Bunch extinction, effective emittance growth
  MEBT beam absorber
    Reliability and lifetime
  MEBT vacuum management
  CW operation of HWR
    Degradation of cavity performance
    Optimal distance to 10 kW absorber
  Operation of SSR with beam
    CW and pulsed operation
    Resonance control and LFD compensation in pulsed operations
  Emittance preservation and beam halo formation through the front end
Collaborators
ANL: HWR
LBNL:LEBT, RFQ
SNS: LEBT
BARC: MEBT, SSR1, RF
IUAC: SSR1
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
2018
2017
2015
Now
2019

## Slide 20: MEBT Emittance Measurement