## Slide 1
Steve Holmes
PIP-II Project Management Group
17 May 2017
PIP-II Project Manager’s Report

## Slide 2: Outline
Goals
Financials
ES&H/NEPA
Technical/R&D
India Collaboration
Project Management
  CD-1 Status

## Slide 3: Project Goals
Funding profile as contained in the approved Mission Need Statement, adjusted for FY2017 actual
  Moved $4.3M from FY25 to FY19 per DOE guidance of 2/6/17
Corresponds to cost range upper bound
Milestone | Planned | Actual or Forecast
CD-0 | Q1 FY2016 | November 12, 2015 (A)
CD-1 | FY2017 | Q2FY2018
CD-2/3a | FY2019 | FY2019
CD-3 | FY2020 | FY2020
CD-4 | FY2026 | FY2026

## Slide 4: Goals for FY17
New goal is to achieve CD-1 in early 2018
  RLS
  ICR
  Documentation
Financial Goals
  Live within the provided budget: $21.03M (includes FY16 carryover)
  Cross the FY17/18 border with ~$0.75M unobligated (carryover)
ES&H Goals
  Be prepared to initiate Environmental Assessment on 10/1/17
R&D Goals
  Release CDR
  Complete PIP2IT MEBT
  Keep HWR and SSR1 on track for CY2018 delivery
India Collaboration Goals
  Meet 2017 deliverable milestones
  Establish confidence between the partners
Management Goals
  Complete all CD-1 documentation and successfully navigate required reviews
  Fill missing positions on organization chart

## Slide 5: Financials (inception through 4-30-17)
Spending since CD-0
  OPC/Project Office, Civil Const, and SC Linac are only areas of activity to date
  4.6% complete

## Slide 6: FY17 Financials (through 4-30-17)
RIPs: $538K
Current Management Reserve: $245K
Demands against Management Reserve: $572K

## Slide 7: FY17 Financials/Management Reserve
Budgets adjusted following FY17 forecast-to-complete in April
Several funding change requests were approved, most notably
  HB650 cavity dressing + contract designer (shared with SSR)
  RFQ new couplers/tuners
Current Management Reserve: $245K
  Includes $130K of uncosted obligation on Pavac contract that DOE has agreed to move from GARD to PIP-II (in June)
Unfunded Requests: $572K
  SSR1 CM parts $251K
  PIP2IT RFPI $15K
  LLRF $56K
    Partially funded
  Environmental Assessment $250K
Not shown in MR: Anticipate SWF underrun of up to $2M

## Slide 8: ES&H/NEPA
Wetlands Jurisdictional Determination
  Site-wide request for determination to USACE
    If accepted, the wetlands located in the PIP-II footprint would be designated non-jurisdictional
    Process should take ~ 1 year
    Some uncertainty as to whether non-jurisdictional determination would relieve Fermilab of obligation to create or procure mitigating acreage
  FSO has submitted the application package to USACE (Apr 27)
  Fermilab personnel met with USACE representative to provide overview (May 12)
  If denied, a new wetlands permit application would be submitted in FY2018 to allow USACE the 1 year review period in order to meet a PIP-II start work date of late FY2019/early FY2020.
Environmental Evaluation Notification Form (EENF) ready for submission to DOE/FSO
  Expect to forward to FSO this summer and initiate selection of PIP-II NEPA/EA contractor

## Slide 9: Technical/R&D Status
PIP2IT
  2017 goal to complete MEBT and commission with beam
    5 mA × 1 ms × 20 Hz to dump
    Measure kickers’ effects on the beam
  LEBT has been successfully commissioned with
  beam following installation of dipole
  Currently shut down for MEBT
  installation following (partial) receipt
  of magnets from India
  Balance of magnets due to ship 5/15

## Slide 10: Technical/SRF R&D Status
HB650
  Goal is to qualify and dress four cavities in FY17
  Two cavities are qualified
  Third near spec
    Going through “nitrogen infusion” processing
  Fourth went through second vertical test last month
    High FE; will require reprocess
Couplers
  New RFQ coupler design has been completed and reviewed
    Procurement initiated
  HB650 couplers are being prepared for RFP
    Best value procurement with pre-qualified vendors

## Slide 11: India Collaboration
Joint R&D Project Document
  Addendum II: Documentation of Fermilab engineering deliverables.
    DAE comments received March 20
    Mostly concern specific documents they are having difficulties locating
    Returned to DAE with minor modifications and recommendation to accept as is (May 8).
  Addendum I: Modification to DAE deliverable dates to reflect delays in R&D program to FY2020
    DAE to make Addendum I consistent with Addendum II
Visitors
  Attempting to get the visitors program restarted
  First cohort of long term visitors departs Fermilab over Sep–Nov
  Wish list for second round has been developed by DAE
Upcoming Visits
  Leonardo Ristori et al will be visiting BARC in August for:
    Witnessing of SSR1 He vessel welding
    Review of SSR2 cavity design

## Slide 12: Project Management/CD-1
Assumptions Document approved (Mar 9)
Functional Requirements Specification approved (Mar 17)
Lab MOU in development
Critical path is:
  RLS (see L. Lari presentation)
  BOEs (see P. Derwent presentation)
Risk Management
  138 approved risks
  Undertaking initial calculation of associated contingency

## Slide 13: Project Management/CD-1
Agreement with AD on division of scope between PIP-I+ and PIP-II
Scope removed from the PIP-II CD-0 configuration includes:
  Booster Damper Upgrade
  Booster LCW Upgrade
  Booster Collimators Upgrade
  Main Injector gamma-t jump
Scope retained from the PIP-II CD-0 configuration includes:
  New Booster 800-MeV injection area, including higher strength gradient magnets (assumed to be required)
  Booster 20 Hz upgrade (magnets, power supplies, controls)
  New Recycler RF cavities
  Main Injector RF power upgrade
Associate cost impact/savings is:
  Point estimate: $17M
  Upper cost range: $21M

## Slide 14: Project Management/CD-1 Strategy
We are currently developing a “technically limited” RLS, where technically limited means PIP-II completion coincident with completion of the LBNF shutdown (Q2FY26).
  Attempting to complete this RLS asap
  BOEs in parallel
  We will share the resource requirements from this RLS with DOE
DOE/HEP has informed us that they will be able to provide the funding profile to be utilized for CD-1 at the end of August.
  Upon receipt we will iterate the RLS to match the CD-1 profile
Dates
  Director’s Review November
  DOE IPR/ICR January/February 2018
  ESAAB (CD-1) March/April 2018
Note: The technically limited schedule will require a CD-3a in FY18, i.e. in advance of CD-2
  Nb and initial cavity procurements
  Site prep

## Slide 15: CD-1 Timeline/Status
CD-1 Profile from HEP
RLS
BOEs

## Slide 16: RLS status
WBS for BOE
In P6
Detailed Plan
Close to ready/ready
Advanced
Preliminary
~70% of Total PIP-II Project costs

## Slide 17: Project Management
Personnel
  Close to publicly announcing the new Project Engineer
    Working on job description
    Don M will stay for a transition period
  Donato Passarelli succeeding Leonardo Ristori as L3M for SSRs
    Leonardo to devote 75% of time to LHC crab cavities
    Will spend 25% supporting Donato on SSRs
Issues that are impeding progress
  STC operations have not been reliable lately
  Lab2 cleanroom not complete – requires further investment to make usable
  Engineering support for SRF
    Tom N (Mu2e) and Chuck G (LCLS-II) have very minimal availability
    Much of the slack is being taken up by Vikas Jain (RRCAT visitor)
      He returns to India in October → need to identify a replacement
    New guest engineer arriving this month to support SSR1
  Long-term issue: how to support M&O of srf test/fabrication infrastructure

## Slide 18: Summary
Moving toward CD-1, with a newly-modified plan
  Delaying by ~4 months to allow alignment of schedule and funding profile.
India collaboration is taking a lot of attention
  Improving interactions and information exchange
Need to add more staff prior to CD-1
  Essentially there