## Slide 1: PIP-II staff plan
PIP-II RLS is in reasonable shape in terms of logical structure, and M&S, for ~80% of the scope of work
PIP-II staff plan is a potential bottleneck.
For CD-1 a staff profile has to be produced. It is the result of the sum of each sub-project FTE contribution.
In order to have a first screening on staff for your sub-project, use the schedule as a driver and try to quantify them per BOE
112
ESS Example

## Slide 2: Example CF
Chart: 
| FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25
 | 0.3 | 0.5 | 1 | 2 | 2 | 2 | 2 | 2 | 1.6 | 0.8

## Slide 3: Guideline
Fix the “regular” FTE per all the FY (e.g. L2/L3 managers)
Add per FY of key FTEs, using your schedule as guideline
  At the BOE level
Chart: 
| FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24
Cryogenics | 1.8281 | 3.4338 | 2.8388 | 1.3778 | 2.043 | 5.1109 | 5.7353 | 7.0979 | 6.8122
Example Cryogenics