## Slide 1: Magnets Sector Update
  LCLS II – Quadrupoles: SPQA105 shipped to MP9 for assembly, SPQA106 cold test in progress.
  LARP – First 4.2 m long coil QXFA101 (production length) impregnation is complete. Short model MQXFS1c is ready for cool down with increased axial pre-stress. LARP is preparing for Director’s review in June, followed by CD1
  AS – MI spare Lambertson (MLAW) has been delivered to AD for residual gas analysis. LBNF kicker assembly is in process, all parts have been delivered after long wait for the ferrites (1 year delay)
Mu2e – Making steady progress toward acceptance test of the Transport Solenoid proto module in the HAB facility.
G-2 – Inflector conductor is fully insulated and winding tooling is in place. In preparations for testing samples of NbTi shielding
MDP 15-16 T dipole R&D – ROXIE and FEA modeling with stress management continues for 15T dipole, results will be presented at IPAC2017 next week. All 4 layers wound for coil No. 1, preparation to cure the coil is in progress.
Infrastructure (IB1) – Prepared IB1 test systems for site-wide power outages on 5/15
Safety (HAB) – responded to concerns about workplace clutter and safety with thorough cleanup

## Slide 2: SRF Sector Update
R&D
  Two 3.9 GHz 1-cell cavities were vertical tested to find a better processing recipe. Work is in progress
  High gradient R&D: Second 2.6 GHz was prepared. Two cavities are ready for testing this week (5/16)
  Several 1.3 GHz cavities were processed for testing. Basic R&D for surface resistance studies
  One 1.3 GHz 9-cell cavity was vertical tested. Needs new testing hardware for a re-test.
  High gradient alternative shape: One 1.3 GHz 9-cell cavity is pending furnace treatment (5/15 week)
LCLS-II
  RI dressed cavities CAV0076 (1.3 GHz) qualified.
  3.9 GHz 9-cell 3HRI02 bare cavity exceeds specification (now three 3.9 GHz bare cavities passed qualification)
  CM02 Testing is in progress.
    Q0 was measured. Average Q0 is 1.8e10. The CM02 cavity material does not expel flux. More test is needed after another slow cool down on 5/16.
  CM03 WS5 with instrumentation completed. Beamline pump-down is planned on 5/16.
  CM04 is in WS3 stage with inter stage QC. Lower shield welding is planned for today, 5/15
  CM05 WS1 string assembly finished and rolled out of clean room.
  CM06 WS0 is in progress
    Five cavities completed WS0 cold end coupler installation.
  CM07 has one qualified cavity
PIP-II
  One spoke cavity horizontal test assembly is in progress at STC test cave.
  Resonance control test is in progress.
  One 5-cell 650 MHz cavity is under optical inspection.
  One 1-cell 650 MHz cavity will be EP’d on 5/16.