## Slide 1: Monday May 15th Schedule

## Slide 2
Time | 
0500 | Confirmation call to ComEd that we can proceed. If the weather is bad we may not proceed (Tuesday {5/16/17} is the contingency day for power outages and access)
0500-0600 | Turn off accelerators, prep controls and accelerator systems for no cooling. Initiate necessary switching off.
0600 | CUB turns off cooling in preparation for the first power outage. No cooling/heating.
0630-0700 | First power outage for Master Substation loads. Loads transferred to Kautz Rd to establish power to site.
0700 | CUB recovers cooling ~ 40 min. Access keys available
0700-0900 | ComEd LOTO to isolate SW2002.
0900-1300 | ComEd repair/replace SW2002
1300-1630 | ComEd returns SW2002 to service. Access keys returned by end of day shift
1630 | CUB turns off cooling in preparation for the second power outage.
1700-1730 | Second power outage for Master Substation loads. Loads transferred from Kautz Rd to re-establish power to site.
1730 | CUB cooling recovery
1800-??? | Start to turn complex back on. Deal with problems. Establish physics…..get ice cream