## Feuil1
Subsystem | No | Recommendation | Reply
CRP, electronics,DAQ | 1 | Consider if alpha source testing could be done during acceptance testing of every LEM module so that operating and maximum allowable voltages can be determined accurately before installation. | Testing each LEM individually with an alpha source does not appear to be realistic given the present schedule. The Saclay high pressure chamber cannot accommodate more than one TPC fof gain measurements with a source. The minimal amount of time required for the whole process, including LEM installation, pumping, baking in dry air, pumping again before filling with argon, charging up and testing, is 2 days. The total amount of time needed to test all the LEMs produced with the current setup would therefore be nearly 300 days. Moreover, the test with a source can only be done at one position at a time, with an illumination of about 10cm2 (@ 3.3 bar absolute pressure), as there is no remote system to displace the source inside the vessel. However, during the LEM production phase, one could envisage to test a few LEMs (e.g. 1/18) to check the uniformity of the construction quality of the LEMs. The main parameters that define the gain uniformity within a LEM and from LEM to LEM are linked to the geometrical accuracy (e.g. thickness, rim and hole size). We believe those parameters can be controlled to a large extent since the supplier will provide for each LEM, sample measurements. The foreseen tests in Saclay of the LEMs will consist in HV tests above 3kV in argon @ 3.3 bar, after baking in dry air. We believe we can test 2 batches of 6 LEMS per week. These tests will be performed with a well-defined procedure and controlled conditions so that they should allow bad LEMs to be identified and discarded.
| 2 | A cleanliness program should be defined and it should be verified that the proposed assembly sequence meets its requirements - many particulates produced during installation will end up being captured at the liquid surface by the extraction grid combs. | The pre-assembly and assembly of the detector as well as the cryostat itself should respect certain cleanliness standards. What should be avoided is the presence of small but macroscopic debris (such as metallic residues from drilling , FR4 fibres, ..) that could indeed float to the surface and disrupt the charge extraction. To avoid this issue all activities from pre-assembly of subcomponents to assembly of detector will take place in class 100'000 clean room (also called grey room). During pre-assembly: 1) all detector subcomponents will be pre-assembled inside class 100'000 clean rooms and workers will wear appropriate clothing to make sure that no dust or fibres get trapped in various parts. 2) Before entering the clean room, all delivered subcomponents will undergo thorough cleaning especially in areas near drilled holes where residues from the manufacturing process could still be present. 3) All the welds will be throughly cleaned with alcohol+ DM water and visually inspected. During detector installation: 1)the cryostat and CRB will both be at slight overpressure with respect to the experimental hall. Filtered air is blown from the cryostat manhole and exits throughout the CRB. The cryostat will follow the minimal requirements of a class 100'000 clean room. 2)The transport boxes of the detector subcomponents will be wrapped or have an envelope that is to be removed in the CRB prior to entry in the cryostat. 3)Once the subcomponent is removed from the box we foresee a visual check an if required additional manual cleaning of all the parts that enter the cryostat. 4)The detector installation purposely only consists of processes involving bolting, clipping, cabling etc... No soldering, drilling, wire stripping, or potential dirty activity will take place. We note that one activity that will require particular attention is the closure of the TCO, the details are still under discussion with the Neutrino Platform.
| 3 | Consider protecting the CRPs with a removable film after their installation. | Depending on the installation sequence, the CRP zone may be completely protected by the first modules of the drift cage. If not, a dedicated protection will be foreseen.
| 4 | Develop a tension verification system for the extraction grid wires to ensure that these are as designed and to avoid wires breaking with cooling as this would jeopardize the operation of the whole experiment. | Although the design of the grid makes a tension verification not mandatory, it can still be checked on the weaving tooling thanks to an harmonic system. Once the grid is installed on the CRP module, this checking is made impossible by the weaving pattern of the grid subsets. However the grid tension is not directly controlled, the dimensions are carefully measured (in collaboration with the CERN metrology team) on the frame and on the tooling, to insure the right tensioning. A dedicated measurement procedure has been defined.
| 5 | Test the long-term creep of the brazed extraction grid wires and consider a secondary solder point to prevent detachment. | A grid subset will be assembled as soon as possible, so that the brazing will be tested during a long time. For the cold conditions, materials used are similar to the 3x1x1. By now, no brazing problem has been pointed out.
Photon detection system, Slow control | 1 | The specifications for the maximum weights and torque of the cable tray have to be calculated to properly dimension the PMT and Slow Control cabling | The Neutrino Platform collaborators will take care of the designing and dimensioning of the cable trays from the FTs to the PMts location including all the necessary calculations. The final design is not yet completed, the total amount and total weight of the cables are defined and available.
| 2 | The possibility to perform thickness tests after the TPB coating employing ICARUS facilities at Padova should be investigated. | In progress (by Thorsten): preferred option at the moment is to perform the thickness measurement directly at CERN using a mylar foil
| 3 | Finalize the design of the PMT attachment based on the cryogenic glue. | It was already foreseen in the current design to attach the PMT support at its center to the membrane by using cryogenic glue. This recommendation is fully taken into account in the detector construction
HV, Field Cage, Cathode | 1 | Establish a consistent electric field threshold to all subsystems | A consistent requirement of max field of 30 kV/cm is taken into account for all detector parts. In the case of the HV feedthrough it is not practically possible to achieve this figure nearby the termination of the ground outern conductor.
| 2 | Perform a detailed 3D FEA of the E field near the bottom of the HVFT degrader and its interconnect to the cathode frame. | The simulation is in progress
| 3 | Increase the radius of curvature on the rectangular tube on the cathode frame | In progress (see Adamo presentation at the TB of May 31)
| 4 | Provide more data to demonstrate the utility of the degrader rings | 3D simulations in progress. We know locally we have higher electric fields on the surface of the first rings. However, with the degrader we have a field in the liquid argon (several meters region) below 10 kV/cm, while without degrader is 25 kV/cm, at 300 kV.
| 5 | Ensure a safe /redundant termination to ground of the field-cage circuit. | It is indeed foreseen to have a safe redundant termination to ground of the field cage circuit. This point was described in a grounding document distributed to the Technical Design Review commitee the last day of the review