## Slide 1
Steve Holmes
PIP-II Project Management Group
28 June 2017
PIP-II Project Manager’s Report

## Slide 2: Outline
Goals
Financials
ES&H/NEPA
Technical/R&D
India Collaboration
Project Management
  CD-1 Status

## Slide 3: Project Goals
Profile unlikely to survive the summer
  PBR is for $14.0M in FY18
  Balance of years due from OHEP by August 31
Milestone | Planned | Actual or Forecast
CD-0 | Q1 FY2016 | November 12, 2015 (A)
CD-1 | FY2017 | Q2FY2018
CD-2/3a | FY2019 | FY2019
CD-3 | FY2020 | FY2020
CD-4 | FY2026 | FY2026

## Slide 4: Goals for FY17
New goal is to achieve CD-1 in early CY2018
  RLS
  ICR
  Documentation
Financial Goals
  Live within the provided budget: $21.03M (includes FY16 carryover)
  Cross the FY17/18 border with ~$2.0M unobligated (carryover)
ES&H Goals
  Be prepared to initiate Environmental Assessment on 10/1/17
R&D Goals
  Release CDR
  Complete PIP2IT MEBT
  Keep HWR and SSR1 on track for CY2018/19 delivery
India Collaboration Goals
  Meet 2017 deliverable milestones
  Establish confidence between the partners
Management Goals
  Complete all CD-1 documentation and successfully navigate required reviews
  Fill missing positions on organization chart

## Slide 5: Financials (inception through 4-30-17)
Spending since CD-0
  OPC/Project Office, Civil Const, and SC Linac are only areas of activity to date
  4.6% complete

## Slide 6: FY17 Financials (through 5-31-17)
RIPs: $138K
Current Management Reserve: ($75K)
Demands against Management Reserve: $679K

## Slide 7: FY17 Financials/Management Reserve
Budgets adjusted following FY17 forecast-to-complete in April
Several funding change requests were approved, most notably
  HB650 cavity dressing + contract designer (shared with SSR)
  RFQ new couplers/tuners
  SSR1 CM parts
Current Management Reserve: ($75K)
  Includes $130K of uncosted obligation on Pavac contract that DOE has agreed to move from GARD to PIP-II (in June)
  Note: We have not seen funds yet, although we have obligated the work. Potential issue with recoloring or money?
Unfunded Requests: $679K
  Lab 2 Improvements $338K
  PIP2IT RFPI $15K
  LLRF $56K
    Partially funded
  CF subsurface documentation $20K
  Environmental Assessment $250K
Not shown in MR: Anticipate SWF underrun of up to $2M

## Slide 8: FY18 Strategy @ $14.0M
Currently projecting FY17 underrun of $1.8M
Budget FY18 for $15.8M
  Support 40 FTE
    Standing army (20) + priority activities (20)
    Compare to 54 FTE budgeted in FY17
  SWF+OHD $10.7M
  M&S + OHD $5.1M
  Schedule ~$1M of M&S in Q4 FY18 = virtual reserve
Priorities
  CD-1
  CDS install at PIP2IT
  MEBT absorber at PIP2IT
  HWR (pCM)
  SSR1 (pCM)
  HB650
  CF design start (site prep and buildings)
  EA
Issues
  Essential that we get operations support for Lab2 ($338K w/ovhd)
    We need this for SSR1 assembly
    We have requested from Laboratory Reserve
  Booster injection design

## Slide 9: ES&H/NEPA
Wetlands Jurisdictional Determination
  FSO has submitted the application package to USACE (Apr 27)
  Fermilab personnel met with USACE representative to provide overview (May 12)
  If accepted, the wetlands located in the PIP-II footprint would be designated non-jurisdictional
    Process should take ~ 1 year
  If denied, a new wetlands permit application would be submitted in FY2018 to allow USACE the 1 year review period in order to meet a PIP-II start work date of late FY2019/early FY2020.
Environmental Evaluation Notification Form (EENF) ready for submission to DOE/FSO
  Expect to forward to FSO this summer and initiate selection of PIP-II NEPA/EA contractor before the end of FY17

## Slide 10: Technical/R&D Status
PIP2IT
  2017 goal to complete MEBT and commission with beam
    5 mA × 1 ms × 20 Hz to dump
    Measure kickers’ effects on the beam
  Completed installation of MEBT-2. Operations have resumed with 4 MEBT triplets, additional buncher cavity. Transmission to dump at ~99%, starting commissioning of chopper kickers
  Final 3 triplets to complete
  MEBT arrived @FNAL,
  2 now at CMTF,
  1 being measured in TD.

## Slide 11: Technical/SRF R&D Status
HB650
  Goal is to qualify and dress four cavities in FY17
  Two cavities are qualified
  Third near spec
    Going through “nitrogen infusion” processing
  Fourth went through second vertical test last month
    High FE; will require reprocess
SSR1
  Dressed cavities are showing FE in full power tests (at STC)
  This is delaying the SSR1 schedule
  Investigating
Couplers
  New RFQ coupler design has been completed and reviewed
    Procurement initiated
  HB650 couplers RFP has been released
    Best value procurement with pre-qualified vendors

## Slide 12: India Collaboration
Joint R&D Project Document
  Addendum II: Documentation of Fermilab engineering deliverables.
    Close to convergence – shooting for end of June
  Addendum I: Modification to DAE deliverable dates to reflect delays in R&D program to FY2020
    DAE to make Addendum I consistent with Addendum II
Visitors
  We have been authorized by DAE Secretary to restart the long- and short-term visitors programs
    Can accommodate 36 months LT, and 12 months of ST in FY18 budget
  Wish list for second round has been developed by DAE
Exports
  Procurement of MOSFETs for SSR1 RF sources is becoming critical
  No distributor willing to sell if BARC is end user (business decisions)
  Options:
    Convince distributors it is in their interest to apply for the require export license
    Convince Department of Commerce to remove BARC from entities list for Annex I activities
Upcoming Visits
  Leonardo Ristori et al will be visiting BARC in August for:
    Witnessing of SSR1 He vessel welding
    Review of SSR2 cavity design
IIFC Meeting
  Preparations initiated for a meeting at BARC in October
Schedule in doubt.
These cavities must be on-site 12/31 to end up in SSR1 pCM

## Slide 13: Project Management/CD-1
Assumptions Document approved (Mar 9)
Functional Requirements Specification approved (Mar 17)
Lab MOU draft under internal (project) review
Critical path is:
  RLS (see L. Lari presentation)
  BOEs (see P. Derwent presentation)
Risk Registry
  140 approved risks
  Undertaking initial calculation of associated contingency
Agreement with AD on division of scope between PIP-I+ and PIP-II
  Associate cost impact/savings is:
    Point estimate: $17M
    Upper cost range: $21M

## Slide 14: Project Management/CD-1 Strategy
We are currently developing a “technically limited” RLS, with a goal of PIP-II completion coincident with completion of the LBNF shutdown (Q2FY26).
  RLS includes DOE funded activities only
  Earliest finish date appears to be ~Q1FY27; limited by SRF assembly and testing facilities
We are concentrating on eight level-3 sub-projects, representing ~70% of the project cost.
  These have all been through internal review and are frozen for the moment.
  All are showing increases of several x 10% as compared with the CD-0 estimate
  Some (currently) show a reduced scope of DAE deliverables as compared to CD-0 estimate
    Need to normalize this
We have committed to sharing with DOE the funding profile associated with these eight level 3 sub-projects at the IPT meeting on June 29 (tomorrow)
  See Luisella’s presentation
DOE/HEP has informed us that they will be able to provide the funding profile to be utilized for CD-1 at the end of August.
  Upon receipt we will iterate the RLS to match the CD-1 profile
Dates
  Director’s Review November
  DOE IPR/ICR January/February 2018
  ESAAB (CD-1) March/April 2018

## Slide 15: RLS status
~70% of Total PIP-II Project costs
Internal Review
WBS for BOE
In P6
Detailed Plan
Close to be ready/ready
Advanced
Preliminary

## Slide 16: Project Management
Personnel
  Allan Rowe has succeeded Don Mitchell as Project Engineer
  Assisted by Jim Steimel as Project Engineer for Electrical Systems
Issues that are impeding progress
  Lab2 cleanroom not complete – requires substantial further investment to make usable
  Engineering support for SRF
    Tom N (Mu2e) and Chuck G (LCLS-II) have very minimal availability
    Much of the slack is being taken up by Vikas Jain (RRCAT visitor)
      He returns to India in October → need to identify a replacement
  Six DAE long-term visitors will be returning India over Sep-Nov
    Replacements TBD: Budgeting four people arriving Jan 1.

## Slide 17: Summary
Moving toward CD-1, with a newly-modified plan
  Delaying by ~4 months to allow alignment of schedule and funding profile.
India collaboration is taking a lot of attention
  Improving interactions and information exchange
Need to add more staff prior to CD-1
  Essentially there