## Slide 1
Luisella Lari
PIP-II PMG meeting
28 June 2017
Resource Loaded Schedule Status
Thanks to L3/L2 managers
and PIP-II Project Management Team

## Slide 2: Outline
PIP-II RLS news
PIP-II RLS draft cost profile
PIP-II RLS FY18 obligations
PIP-II RLS next steps

## Slide 3: PIP-II RLS news
The PIP-II Project requires a complex RLS: a reminder from May PMG

## Slide 4: PIP-II RLS news
Internal
Reviewed
WBS for BOE
In P6
Detailed Plan
Close to be ready/ready
Advanced
Preliminary
~70% of Total PIP-II Project costs

## Slide 5: PIP-II RLS news: major changes with respect CD-0
CF cost profile updated in P6, following the new estimations (May 2017) for construction phase (about 40 M$ on top of CD-0 estimation).
CMs (but HWR) technical driven RLS updated:
  With the availability of Test Facilities  i.e. All the Dressed cavities will be tested in VTS and about 30% in STC/HTS-2, including samples test for IIFC dressed cavities (@ CD-0 it was foreseen not to test any IIFC dressed cavities and to test 50% of FNAL cavities).
  Including RF tests for each CM in PIP2IT or CMTS before final installation in PIP-II tunnel (not foreseen @ CD-0).
RF Power RLS includes the circulators as part of the FNAL scope (about 3 M$ cost identified as in-kind contribution @ CD-0)
Cryogenics RLS includes the CM bayonet boxes as part of FNAL scope (about 4 M$ cost identified as in-kind contribution @ CD-0) .

## Slide 6: PIP-II RLS draft cost profile in P6
In P6 in May
Now in P6: including escalation and overhead
Please note that P6 is not yet including the SWF costs for CMs and RF Power and Contingency

## Slide 7: PIP-II RLS draft cost profile in P6
In P6 now

## Slide 8: PIP-II RLS with respect to Early CD-4
Early dates for CD-4 presented at the November Review 2016
End on March 2026  end of RF test in PIP2IT for the last SSR2 CM.

## Slide 9: PIP-II RLS obligations for FY18
Technical driven schedule in P6, including the SWF costs for CMs and RF Power is over budget for FY18
About 3 M$ in obligations for FY18, mainly for SSR2 Nb and LB/HB650 Prototype Cavities and HWR SSAs
NB: FY18 Budget foreseen is 14+1.8 M$

## Slide 10: PIP-II RLS draft cost profile in P6
Total P6+SWF costs
= 381 M$
i.e. 70% of the Total Budget

## Slide 11: PIP-II RLS next steps
Include SWF costs in P6 for CMs and RF Power;
Checking/Review the RLS Critical Path (meeting on July the 10th);
Review the RLS (70% in cost) - on the point of view of planning - at the end of July by the OPSS office;
Continue the RLS internal Reviews;
Include the missing plans and checking possible discrepancies with CD-0 data;
Produce the obligations profile for all FYs;
Align to FY18 budget?
Thanks to L3/L2 managers
and PIP-II Project Management Team