## Slide 1: Muon (g-2) to ≤ 140 ppb State of the Experiment
David Hertzog (Washington) and Lee Roberts (Boston)
for the E989 Muon (g-2) Collaboration
“Right now we have a symphony of issues … “
From a C. Polly email
And we are having FUN solving them and realizing first beam after 9+ years of planning

## Slide 2: g-2 Theory Community very active Strong support from DOE and Fermilab

## Slide 3: “What the PAC would like to hear …” Steve Geer
What would you do if FY18 run is ~3 months only
What would you do if there is no FY18 run
Run Plan for a FY18 full-year run
- p. 3
I have added to that charge:
  Status of commissioning run
  Health Test of Subsystems
  Flash plots of performance to date
… which I will present first

## Slide 4
Goals of Commissioning run
Test / exercise all experimental equipment with beam
Establish muon storage rates to check TDR estimates
Acquire enough statistics for meaningful offline analysis development
and, we should not forget
Train the crew and be ready for Physics Runs in early FY18
- p. 4
Nominal commissioning schedule:
May 23rd: 1 fill / minute*
June: 6-8 fills / minute
July 7th: Shutdown
*720 fills / minute when running fully

## Slide 5: Test / exercise all experimental equipment: The wp Measuring Systems
Precision shimmed Field
Fixed NMR probes
NMR Trolley system
NMR Plunging probe (just installed)
Online monitoring
Field DAQ
✔
✔
✔
✔
~✔
✔= almost perfect; ~✔= not yet optimized, fully tested, or complete
All working
FID
~✔

## Slide 6: Test / exercise all experimental equipment: The Muon Storage Optimization Systems
T0 start counter
IBMS imaging system
Inflector
Pulsed Electric Quadrupoles
Fast magnetic Kicker
Fiber Harp x/y planes in vacuum
✔
~✔
✔
~✔
~✔
~✔
✔= almost perfect; ~✔= not yet optimized, fully tested, or complete
m+
x
B
m coming at you

## Slide 7: Test / exercise all experimental equipment: The wa Measuring Systems: General conclusion “working very well”
In vacuum straw trackers
PbF2 calorimeter arrays
800 MSPS digitizers
6-laser, distributed calibration system
Real-time GPU processing
MIDAS DAQ
Online Data Quality Monitors
Nearline / Offline processing
Slow Controls
✔
✔
✔
~✔
~✔
✔
✔
~✔
~✔
✔= almost perfect; ~✔= not yet optimized, fully tested, or complete

## Slide 8
Creating the Muon Beam for g-2
8 GeV p batch into Recycler
Split into 4 bunches
Extract 1 by 1 to strike target
Long FODO channel to collect p  mn
p/p/m beam enters DR; protons kicked out; p decay away
m enter storage ring
Intensity profile is 120 ns wide with “W” shape

## Slide 9
This year we are bypassing the DR
Protons: 60
Pions: 4
Muons: 1
At Storage Ring Entrance
And in front of Inflector with our IBMS detector
X Y
X
Y

## Slide 10: Recent success: May 23rd
First Beam Crashes into Calorimeters

## Slide 11: Recent success: June 5
First evidence of stored protons from some hand-selected events
Image from Tracker of escaping proton at late times

## Slide 12: How do we tune in real time? (this is online displays)
Now dumped out and integrated as proxy for storage.
500 ms
 Now stored 
Protons scraped out
Sweep the following to optimize Storage of Protons (muons)
  Kicker timing
  Quad strength
  Inflector current
  Incoming beam x,x’, y,y’
  Incoming beam focus parameters
We have online monitors of:
  Stored protons
  Stored muons
  Incoming beam composite intensity

## Slide 13: Rich information on stored beam from in-vacuum Fiber Harps arrays
Looking downstream as a Muon or Proton would

## Slide 14: What a high-energy positron looks like in our calorimeter
~3 GeV
Online pre-calibration gain of 1294 crystals using Laser system for absolute PE / pulse integral

## Slide 15: 1294*/1296 crystals working and calibrated in Calorimeter
*easy to fix after run ends and we have access
Muon Decay Positrons
Escaping protons
Spectrum “as expected”
Muons Here
Hit positions “as expected”

## Slide 16: Recent success: June 11
First evidence of stored muon precession

## Slide 17: Proton and Muon Fast Rotation in calorimeters (could not see this at BNL so easily)
Protons only
Muons only
CBO
g-2 precession

## Slide 18: Tracker & Calorimeter working together
DT = Calo(t) – Tracker(t)
X

## Slide 19: Getting better … : June 25

## Slide 20: Transmission and Storage so far …
 | Diktys simulation 1E12 POT | June 18 1.3E11 POT | Normalized to POT (*)
Into M2 Line (IC804) | 6.77E8 | 6.60E7 | 80%
In downstream M3 Line (IC740) | 2.12E8 | 1.86E7 | 81%
In M4 Line (IC902) | 1.16E8 | 0.60E7 | 47%
End of M5 Line (IC025) | 1.00E8 | 0.27E7 | 29%
Ion Chamber readbacks versus simulation
(normalized to protons on target)
Transmission and Muon Storage Fraction ~ 1/6 of expectation at this time:
  Not yet optimized:
    Inflector transmission (possibly significant)
    Quad HV (limited by present vacuum)
    Kicker strength (1/3 needs repair)

## Slide 21: 2015 Schedule overview (PAC talk 6/15)
MC-1 (GPP)
g-2 Cryo Plant (AIP)
Ring Assembly
Shim Field
Prep Chambers/Install
Construct/Install Sub-systems
Accelerator Modifications
Ring cold ready for operations
Experiment ready for operations
Accelerator ready for operations
Ring Cold
Detector/DAQ Commission
Beam
Tune-up
Physics Production Running
Analysis Tools Development
Mock Data
2nd Results
Full Running Intensity
Construction (Project & Muon Campus):
Operations (Laboratory):
Analysis (Collaboration):
1-2 x BNL statistics
~5-10 x BNL
21 x BNL
Final Results
1st Results
In 2 years, schedule slipped only 3 months
Nice job by all

## Slide 22: 2017 PLANNING
Mar/Apr 17
May/Jun 17
Jul/Aug 2017
Sep/Oct 17
Nov/Dec 17
Jan/Feb 18
Mar/Apr 18
May/Jun 18
Jul/Aug 18
Accelerator commissioning
Finish proj. scope
Physics production running + continued intensity tune-up
p
Shutdown
p
DR comm. + intensity ramp up
First beam available
to ring w/ protons
Additional ring/detector
commissioning
Shutdown
m
Superconducting Main Magnet and Inflector Up Reliably

## Slide 23: If FY18 Run is 3 months long: (factual statements)
AD estimated 6 months to achieve full intensity and rep rate:
  1012 POT/fill, 90% transmission, 12 Hz operation (as expected in our TDR)
This year, 3 months well used to bring beam to ring, even with known rep-rate and flux limitations:
  Muons to ring entrance ~10-3 / hour compared to when fully operational
Completion of tuning & commissioning in FY18 will require 3 months
  Install new pulsed septa magnets
  Commission all pulsed power supplies for 12 Hz avg / 100 Hz bursts
    Target station lens and pulsed magnet
    Delivery Ring injection and abort septa
    Delivery Ring injection, extraction, and abort kickers
The Storage Ring transmission and muon capture efficiency low
AD Plan

## Slide 24: If FY18 Run is 3 months long: (impact statements)
Nearly the entire period will be a dynamic tuning / optimization exercise to achieve the required running conditions.
Non-optimized beam will provide opportunity to further commission experiment and muon storage parameters
Precession data obtained should compare to BNL E821 statistics
BUT! Depending on the quality, it may not provide a “physics” quality data set unless we get at least 1 month of good and stable conditions with all systems functioning well
THE IMPACT
  Lose a full year on our Physics Production calendar
  Highly inefficient use of time and resources
  Likely lose critical (young) people who have brought the experiment up to a running condition. These are the experts. Many are on fixed-term contracts and thesis calendars.
    Run restart 9 months later will be at risk if some experts depart
    Could also lose critical Fermilab technical support
  Impact to Mu2e is likely if g-2 is slowed significantly

## Slide 25: If there is NO FY18 Running at all…
A Doomsday Scenario for g-2
The Experiment is built and ready after 9+ years of planning, design, construction
The Experiment has largely been commissioned.
It’s too delicate to simply stand down for 15 months and be expected to come back alive without serious problems
International partners will be dumbstruck
University grants devastated and groups diminished
Trust destroyed

## Slide 26: Summary
Our Run Plan for (full) FY18 cycle
  Use Shutdown to address known issues
    Vacuum improvement  kicker and quad increased HV expected
    Small noise issues on some signals; new T0, additional IBMS planes
    Integrate final aux systems into DAQ
  Tune our systems using parasitic beam during AD muon campus development
  Take high-quality data aggressively until 2018 summer shutdown
What happens if it’s only 3 months …
  Mostly commissioning
  Setback of 1 year on physics calendar
  Delayed “discovery” window for new physics
  Mu2e likely impacted
And worse? No running?
  Honestly?
- p. 26
The Collaboration continues to thank the Lab for strong support

## Slide 27: Systematic Errors on wp (ppb)
Brookhaven E821
FNAL
- p. 27
The Muon (g-2) Collaboration, Fermilab PAC – 24 - June – 2015

## Slide 28: Systematic Errors on wa (ppb)
Ring Team
Detector Team
Detector Team
- p. 28
The Muon (g-2) Collaboration, Fermilab PAC – 24 - June – 2015

## Slide 29: DAQ Performance
MIDAS DAQ is reading data from all 24 calorimeters, Laser system, tracker, fiber harps, Quads and IBMS, as well as 33 slow controls.
Total uptime after first 25.5 days is 66% with almost 3M fills collected.

## Slide 30: The Laser Calibration System is fully installed and operational

## Slide 31: Measuring wa [ from BNL realized  FNAL goals ]
Statistical error: [ 460 ppb  100 ppb ]
  x21 in statistics, ~1.8 x 1011 events
Producing and storing 21x more muons than BNL requires a new beam development concept
AND: Understanding at a deep level, the beam production, polarization, phase space properties.

## Slide 32: Commissioning beam will have a large proton and pion background.
Muon Campus
Muon Campus without DR (g-2 commissioning)
D. Stratakis, GM2-doc-5664

## Slide 33: g-2 beamline work during shutdown
Install new pulsed septa magnets
  Commissioned using old Pbar septa which does not have cooling to run at full g-2 repetition rate
Commission all pulsed power supplies for 12 Hz avg / 100 Hz bursts
  Target station lens and pulsed magnet
  Delivery Ring injection and abort septa
  Delivery Ring injection, extraction, and abort kickers