## Slide 1
Cons Gattuso
All Experimenter Meeting
7/17/17

## Slide 2: Shutdown Planning Guidance
Start Date
  July 7th Friday
    12:00 beam was turned off
  July 10 Monday
    Access to the tunnel commenced
Duration
  ~16 weeks duration
    Turning on Week of October 23rd
      1-2 Week of Start up/ Commissioning

## Slide 3: Proton Source Shutdown Work list
RIL
Source maintenance
Einzel Lens maintenance
RFQ maintenance
General maintience
Linac
Marx modulator project -~8% Done
  Fabrication and Testing underway
    Planning to installed 2 modulator in 2017
      Duration ~6-7 Weeks for the removal of old and installation of new
LE tasks (performed by Linac techs) ~40% Done
  Modulator/driver maintenance
  Inductrol maintenance
  Water skid maintenance
HE tasks (performed by Linac techs) ~40% Done
  CS & PFN maintenance
  PFN cap bank maintenance
  QPS PM
  Water skid maintenance
  Heat exchanger maintenance
Booster
BRF21 and BR22 installation ~6-8 weeks
IPM Installation
  Controls Rack installation
  Tunnel component installation
General Maintenance
  Power supplies
  Cooling Systems
  Vacuum
~10% Done
~10% Done

## Slide 4: LRF2 Disassembly

## Slide 5: Main Injector/Recycler
MI
  Replace MI RF station 6 or 4 ~5% Done
    ~1.5-2 weeks
  Ion pump maintience
    ~1-2 Weeks
  8 Gev line
    Ion pump Maintenance
      ~1-2 weeks
    Vacuum leak check
      ~1-2 Weeks
    Multi wire replacement (2)
      ~1 Week
  General maintience for MI/RR ~5% Done
    ~2-3 weeks
      Tunnel and service building
  Replace the beam pipe in Q504 -50% Done
    Vacuum leak on BPM feed through
  Switching Flourinert in the MI-10 and 60 kicker systems
    Replacing FC-77 to FC-40
RR
  TSP upgrade from 106-229 -~12% done
    10-11 weeks
  Aperture improvement at the RR 402 and 520 locations
    ~3 weeks at the 402
    ~1.5 weeks at the 520 ~3% Done
  Recycler Abort lamberstons replacement
    ~3 weeks at the 402
  Recycler Sextupole stand change out ~2% Done
    ~3 weeks
  New Pinger installation in the 10 region
  Rebuilding and putting back into operations RRRF Anode power supply ~10% Done

## Slide 6: Tunnel Survey (comparing 8/1/16 and 7/10/17)
~30-40% Reduction
Tsp 2 IP dose reduce by ~1800 person-mrem

## Slide 7: Tunnel Work
Installing first of 19 vertical sextupole stands in Recycler

## Slide 8: External Beam line
P3 rough vacuum ~5% Done
  F3 House IP to Turbo Station upgrade (~2 weeks)
    Run 4" vacuum pipe from service buildings down stairwells to tunnel
    Install Roots blower stations in service buildings, one per house.
    Switch controls over to Tevatron CIA crates, rename parameters
    Remove and cap ion pumps.
  Cable mitigation in the Meson and Neutrino Muon areas: (~6-7 weeks)
Separating the Booster 95 LCW system from Switchyard (~3-4 weeks)
  Switchyard would be its own separate stand alone system. Feed from the F-Sector old MR system.
  On hold until Mid August
    Osprey Fly the coop
BNB
  Relocation of the of the
  DI bottles (~2 weeks)
~5% Done

## Slide 9: External Beam line (continued)
NuMI (~10-12 weeks)
  Target removal for beam scan of the horns
  General maintience
    Dehumidifiers
    Replace Filter and water in the Absorber and Decay pipe cooling system
    Drain tile cleaning
    Ext.
  Water system repair
    Repaired cracked nipple on LCW supply manifold in Pre-Target enclosure near Q115.
    Repaired cracked weld on Decay Pipe RAW system in Absorber Hall.
~10% Done
~90% Done

## Slide 10: Pictures
Open Wall to Target Hall
Top: Cracked nipple on LCW supply manifold near Q115.
Bottom: Newly installed copper pipe in Decay Pipe RAW skid

## Slide 11: Muon Campus Work
  Mu2e work
    M4 line installation ( first half to absorber) ~5% Done
      Stand and magnet and cable pulls installation (7-9 weeks)
  In support of g-2
    Delivery ring straight section
      Injection septa (1-2 weeks)
      Removal and reinstallation of ring for the M4 line installation ~ Done
      Rotate Q207 and Q210 BPMs ~ 2-3 days
      Relocation of ELAM ~2-3 days
    Abort line
      Extraction septa (1-2 weeks)
    Magnet replacement Internal water leaks
      H212 ~ 1 week
      Q211 ~2 days
      V742 ~ 1 week ~ Done
    Instrumentation Repair
      PWC and IC’s ~ 1-2 weeks

## Slide 12: Shutdown Duration Drivers
Linac Marx Modulator installation
  Station 2 upgrade is underway
  Station 3 will follow
RR TSP to IP conversion
  Progressing
Muon Campus Overlap with Switchyard crews
  Crew is responsible