## Slide 1
Cons Gattuso
Summer Shutdown Status
7/24/17

## Slide 2: Proton Source Shutdown Work list
RIL
Source maintenance
Einzel Lens maintenance
RFQ maintenance
General maintience
Linac
Marx modulator project -~25% Done
  Fabrication and Testing underway
    Planning to installed 2 modulator in 2017
      Duration ~6-7 Weeks for the removal of old and installation of new
LE tasks (performed by Linac techs) ~43% Done
  Modulator/driver maintenance
  Inductrol maintenance
  Water skid maintenance
HE tasks (performed by Linac techs) ~45% Done
  CS & PFN maintenance
  PFN cap bank maintenance
  QPS PM
  Water skid maintenance
  Heat exchanger maintenance
Booster
BRF21 and BR22 installation ~6-8 weeks
IPM Installation
  Controls Rack installation
  Tunnel component installation
General Maintenance
  Power supplies
  Cooling Systems
  Vacuum
~30% Done
~15% Done
~5% Done

## Slide 3: LRF2 Disassembly

## Slide 4: Main Injector/Recycler
MI
  Replace MI RF station 6 or 4 ~5% Done
    ~1.5-2 weeks
  Ion pump maintience
    ~1-2 Weeks
  8 Gev line
    Ion pump Maintenance
      ~1-2 weeks
    Vacuum leak check
      ~1-2 Weeks
    Multi wire replacement (2)
      ~1 Week
  General maintience for MI/RR ~10% Done
    ~2-3 weeks
      Tunnel and service building
  Replace the beam pipe in Q504 -95% Done
    Vacuum leak on BPM feed through
  Switching Flourinert in the MI-10 and 60 kicker systems
    Replacing FC-77 to FC-40
RR
  TSP upgrade from 106-229 -~20% done
    10-11 weeks
  Aperture improvement at the RR 402 and 520 locations
    ~3 weeks at the 402
    ~1.5 weeks at the 520 ~3% Done
  Recycler Abort lamberstons replacement
    ~3 weeks at the 402
  Recycler Sextupole stand change out ~2% Done
    ~3 weeks
  New Pinger installation in the 10 region
  Rebuilding and putting back into operations RRRF Anode power supply ~10% Done

## Slide 5: Work Stoppage
On Friday July 21st we had two VDPA (4-4-30 dipoles) fell off of there stands.
Normal installed configuration
8 magnets in total
4 in each of the decommissioned RR to MI beamlines

## Slide 6
Welder in position prior to magnet falling

## Slide 7
If the bottom of the magnet had been flat
z
x
y
Beam direction
up down
In out
Tipping force ~ 130 lb as designed
Tipping force ~40-60 lb

## Slide 8: Action taken
Complete work stoppage in the MI tunnel
Friday afternoon with safety's approval we started abating the immediate tunnel hazard.
  This consisted of removing 8 VDPA from there stands
  This was completed this morning
  Completed several walkthrough of the MI tunnel verifying that we don’t have any other issues
    A hand full of magnets will be looked at….
      Tip calculation run on them.
  We have also asked all of the other machines to complete walk throughs as well
    Magnets that may be issues in that are currently used in operations
    Stored in the tunnel
    Or in Decommissioned lines

## Slide 9: External Beam line
P3 rough vacuum ~45% Done
  F3 House IP to Turbo Station upgrade (~2 weeks)
    Run 4" vacuum pipe from service buildings down stairwells to tunnel
    Install Roots blower stations in service buildings, one per house.
    Switch controls over to Tevatron CIA crates, rename parameters
    Remove and cap ion pumps.
  Cable mitigation in the Meson and Neutrino Muon areas: (~6-7 weeks)
Separating the Booster 95 LCW system from Switchyard (~3-4 weeks)
  Switchyard would be its own separate stand alone system. Feed from the F-Sector old MR system.
  On hold until Mid August
    Osprey Fly the coop
BNB
  Relocation of the of the
  DI bottles (~2 weeks)
~50% Done
~30% Done

## Slide 10: External Beam line (continued)
NuMI (~10-12 weeks)
  Target removal for beam scan of the horns
  General maintience
    Dehumidifiers
    Replace Filter and water in the Absorber and Decay pipe cooling system
    Drain tile cleaning
    Ext.
  Water system repair
    Repaired cracked nipple on LCW supply manifold in Pre-Target enclosure near Q115.
    Repaired cracked weld on Decay Pipe RAW system in Absorber Hall.
~30% Done
~95% Done

## Slide 11: Muon Campus Work
  Mu2e work
    M4 line installation ( first half to absorber) ~10% Done
      Stand and magnet and cable pulls installation (7-9 weeks)
  In support of g-2
    Delivery ring straight section
      Injection septa (1-2 weeks)
      Removal and reinstallation of ring for the M4 line installation ~ Done
      Rotate Q207 and Q210 BPMs ~ 2-3 days
      Relocation of ELAM ~2-3 days
    Abort line
      Extraction septa (1-2 weeks)
    Magnet replacement Internal water leaks
      H212 ~ 1 week
      Q211 ~2 days
      V742 ~ 1 week ~ Done
    Instrumentation Repair
      PWC and IC’s ~ 1-2 weeks

## Slide 12: 2017 Shutdown Pocket Dosimeter Reports – Week 1
Chart: Cumulative Effective Dose per Week of Shutdown
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 13: Shutdown Duration Drivers
Linac Marx Modulator installation
  Station 2 upgrade is underway
  Station 3 will follow
RR TSP to IP conversion
  Progressing
Muon Campus Overlap with Switchyard crews
  Crew is responsible