## Slide 1: 2017 Main Injector/Recycler Shutdown
D. Morris
9 o’clock Meeting
August 4, 2017

## Slide 2: Tunnel Work
Safety Stand-down lifted previous Thursday 06:00
Finished removing 6 permanent magnets from RR->MI lines
Finished work on MI-10 fluorinert skid
MI-52 section
Opened MI-52 Septa region
  Multiple damaged wires on upstream septa: replacing with 4 mil
Replaced multiple aging Ion Pumps
Removed toroid for use in Recycler abort line
Removed e-cloud beam pipe
  Replaced with single pipe, removing multiple leak locations

## Slide 3: TSP to IP Conversion
From 106 to 229 starting at the 229 end
Mu metal shielding removed 229 to106
Cuts made from 229 to 106
Ports welded on from 229 to 129
Pumps installed 229 to 207
Vacuum established 229 to 220

## Slide 4: Cable Pulls
Actively pulling cables from MI-40 service building to R:LAM40

## Slide 5: Miscellaneous
Heat Exchanger cleaning:
MI-10, MI-20, MI-30, MI-40, MI-50 and MI-52 clean
Testing and re-assembling clean exchangers
MI-52 tunnel sump discharge line repair scheduled to start
August 9th (Wednesday)

## Slide 6: Power Outages
  Today:
MI-60 all day
No more scheduled tunnel outages (other than site wide)