## Slide 1
Steve Holmes
PIP-II Project Management Group
23 August
PIP-II Project Manager’s Report

## Slide 2: Outline
Goals
Financials
ES&H/NEPA
Technical/R&D
India Collaboration
Project Management
  CD-1 Status

## Slide 3: Project Goals
CD-1 profile as receive from OHEP on July 17
  We are in discussion with OHEP as to whether $20M is a more realistic number for FY18
We will be aligning the RLS with this profile, but may reallocate between OPC, PED, and TEC in years FY20 and beyond
Milestone | Planned | Actual or Forecast
CD-0 | Q1 FY2016 | November 12, 2015 (A)
CD-1 | FY2017 | Q2FY2018
CD-2/3a | FY2019 | FY2019
CD-3 | FY2020 | FY2020
CD-4 | FY2026 | FY2026

## Slide 4: Goals for FY17 (unchanged since July PMG)
Goal is to achieve CD-1 in ~January 2018
  RLS
  ICR
  Documentation
Financial Goals
  Live within the provided budget: $21.03M (includes FY16 carryover)
  Cross the FY17/18 border with ~$2.0M unobligated (carryover)
ES&H Goals
  Be prepared to initiate Environmental Assessment on 10/1/17
R&D Goals
  Release CDR
  Complete PIP2IT MEBT
  Keep HWR and SSR1 on track for CY2018/19 delivery
India Collaboration Goals
  Meet 2017 deliverable milestones
  Establish confidence between the partners
Management Goals
  Complete all CD-1 documentation and successfully navigate required reviews
  Fill missing positions on organization chart

## Slide 5: Financials (inception through 6-30-17)
Spending since CD-0
  OPC/Project Office, Civil Const, and SC Linac are only areas of activity to date
  5.6% complete

## Slide 6: FY17 Financials (through 7-31-17)
RIPs: $531K
Current Management Reserve: ($75K)
Demands against Management Reserve: $71K

## Slide 7: FY17 Financials/Management Reserve
Budgets adjusted following FY17 forecast-to-complete in April + adjustments from approved funding change requests
Current Management Reserve: ($75K)
  OHEP + Directorate made available $127K of uncosted obligation on Pavac contract for application to HB650 dressed cavities (GARD funds)
    This has been obligated!
  Directorate provided $250K from reserve to support Lab 2 improvements
    Thanks!
Management Reserve does not reflect anticipated SWF underrun of ~$2M
Unfunded Requests: $71K
  PIP2IT RFPI $15K
  LLRF $56K
    Partially funded
  CF subsurface documentation $20K
Have removed Environmental Assessment from this list as on track for early FY18 contract award

## Slide 8: ES&H/NEPA
Wetlands Jurisdictional Determination
  In process with USACE
  If accepted, the wetlands located in the PIP-II footprint would be designated non-jurisdictional
  If denied, a new wetlands permit application would be submitted in FY2018 to allow USACE the 1 year review period in order to meet a PIP-II start work date of late FY2019/early FY2020.
EENF submitted to DOE/FSO (Aug 18)
  Expect determination from FSO Friday (Aug 25)
Environmental Assessment scope of work sent to Procurement for review
  Preparing RFP with anticipated release date of ~Oct 1

## Slide 9: ES&H/Safety Incident
HWR accident at ANL (July 18)
  Cryomodule lid fell to floor
  Damage: cryo valves, bayonets, alignment pins
  Category 3 event
    Currently under investigation
  Lid repair estimated at 24 weeks
    Expect somewhat less delay in cryomodule delivery because lid not on critical path

## Slide 10: Technical/R&D Status
PIP2IT
  2017 goal to complete MEBT and commission with beam
    5 mA × 1 ms × 20 Hz to dump
    Measure kickers’ effects on the beam
  Completed installation of
  MEBT in early August
  Beam Commissioning
  underway

## Slide 11: Technical/SRF R&D Status
SSR1
  Dressed cavities are showing FE in full power tests (at STC)
  This is delaying the SSR1 schedule
  Investigating, using the previously qualified cavity
    Retest shows degraded performance (FE above 15 MV/m), but still meets spec
HB650
  Goal is to qualify and dress four cavities in FY17
  Two cavities are qualified
  One ready for retest; other being prepared for retest
Couplers
  New RFQ coupler design has been completed and reviewed
    Procurement initiated
  HB650 couplers RFP has been released
    Best value procurement with pre-qualified vendors
    Bids came in, substantially higher than estimate

## Slide 12: Project Management/CD-1 Strategy
Timeline
  Director’s Review September 19-21
  DOE IPR/ICR November
  ESAAB (CD-1) January 2018
Critical path is:
  Complete RLS (technically limited, see L. Lari presentation)
  Complete BOEs (see P. Derwent presentation)
  Adjust TPC/UCR to fit into $700M box
  Edit BOEs accordingly
  Align RLS with BOEs and with CD-1 funding profile
Complete all required documentation
  Good shape (see P. Derwent presentation)

## Slide 13: Project Management/CD-1 Status
RLS
  Major outstanding items are integration of all labor associated with cavities & cryomodules and installation & commissioning
BOEs
  133/146 of BOEs have data in them as of last Friday (8/18)
    48 have been validated through our review process
  Expect to have everything in by Friday (8/25)
Adjust TPC/UCR to <$700M
  Currently stand at ~$7XXM
    With 30% contingency + 15% maturity contingency to UCR (50% total)
    Scope reduction menu created. Will finalize on Friday (8/25).
Edit BOEs to align with UCR and align RLS with new BOEs
  We must have this by 8/30 to stay on schedule for Director’s Review
Align RLS with funding profile
  I am dubious that we can have this done for Director’s Review

## Slide 14: RLS status
BOE data in P6
70%Detailed in P6
WBS/BOE in P6
Close to ready/ready
Advanced

## Slide 15: India Collaboration
Joint R&D Project Document
  Addendum II: Documentation of Fermilab engineering deliverables.
    DAE responded with 12 pages of comments to my July 5 proposal.
  Addendum I: Modification to DAE deliverable dates to reflect delays in R&D program to FY2020
    DAE to make Addendum I consistent with Addendum II
Visitors
  Authorization to restart the long- and short-term visitors programs has been give to the Technical Coordinators
  They are discussing the areas in which they would like to deploy the next cohort.
  No opportunity for overlap with current visitors at this point
Exports
  Procurement of MOSFETs for SSR1 RF sources is becoming critical
    Identified potential distributor willing to sell with BARC as end user
  Discussion with SC (Mike Salamon) on modification to DOC entities list
    He will discuss possibility with DOC
SSR1 cavities
  Leonardo Ristori and Paolo Berrutti will be visiting BARC in October for:
    Witnessing of SSR1 He vessel welding
    Review of SSR2 cavity design
    We have advised DAE that we need these cavities on the Fermilab site by December 31, 2017 in order to incorporate into the prototype SSR1 cryomodule
IIFC Meeting
  Moving meeting to Fermilab, immediately after the DOE Review, expected in November

## Slide 16: Project Management
Personnel
  No personnel actions this month
Issues that are impeding progress
  Lab2 cleanroom not complete – requires substantial further investment to make usable – funds received from Directorate
  Engineering support for SRF
    Tom N (Mu2e) and Chuck G (LCLS-II) have very minimal availability
    Much of the slack is being taken up by Vikas Jain (RRCAT visitor)
      He returns to India in October → we will need access to Chuck starting in FY2018

## Slide 17: Summary
Moving toward CD-1, with a newly-modified plan
  Acceleration by ~2 months is a challenge, but is providing good motivation for the project.
India collaboration is taking a lot of attention
  Improving interactions and information exchange
Need to add more staff prior to CD-1
  Essentially there

## Slide 18: Backups

## Slide 19: FY18 Strategy @ $14.0M (unchanged since last month)
Currently forecasting FY17 underrun of $1.9M
Budget FY18 for $15.8M
  Support 40 FTE
    Standing army (20) + priority activities (20)
    Compare to 54 FTE budgeted in FY17
  SWF+OHD $10.7M
  M&S + OHD $5.1M
  Schedule ~$1M of M&S in Q4 FY18 = virtual reserve
Priorities
  CD-1
  CDS install at PIP2IT
  MEBT absorber at PIP2IT
  HWR (pCM)
  SSR1 (pCM)
  HB650
  CF design start (site prep and buildings)
  EA
Issues
  Essential that we get operations support for Lab2 ($338K w/ovhd)
    We need this asap to be ready for SSR1 assembly in Jan. 2018
    We have requested from Laboratory Reserve – no response yet
  Booster injection design