## Slide 1
Luisella Lari
PIP-II PMG meeting
23 Aug 2017
Resource Loaded Schedule Status
Thanks
To L3/L2 Managers,
To PIP-II Project Management Team
To J. Randall

## Slide 2: Outline
PIP-II RLS Status vs BOEs
PIP-II RLS Working in Progress
PIP-II RLS Completion Strategy

## Slide 3: PIP-II RLS status vs BOEs (1/2)
BOE data in P6
70%Detailed in P6
WBS/BOE in P6
Close to ready/ready
Advanced

## Slide 4: PIP-II RLS status vs BOEs (2/2)
Up-to-date: 146 BOEs in Total  48 validated/approved and moved in P6
P6 WBS and activities are already created to allocate BOE data

## Slide 5: PIP-II RLS working in progress
The validation of BOEs doesn’t mean that the costs are approved  working in progress to align P6 with on-going costs scrubbing.
CM FTE P6 implementation as well as the PIP-II critical path are depending by the approval of proposed cost reduction.
Approval of possible cost reduction  end of this week
Preliminary BOE cost analysis shows the need of scrubbing costs
Moreover we are working on align P6 to the new starting date i.e. Oct 17

## Slide 6: PIP-II RLS completion strategy
From PMG 26 July 2017
BOE Validation, cost scrubbing and P6 Completion foreseen for August the 30th