## Slide 1: Proton Source Week 6
Joe Compton
9am Meeting
8/18/2017

## Slide 2: RIL/Linac
RIL
  Ran source A all week with the new electronics
    Running good with a fair amount of extractor sparking
  Tested a card to turn off the extractor trigger during sparks
  FESS worked on AC unit
Linac
  Electricians worked all week on Marx modulator at LRF2
    Should finish up today
    Driver testing will begin shortly after
  P1 Marx modulator being installed at LRF5
  Power outage scheduled for September 8
    L1, L2 & L3 substation maintenance
  LE general maintenance

## Slide 3: :LRF2/LRF5
LRF2
LRF5

## Slide 4: Booster
BRF22 cavity installed
  Aligned
  CHG0 torroid moved
  Shielding tests for CHG0 torroid continues
BRF22 PS room prep continues
Cable pulls for L11 perpendicular cavity
Kicker loads were inspected/cleaned/repaired
Correctors were inspected
  Corrector at L10 was found to be suspect and was replaced
  Corrector at L4 will be replaced today

## Slide 5: Booster
Cleared out rack space for new BPM electronics installation
LCW leaks on back tuners on BRF1 and BRF17
  LRF1 tuner was fixed in place
  LRF17 needed to be pulled out for repair
    Was re-installed yesterday morning after repairs
IP61 & IP62 will be replaced today
General RF maintenance
Notch absorber frame installed
  Marble shielding still to be installed

## Slide 6: BRF22

## Slide 7: L10 Corrector