## Slide 1: A few thoughts on Consortia and DUNE Project Office (DPO) collaboration
First task is to identify the scope of your consortium, building on your list of deliverables
This leads to the development of a WBS (work breakdown structure) – a logical means to organize your work to deliver your subsystem. This also means understanding the boundaries with other subsystems
The WBS should form the basis for developing your schedule.

## Slide 2: DUNE Schedule
Consortium/Technical Lead is responsible for
  Establishing project technical and scientific requirements
  Define scope
  Develop Work Breakdown Structure (WBS)
  Identify activities and durations
  Develop schedule (MS Project)
  Update and maintain consortium schedule
The schedules are developed/owned by the consortia

## Slide 3: DUNE Schedule
DPO will provide
  Guidelines for developing the consortia schedules
  Initial ideas/format/template for schedule development
  Support in developing and revising the schedules
  Logically link all consortia schedules in one master schedule
  Maintain and regularly update master schedule
  Updating the baseline schedule through the established change control process
  Collecting schedule progress information on a monthly basis from each Consortia
  Providing schedule reports to consortia and project manager
  Working with Consortia to develop mitigations for possible schedule slippage
Schedule development will be an iterative process
Goal is to compete the master schedule by October 2018 (in advance of TDR and LBNC review)

## Slide 4: Timeline for Developing DUNE Schedule
Oct 17 | Jan 18 | Apr 18 | Jul 18 | Sept 18
Tasks
Develop WBS
First draft of the consortia schedules
Identify interface milestones
All consortia schedules linked together
Second version of the consortia schedules
Revisions/adjustments
Schedule Review

## Slide 5: WBS Development – Option 1
APAs
Institution A
Institution B
Institution C
Design
Procurement
Design
Production
Procurement
Production
Design
Procurement
Production

## Slide 6: WBS Development – Option 2
APAs
Design APA Tooling
Procurement
APA Production
Institution A
Institution B
Institution C
Institution A
Institution B
Institution C
Institution A
Institution B
Institution C
APA Installation
Institution A
Institution B
Institution C
APA Commissioning
Institution A
Institution B
Institution C

## Slide 7: WBS Dictionary Example
DocDB-427

## Slide 8: Schedule Development Flowchart
Identify Scope
Define WBS
Setup Schedule Template
Define Activities, Durations, Relationships
Identify Interface Milestones
Link all Schedules Together
Adjust Durations

## Slide 9: Steps in Preparing the Schedule
  Develop activity list and milestones at lowest WBS level
  Sequence project activities and milestones
  Determine relationships between activities and milestones
  Establish activity durations
  Identify interfaces to other sub-systems

## Slide 10: Think about the Interfaces to other systems
Example from Single Phase
Subsystem | Activity Name | APA | DAQ
Photon | Photon Detectors available for installation on the APAs (Det #1) | TBD | TBD
Cold Electronics | Cold Electronics available for installation on the APAs (Det #1) | TBD | TBD
Cryostat | Cryostat #1 roof |  | TBD
 | Mezzanine #1 |  | TBD

## Slide 11: High level schedule milestones
Detector #1 |  |  | 
Activity ID | Activity Name | Start | Finish
131122.0404.MB01MS4 | T4 MS - FSCF - Beneficial Occupancy - Surface Facilities |  | 
131123.04.02.34MS | BO for Cryostat #1 and Central Utility Cavern available |  | 
131123.01.01.858MS | Cryostat #1 roof available for infrastructure installation |  | 
131123.01.01.860MS | Mezzanine (#1) installation complete |  | 
13122.01.02.260MS | T4 MS - Cryostat Ready to start detector #1 installation |  | 
13122.01.02.275MS | T4 MS - Detector #1 Installation Complete |  | 
13122.01.02.265MS | T4 MS - Begin Testing Detector #1 |  | 
131123.01.01.862MS | T6 MS - Steel frame TCO closed #1 |  | 
131123.01.01.870MS | T6 MS - Testing prior to filling #1 complete |  | 
131123.01.01.872MS | T6 MS - Completion of safety documentation |  | 
131123.04.02.276MS | T4 MS - Purge and Cooldown #1 complete |  | 
131123.04.02.291MS | T4 MS - LAr Filling Complete Cryostat #1 |  | 
13122.01.02.305MS | T4 MS - Detector #1 Ready for Commissioning |  | 
13122.01.02.310MS | T4 MS - High Voltage Checkout Detector #1 Complete |  | 
13122.01.02.315MS4 | T4 MS - Detector #1 Commissioning Complete |  | 
Detector #2 |  |  | 
131123.01.01.882MS | Cryostat #2 roof available for infrastructure installation |  | 
131123.01.01.884MS | Mezzanine (#2) Installation complet |  | 
13122.01.02.270MS | T4 MS - Cryostat Ready to start detector #2 installation |  | 
13122.01.02.350MS | T4 MS - Detector #2 Installation Complete |  | 
13122.01.02.295MS | T4 MS - Begin Testing Detector #2 |  | 
131123.01.01.886MS | T6 MS - Steel frame TCO closed #2 |  | 
131123.01.01.894MS | T6 MS - Testing prior to filling #2 complete |  | 
131123.04.02.278MS | T4 MS - Purge and cooldown #2 complete |  | 
131123.04.02.293MS | T4 MS - LAr Filling Complete Cryostat #2 |  | 
13122.01.02.345MS | T4 MS - Detector #2 Ready for Commissioning |  | 
13122.01.02.360MS | T4 MS - High Voltage Checkout Detector #2 Complete |  | 
13122.01.02.370MS | T4 MS - Detector #2 Commissioning Complete |  | 

## Slide 12: Some future work to consider…
Consortia need to review and propose modifications or updates to the requirements (DocDB-112) [These are under change control and managed by Elaine as LBNF manager & Eric as TC]
Consortia will need to develop Interface Control Documents. Various ICDs are in SharePoint and DocDB. Currently these describe DUNE/LBNF Interfaces and ProtoDUNE-SP interfaces.
LBNF/DUNE has a Risk Register in SharePoint and in Excel files. Some version of this should be updated and maintained. This relates to items that may be a risk for schedule delay.
DUNE maintains a list of Recommendations from our many reviews. The recommendations for your subsystem must be considered and responses developed and/or implemented.
…Don’t forget installation, testing (QC) plans and commissioning…
…