## Slide 1: Delivery Ring Update
Jerry Annala
Muon Campus Shutdown Status - week 9
8 September 2017

## Slide 2: Major shutdown efforts
Install the M4 line
  Magnets installed past the temp shield wall (100%)
  Cables are being installed (40%)
  Water connections will follow cable installation (0%)

## Slide 3: Install new pulsed septa magnets
First Magnet is at NWA
  Magnet has been pumping since 8/10/17
  Vacuum pressure at 1.3e-6 torr
  Ion pumps are holding on their own
  Organizing all of the installation work so that actual vacuum installation time is as short as possible.

## Slide 4: Repair of PWCs and Ion Chambers

## Slide 5: Additional jobs (unchanged)
Installation of 3 extra correction elements
  Stands being machined
  Cables have been pulled
Search for aperture restrictions
  Have inspected the M2 and M3 lines
  Will still inspect the M4 and M5 lines

## Slide 6: Schedule
Electricians continue pulling M4 line cable
Have resumed AP-0 pulse testing
Begin installation of injection Septum magnet on next week
Production line repair of PWCs and Ion Chambers is underway.