## Slide 1: 2017 Main Injector/Recycler Shutdown
D. Morris
0900 Meeting
September 8, 2017

## Slide 2: Tunnel Work
MI/RR-52 section
Recycler 52 Lamberston aperture upgrade
  New beam pipe and flange have been installed
  Alignment assisting in getting pipe deviations removed

## Slide 3: Tunnel Work
MI-Instrumentation/RF section
Located vacuum leak inside RF #7
Leak check of instrumentation/damper region
  Final leak check complete but…
  I:IP601 failed and has been replaced
    Needs leak checking after stand fabrication

## Slide 4: Tunnel Work
Installation of modified Recycler sextupole stands complete
Need aligning
  Crew is removing more transfer line magnets

## Slide 5: MI-8 Line Vacuum Work
Crew is working on ion pump replacement in MI-8GeV line
  826 through 846 roughing down
    One failed pump has been replaced
    New leak located near collimators
  Leak check complete for 846 - 852

## Slide 6: Miscellaneous
MI-52 tunnel sump discharge line repair nearing completion
MI pond from MI-10 to MI-60 has been lowered for MI-62 sprayer repairs which are nearing completion
Water group is fixing leaks on the compressed air system
Installing two new compressors
Multiple LCW valve leaks to address

## Slide 7: MI-52

## Slide 8: MI-62

## Slide 9: Going Forward
Jobs still on the schedule:
  MI RF cavity #4 (~Sept.15th)
  MI e-beam scanner (?)
  R40 abort lamberston (MLAW) installation
  RR abort toroid replacement
  RR 104 HIPM MCP
  R-103 pinger kicker
  SEY sample change
  Investigate MI vacuum at MI-301
  Tunnel cleaning