## Slide 1: protoDUNE APA production in the UK
Justin Evans
University of Manchester
11th September 2017

## Slide 2: protoDUNE in the UK
We are making three protoDUNE APAs in the UK
  Using a copy of the system designed by the PSL engineers
Working at the Daresbury laboratory
In close proximity to Manchester and Liverpool (30 min drive)
  1 hour to Lancaster
  90 minutes to Sheffield
This is important
  Allows technical and academic staff from multiple universities to have day-to-day involvement in the project

## Slide 3: Working space
Production happening inside a class 100,000 clean tent; similar setup to PSL
  The room is covered by a crane, rated to 6 tonnes
  Clean tent has a separate internal crane
Winding
machine
Process cart

## Slide 4: APA frames
Steel from Atlantic Steel (same supplier as PSL)
  Steel selection process required to ensure tolerances
Portobello (engineering company near Sheffield) produce the frames
  protoDUNE frame production has gone very smoothly
  Currently £30k per frame

## Slide 5: Production process
Install photon detectors
  Quick
Apply mesh and combs
  ~2 weeks: 8 hours of epoxy drying each time, limited parallelisation
Install PCBs for wiring onto
  1 day: epoxy must dry
Mesh application
Comb installation

## Slide 6: Wiring
Wind a half-layer at a time
Takes 2-4 days depending on the layer
  Or longer if the machine plays up

## Slide 7: The winding machine
PSL have designed a very nice piece of machinery
For mass production, reliability is important
  Machine can get confused and stop mid-job; easy to fix but needs expert supervision
  Motors can seize up
  Wire can snap and tangle around the clutch
Other suggested improvements
  Clutch that provides tension needs 20 minutes to warm up before winding
  Redesign to wire a whole layer at once
  Automation software is currently expert level: not trivial to push out to a number of sites with beginner operators

## Slide 8: Tension testing
This takes a long time
  Upwards of 3-4 hours to test one side of half a layer
Current procedure
  Test every wire on both sides of a half layer (most of a day)
  Solder and cut all wires (2-3 hours)
  Test every wire on both sides again (most of a day)
We’re being super-cautious for our first layer, so could cut the first test down to every 10 wires or so
  But this is still an integrated 2 weeks of tension testing for every APA
On top of that, there are a few hours of electrical tests per layer

## Slide 9: Cold testing
Lancaster-built cryo-box that can cool SBND and protoDUNE frames down to ~100 K in gaseous nitrogen
  Goal is cool-down rate of 50 K / hour
  Equipped with sixteen cameras and lighting
Not clear if we will use this on the protoDUNE frames
  Time, risk, not clear what we will learn
  We will by trying this out as part of our SBND production process

## Slide 10: Production process summary
Currently taking around 3 months to wire an APA
  For mass production, each site needs to push out an APA every 2-3 weeks
We’re looking at extending working hours to speed this up
  Working overtime on some weekends
  Moving to 12-hour days (an early crew and a late crew)
Current production procedure is quite manpower heavy
  For most of the time, you need two people working together
  Wiring happens half a layer at a time
  APA must be moved twice between each layer: at these times you need three people
  Many days of tension and electrical tests per APA
We have a very nice machine from PSL to start us off
  A lot of work is needed to turn this into a mass production method