## Slide 1: 2017 Main Injector/Recycler Shutdown
D. Morris
0900 Meeting
September 15, 2017

## Slide 2: Tunnel Work
MI/RR-52 section
Recycler 52 Lamberston aperture upgrade
  New flange and beam pipe is installed, welded and aligned
  Roughing down for leak check today

## Slide 3: Tunnel Work
MI-Instrumentation/RF section
- 601 final leak check complete
- 606 area RF cavity leaks patched
Final leak check today
- 605 area leak check underway.

## Slide 4: Tunnel Work
Installation of modified Recycler sextupole stands complete
Alignment in progress

## Slide 5: MI-8 Line Vacuum Work
Vacuum work is complete
  One issue with a potential cable fault at 835

## Slide 6: RR-10
Crews are starting work to install a new Recycler pinger

## Slide 7: RR-40/Abort

## Slide 8: RR-40/Abort

## Slide 9: Miscellaneous
MI-52 tunnel sump discharge line repair nearing completion
- After it’s operational we need to pull hose from tunnel
Water group is performing LCW pump vibration measurements, balancing and maintenance

## Slide 10: Going Forward
Jobs still on the schedule:
  MI RF cavity #4 (Expected to start next week)
  MI e-beam scanner (?)
  R40 abort lamberston (MLAW) installation (Purging Monday)
  RR abort toroid replacement (Purging Monday)
  RR 104 HIPM MCP (Next week)
  SEY sample change (Next week)
  Investigate MI vacuum at MI-30
  Tunnel cleaning