## Slide 1: Dual Phase Field Cage Trial Installation Proposal
NH1 Integration Meeting Sept. 15, 2017
Jaehoon Yu for
A. Chatterjee, G. Brown & UTA Team
A. Gendotti, S. Murphy, C. Cantini & ETH Team
F. Pietropaolo & CERN Team

## Slide 2
Field Cage and cathode hangs off of the ceiling
Essential to have light yet sturdy structure
Based on modular concept as SP
Field Cage in protoDUNE DP
Charge Readout Planes
Field Cage (common structural elements with SP)
Cathode
6 m
6 m

## Slide 3
Shares common basic structural elements w/ ProtoDUNE-SP
Consists of 8 vertical modules of 6310 x 3010 m2 (2 modules per detector face)
Each module is assembled out of 3 distinct sub-modules with 33, 33, and 32 profiles each held by a frame with two 6” and two 3” horizontal FRP I-beams
98 electrically continuous rings in 60mm pitch using straight aluminum clips
11 profiles with one end bent at 45 degrees are electrically connected by 2 divider boards
Inter-module connections made with FRP plates connected with FRP threaded rods
Sub-module 1
33 profiles
Sub-module 2
33 profiles
Sub-module 3
32 profiles + cathode
Continuity at center and borders w/ Al clips
Field Cage Design

## Slide 4
Assemble and install 3/8 of the DP-FC and test the installation procedure
One full side with two 6mx3m modules
Plus one 90 degree corner formed with an additional 6mx3m module
Connect all field shaping rings with the connecting clips and secure them with the slip nuts and screws
Connect one complete row of HVDB from top to bottom
Allow virtually all combinations of installation scenarios
DP-FC Trial Installation Proposal

## Slide 5
Measure all critical dimensions compared to the drawings
Debur, defiber, sand, clean with simple green and varnish
Pre-assemble with the sample profiles at UTA to check the fit
Disassemble and package all parts except for the Al profiles
DP-FC Parts QA/QC process

## Slide 6
stopper
stopper
stopper
stopper
Al-Profiles will touch this frame
452.1 mm
Assembly Table w/ Profile Alignment

## Slide 7
Current Status of DP-FC Part Prep
Part Number |  | Measured/ Inspected | Cleaned & Varnished
6” I-beams | DP-FC-002 | 18 (out of 18) | 7 (out of 18)
 | DP-FC-003 | 11 (out of 18) | 9 (out of 18)
 | DP-FC-004 | 18 (out of 18) | 9 (out of 18)
3” I-beam | DP-FC-008 | 46 (out of 54) | 8 (out of 54)

## Slide 8
Sept. 15: Complete FRP critical dimension measurements
Sept. 25: Complete FRP deburring, defibering, cleaning and varnishing
Oct. 4: Complete preassembly and packaging of the first 15 sub-modules
Week of Oct. 9: Ship the first 15 (5 of each kind) sub-modules
Oct. 20: Complete preassembly and packaging of the remaining 12 sub-modules, including the 3 spare
Oct. 27: Ship the remaining 12 sub-modules + precision assembly table
Sub-Module Delivery Schedule

## Slide 9: HV Divider Board Mounting to DC
Two parallel columns of 10 boards, totaling 20 boards
The total potential from the extraction grid to cathode: 294kV to 588kV
Two 2GW resisters each stage for each board, providing 0.5GW effective resistance per stage
Current through the entire circuit: 6mA – 12 mA (100 times the expected current from cosmic rays)
A. Gendotti

## Slide 10
Total number of boards needed: 18 long (11 profile) + 2 short (8 profile)
  Preparing 35 – 29 long and 6 short including spare
2GW resisters
  Total Needed: 29*20+6*16 = 676
  Total in hand: 1066 (530 qualified with 1% criteria, enough for what is needed but no spares)
    Additional order of 500 resisters placed
Varistors (1.8kV clamping voltage each)
  Total needed: 29*40+6*32=1352
  Total in hand: 1800 (expect 1440 to pass the criteria – 200mA at 1.75kV)
Anticipated completion date for testing & selection: 25/9
HVDB Preparation

## Slide 11: HVDB Schedule
11
Sept. 25: Complete testing and selection of the first batch of resisters and varistors and ship to the vendor
Sept. 28: Board delivered to the vendor
Oct. 9: First set of 18 long +2 short stuffed board delivered to UTA
Oct. 23: Complete warm and cold testing and qualification of the stuffed boards
Oct. 30: Ship 18 long + 2 short boards to CERN
Week of Oct. 30 – Week of Nov. 13: receive the remaining 11 long + 4 short stuffed boards
Week of Nov. 13: Ship the remaining 11+4 to CERN
Notes: 9/15/17
11
11

## Slide 12: DP-FC Module Installation Sequence
12
Place all eight SS I-beam of the Hanging system in the nominal position on the temporary floor in the cryostat and mark the position  Bring out the five that are not needed
Connect the SS I-beam to the corresponding winches and lift it up ~2.5m
Assemble submodule inside the CRB and attach the steel reinforcement bar in its horizontal position
Connect the steel reinforcement bar to the I-beam rail, roate 90 deg fir lifting and transporting the sub-module through the TCO
Insert and secure the sub-module onto the wheeled support trolley while it is suspending from the transport I-beam crane
Position the sub-module under the hanging SS top frame bar
Remove the sub-module top reinforcement
Connect the sub-module to the SS top frame bar and lift it uo ~2.5m for the next sub-Module
Repeat procedure 3 – 8 for the other two sub-modules
Notes: 9/15/17
12
12

## Slide 13
1) SS I-Beam for Hanging System
32
Accordingly to the position of the CRP  Mark the position of the field cage on the construction floor
Position the SS I-Beam (hanging system) in the right position
Lower the hanging SS wire and connect to the I-Beam  Connection point centered at the wire

## Slide 14
3.Assembled on the wheeled Table
4.Attach L-Profile Top and Bottom
4. Reinforcement U-Profile Top and Bottom

## Slide 15
I-Beam Rail
5) Sub-module transport through the TCO

## Slide 16
Teflon Plate for vertical stability and and vertical alignement
6) Wheeled trolley support

## Slide 18
8) Connection to the SS bar of the hanging system
33
Lift the SS I-Beam ~2.5 m
Bring in first sub modules and connecto to hanging system
Already install the PCB boards of the HV divider (if it’s needed in module)
Sub module Installation:
2 Person on Top Lifting
3 Person inside the Cryostat

## Slide 19
2nd Sub Module
34
Same for 2nd sub module
Lift for another 2.5m

## Slide 20
3rd Submodule
35
3nd sub module
Lift the entire module at his nominal position

## Slide 21: Material Prep Matrix for Trial Installation
21
Notes: 9/15/17
21
21

## Slide 22: Proposed Schedule
22
20/11 – 8/12: Maximum two people from UTA out to prepare and to help CERN technicians to learn sub-module assembly
30/11 – 22/12: Jae Yu coming to CERN as early as Nov. 30 and to stay through CERN shut down on Dec. 22, having one full week of overlap with the UTA people
Goal: Install 3/8 of the DP-FC – two modules on a straight section and one connected module with a 90 degree turn to explore all possible combinations of installation scenario
To the extent possible, leave the three modules of 6mx3m installed for expedited installation in 2018
Notes: 9/15/17
22
22

## Slide 23: Summary
23
Proposed trial installation of three full 6mx3m DP-FC modules allow exploration of all combinations of installation scenarios
All DP-FC parts to be delivered to CERN by mid-Nov.
Up to 2 UTA people will be at CERN for 3 weeks from Nov. 20 to help prepare for this installation
Yu to join them for 1 week overlap and stay through CERN shut down for the completion of the task
Need all administrative documentations must be in place well ahead of Mid-Nov.
All training arrangements must be made to minimize time spent for these necessary preparations
All equipment needed for the task must be prepared ahead
Notes: 9/15/17
23
23