## Slide 1
Steve Holmes
PIP-II Project Management Group
20 September 2017
PIP-II Project Manager’s Report

## Slide 2: Outline
Goals
Financials
ES&H/NEPA
Technical/R&D
India Collaboration
Project Management
  CD-1 Status

## Slide 3: Project Goals
CD-1 profile as receive from OHEP on July 17
  For the Director’s Review we will use the technically limited profile coming from P6
  We need agreement with OHEP on the profile to use for the DOE Review by the end of the Director’s Review
Milestone | Planned | Actual or Forecast
CD-0 | Q1 FY2016 | November 12, 2015 (A)
CD-1 | FY2017 | Q2FY2018
CD-2/3a | FY2019 | FY2019
CD-3 | FY2020 | FY2020
CD-4 | FY2026 | FY2026

## Slide 4: Goals for FY17 (unchanged since July PMG)
Goal is to achieve CD-1 in ~January 2018
  RLS
  ICR
  Documentation
Financial Goals – on track
  Live within the provided budget: $21.03M (includes FY16 carryover)
  Cross the FY17/18 border with ~$2.0M unobligated (carryover)
ES&H Goals – on track
  Be prepared to initiate Environmental Assessment on 10/1/17
R&D Goals – on track
  Release CDR
  Complete PIP2IT MEBT
  Keep HWR and SSR1 on track for CY2018/19 delivery
India Collaboration Goals - delayed
  Meet 2017 deliverable milestones
  Establish confidence between the partners
Management Goals -delayed
  Complete all CD-1 documentation and successfully navigate required reviews
  Fill missing positions on organization chart

## Slide 5: Financials (inception through 7-31-17)
Spending since CD-0
  OPC/Project Office, ConvFac, and SC Linac are only areas of activity to date
  5.9% complete

## Slide 6: FY17 Financials (through 8-31-17)
RIPs: $760K

## Slide 7: FY17 Financials
Current (Sep 10) forecast is ~$3.6M underrun
  2.6 FTE/$900K SWF
    This estimate has held steady for last several months
  $1.4M M&S
    Activity slowed noticeably as engineers starting working on BOEs and RLS over last two months
    Underrun is delayed procurements, not things coming in under budget
    So we will be spending this money in FY18
  $1.3M OHD
  Expect to cross the FY17-18 boundary with ~$1.0M RIPs

## Slide 8: FY18 Financials
FY18 could lie anywhere in the range $14-24M
We have provided DOE with a plan for $20M
  63.0 FTE (compare 50.3 in FY17)
  $4.3M M&S (compare $4.7M in FY17)
  ($431K) Management Reserve
  Major procurement on next slide

## Slide 9: FY18 Financials

## Slide 10: ES&H/NEPA
Wetlands Jurisdictional Determination
  In process with USACE
  If accepted, the wetlands located in the PIP-II footprint would be designated non-jurisdictional
  If denied, a new wetlands permit application would be submitted in FY2018 to allow USACE the 1 year review period in order to meet a PIP-II start work date of late FY2019/early FY2020.
Environmental Assessment
  Purchase Requisition/Scope of Work is in the system
  RFP released Sep 19

## Slide 11: Technical/R&D Status
PIP2IT
  2017 goal to complete MEBT and commission with beam
    5 mA × 1 ms × 20 Hz to dump
    Measure kickers’ effects on the beam
  Completed installation of
  MEBT in early August
  Beam to end of MEBT
  Considering designating
  200  kicker as baseline
  FY17 goals met

## Slide 12: Technical/SRF R&D Status
SSR1
  Dressed cavities have been showing FE in full power tests (at STC)
  This is delaying the SSR1 schedule
  Reprocessing/retesting of cavities
    S112 qualified w/ unity (low power) coupler; retesting with high power coupler
    S113 failed to overcome MP barrier at 9 MV/m
HB650
  Goal is to qualify and dress four cavities in FY17
  Two cavities are qualified
  One ready for retest; other being prepared for retest
  Awaiting access to VTS
  RRCAT prototype cavity fabricated; should go to processing (@RRCAT) this week
Couplers
  New RFQ coupler design has been completed and reviewed
    Procurement initiated
  HB650 couplers contract award imminent
    Best value procurement with pre-qualified vendors

## Slide 13: Project Management/CD-1 Strategy
We have concluded it is not possible to keep the TPC/UCR <$700M, and that keeping the TPC/UCR <$750M requires removal of the Recycler/Main Injector scope
Risks of retaining or removing Recycler & Main Injector from scope:
  On project: TPC/UCR will exceed $750M. CD-1 will have to go to undersecretary who is either acting or new on the job. Risk is that it will take a while to get approval
  Off project: Recycler/Main Injector scope is required to meet Mission Need Statement (1.2 MW). Risk is that the money required for RR/MI will not materialize
Where we stand as of Friday: Point Estimate = $638M
  Recycler/Main Injector out of scope
  Based on technically limited schedule – funding profile unconstrained
  $33M actual cost to date + $605M estimate to complete
  Includes 23.1% estimate uncertainty
  10% risk uncertainty
  May still be some adjustments to this number (either direction)
Upper cost range derived from this:
  $729M @ 15% maturity premium
  $759M @ 20%
  $789M @ 25%
It appears unlikely we can keep the UCR < $750M beyond the Director’s Review
  Any draw out in the schedule adds about $15M/year
    For example, to align with funding profile provided by OHEP
  Unlikely DOE will accept 15% multiplier to get from point estimate to UCR
    Each % increase adds ~$6M to UCR
  Once we break $750M there is no rationale for keeping Recycler/Main Injector off project
    Adds about $30M to UCR

## Slide 14: Project Management/CD-1 Strategy
Review Timeline
  Director’s Review October 10-12
  DOE IPR Dec 12-14 (backup Nov 28-30)
  DOE/ICR Dec 4-7 (site visit)
  ESAAB (CD-1) January/February 2018
Director’s Review Timeline:
  RLS complete for cavities/cryomodules: Wednesday, Sep 20
  RLS complete for everything else Friday, Sep 22
  BOEs complete/aligned with RLS (P6) Monday, Sep 25
  Rehearsals Sep 25-29
  Talks posted Oct 3

## Slide 15: RLS Status
Close to be checked against BOE data
Partially resource loaded
High level plan to be integrated in P6
To be completed
Advanced integr.
CLOSED - BOE=P6
CLOSED  43 BOEs
Advanced integration

## Slide 16: Project Management/CD-1 Documentation Status
CDR - Done
Assumptions Document - Done
PIP-II FRS - Done
Alternatives Analysis Report - Done
Alternatives Determination letter - Done
Lab MOU/interface document – in process
Preliminary Hazard Analysis Report – Done
Quality Assurance Plan – in process
PSVAR – Done
ISM – Done
NEPA Strategy – Done
Risk Management Plan – Done
PMP – Draft (not required by DOE413.3)
Procurement Management Plan - Draft (not required by DOE413.3)
PPEP – Done? (DOE document)
Acquisition Strategy – Done? (DOE document)

## Slide 17: India Collaboration
Joint R&D Project Document
  Addendum II: Documentation of Fermilab engineering deliverables.
    DAE responded with 12 pages of comments to my July 5 proposal.
  Addendum I: Modification to DAE deliverable dates to reflect delays in R&D program to FY2020
    DAE to make Addendum I consistent with Addendum II
  HTS-2 cryostats P.O. has now been issued by RRCAT
Visitors
  Authorization to restart the long- and short-term visitors programs has been give to the Technical Coordinators
  They have proposed six assignment they would like filled in the next cohort
  We are discussing and will propose some modification
  Shooting for arrival in early 2018
Exports
  Procurement of MOSFETs for SSR1 RF sources is becoming critical
    Identified potential distributor willing to sell with BARC as end user
  Discussion with SC (Mike Salamon) on modification to DOC entities list
    He will discuss possibility with DOC
SSR1 cavities
  Leonardo Ristori and Paolo Berrutti visit rescheduled to first week in November:
    Witnessing of SSR1 He vessel welding
    Review of SSR2 cavity design
    We have advised DAE that we need these cavities on the Fermilab site by December 31, 2017 in order to incorporate into the prototype SSR1 cryomodule
IIFC Meeting
  Moving meeting to Fermilab, immediately after the DOE Review, expected in December

## Slide 18: Summary
Moving toward CD-1, with a newly-modified plan
  Acceleration by ~2 months has been challenging
Director’s Review now Oct 10-12
  Recycler/Main Injector off-project for this review
  Schedule is technically limited – not matched to DOE profile
Believe we are heading for >$750M (major system) by time of DOE review
India collaboration is taking a lot of attention
  But have not had much time on this lately
  (Although weekly teleconference is continuing)