## Slide 1
Cons Gattuso
Summer Shutdown Status
9/18/17

## Slide 2: Proton Source Shutdown Work list
RIL 100% complete
Source maintenance
Einzel Lens maintenance
RFQ maintenance
General maintience
Linac
Marx modulator project ~65% complete
  Fabrication and Testing underway
    Planning to installed 2 modulator in 2017
      Duration ~6-7 Weeks for the removal of old and installation of new
LE tasks (performed by Linac techs) ~90% complete
  Modulator/driver maintenance
  Inductrol maintenance
  Water skid maintenance
HE tasks (performed by Linac techs) ~90% complete
  CS & PFN maintenance
  PFN cap bank maintenance
  QPS PM
  Water skid maintenance
  Heat exchanger maintenance
Booster
BRF21 and BR22 installation
  ~6-8 weeks ~95% complete
IPM Installation ~90% complete
  Controls Rack installation
  Tunnel component installation
General Maintenance ~85% complete
  Power supplies
  Cooling Systems
  Vacuum

## Slide 3: LRF2/LRF3
LRF2
LRF3

## Slide 4: LRF2 Marx Modulator Commissioning

## Slide 5: BRF22

## Slide 6: Main Injector/Recycler
MI
  Replace MI RF station 4 ~15% Done
    ~1.5-2 weeks
  Ion pump maintience ~90% Done
    ~1-2 Weeks
  8 Gev line
    Ion pump replacement ~100% Done
      ~1-2 weeks
    Vacuum leak check~100% Done
      ~1-2 Weeks
    Multi wire replacement (2)
      ~1 Week -Cancelled
  General maintience for MI/RR ~70% Done
    ~2-3 weeks
      Tunnel and service building
  Replace the beam pipe in Q504 -95% Done
    Vacuum leak on BPM feed through
  Switching Flourinert in the MI-10 and 60 kicker systems 100% Done
    Replacing FC-77 to FC-40
RR
  TSP upgrade from 106-229 -~100% done
    10-11 weeks
  Aperture improvement at the RR 402 and 520 locations
    ~3 weeks at the 402 – ~5%Done
    ~1.5 weeks at the 520 ~75% Done
  Recycler Abort lamberstons replacement
    ~3 weeks at the 402
  Recycler Sextupole stand change out ~100% Done
    ~3 weeks
  New Pinger installation in the 10 region ~5% Done
  Rebuilding and putting back into operations RRRF Anode power supply ~50% Done

## Slide 7: And Another Thing
MI 301/301 are vacuum issues

## Slide 8: External Beam line
P3 rough vacuum 100% Done
  F3 House IP to Turbo Station upgrade (~2 weeks)
    Run 4" vacuum pipe from service buildings down stairwells to tunnel
    Install Roots blower stations in service buildings, one per house.
    Switch controls over to Tevatron CIA crates, rename parameters
    Remove and cap ion pumps.
  Cable mitigation in the Meson and Neutrino Muon areas: (~6-7 weeks)
Separating the Booster 95 LCW system from Switchyard (~3-4 weeks)
  Switchyard would be its own separate stand alone system. Feed from the F-Sector old MR system.
MI65 Sprayer repair ~100% Done
  Drain pond down by 4-5 feet
  Remove Sprayer
  Repair/reinforce concrete pillars
BNB ~5% Done
  Relocation of the of the
  DI bottles (~2 weeks)
~99% Done
~95% Done

## Slide 9: MI-62 Sprayer repair

## Slide 10: Installing the MI-62 sprayer

## Slide 11: External Beam line (continued)
NuMI (~10-12 weeks)
  Target removal for beam scan of the horns ~100% Done
  Upgrades
    Heat exchanger installation on Multi stack chiller (tritium mitigations) ~100% Done
  General maintience
    Dehumidifiers
    Replace Filter and water in the Absorber and Decay pipe cooling system
    Drain tile cleaning
    Ext.
  Water system repair
    Repaired cracked nipple on LCW supply manifold in Pre-Target enclosure near Q115.
    Repaired cracked weld on Decay Pipe RAW system in Absorber Hall.
~95% Done
100% Done

## Slide 12: Muon Campus Work
  Mu2e work
    M4 line installation ( first half to absorber)
      Stand and magnet 95% complete
      Cable pulls installation (7-9 weeks) 80% complete
  In support of g-2
    Delivery ring straight section 30% complete
      Injection septa (1-2 weeks)
      Removal and reinstallation of ring for the M4 line installation ~ 2 days
      Rotate Q207 and Q210 BPMs ~ 2-3 days
      Relocation of ELAM ~2-3 days
    Abort line
      Extraction septa (1-2 weeks)
    Magnet replacement/repair Internal water leaks 100% complete
      V742 ~ 1 week
    Instrumentation Repair 10% complete
      PWC and IC’s ~ 10-12 weeks
    Beam Pipe Aperture Inspection 60% complete

## Slide 13: 2017 Shutdown Pocket Dosimeter Reports – Week 9
Chart: Cumulative Effective Dose per Week of Shutdown
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
 | 0 | 280 | 487 | 687 | 1035 | 1261 | 1487 | 2121 | 2470 | 2891 | 0 | 0 | 0 | 0 | 0 | 0
421 person-mrem
55 people reported some dose, with average dose of 7.65 mrem
WEEK 9:
2,891 person-mrem
130 people reported some dose, with average dose of 22.24 mrem
SHUTDOWN SO FAR:

## Slide 14
Chart: Number of Rad. Workers in a Range of Shutdown Cumulative Effective Doses
| 1 - 25 | 26 - 50 | 51 - 75 | 76 - 100 | 101 - 125 | 126 - 150 | 151 - 175 | 176 - 200 | 201 - 225 | 226 - 250
 | 95 | 18 | 9 | 4 | 3 | 1 | 0 | 0 | 0 | 0

## Slide 15: What Next??
Switching over from Shutdown Mode to a Start-up Mode
  Getting Major System back on-line
    Pond Systems
      Starting this the week Sept. 25th
    LCW systems
      MI/Booster/Switchyard
      Starting this the end of week of the Sept. 25th or beginning of week Oct. 2nd
  Tunnel Cleaning
    Linac/Booster Done
    Starting this the week September 25th
      External Beam line enclosure/ 8 Gev line
    Starting this the week Oct. 2nd
      MI/RR, Muon Campus Enclosures
  Tunnel Enclosure Switch back to operational cores
  Safety System Tests

## Slide 16: Shutdown Duration Drivers
Linac Marx Modulator installation
  Station 2 upgrade commissioning underway
  Station 3 tested in the Station 5 has commenced
Muon Campus Work in general
  Additional crews will be added
  Re-structing the workflow