## Slide 1: JLAB QA/QC for Cryomodule
LCLS-II QA/QC Workshop
Anne McEwen / Valerie Bookwalter
19-Sep-2017

## Slide 2: Outline & Introduction
Introduction
  JLAB has an overall Quality Management System managed by EHS&Q
  SRF Quality overall is reviewed monthly with SRF Management
      Status reports & summaries are available to SRF Staff
QA Tools : How are we working to the “Plan”
  LCLS-II uses the same Quality Tools & Quality Management System
  Travelers in Pansophy are used to collect & organize our Data
  NCRs & D3s are recorded & tracked in Pansophy
QC Results /Pareto on Parts & Assembly
  Pareto of types of quality issues that we are finding
  “significant” NCRs are reported Monthly as required by SLAC
  We measure and track many measures including
    Travelers – open/closed
    NCRs & D3s , number open and number closed
  Through Data Mining Many reports are available to assist the Managers , Engineers & technicians to manage the large quantity of data

## Slide 3: Quality Tools How are we working to the “Plan” for LCLS-II Cryomodule
LCLS-II QA/QC Workshop
Valerie Bookwalter
19-Sep-2017

## Slide 4: QA Tools in SRF
Where we keep our data
Pansophy (RECV, INSP, ASSY, TEST)
Docushare
LCLS-II folder on the M Drive (vendor data)
One Drive (Shared Vendor documentation for cavities)

## Slide 5: How we use Pansophy
Travelers
(Data In)
Inspection, Processing and Assembly Data for Cavities & Cryomodules and associated parts
Use and Management
Supports Quality Management (NCRs & D3 Reports)
Data Mining Queries – example Cavity Performance
Reports
(Data Out)
Real-Time Status reports - Dashboards
Docushare links to Procedures & Documents
Production & Project Manager Status reports
Quality & Traveler Status , level of completion,
Reports, tables & graphs, export to PDF/Excel

## Slide 6: Pansophy in use since 2002
Chart: 
| 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
P2 | 2 | 6 | 26 | 19 | 4 | 132 | 66 | 197 | 2073 | 5421 | 1600 | 885 | 369 | 773 | 5803 | 2632
P1 | 536 | 571 | 2221 | 2447 | 740 | 872 | 1279 | 887 | 751 | 213 | 9
Chart: JLAB Cryomodule Production supported by Pansophy
| FY02 | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17
SNS | 2 | 10 | 11
R100 + C100 12GeV | 4 | 4 | 3
C50 Refurbishment | 3 | 4 | 3 | 1 | 1 | 1 | 1
SL21,FEL03,Renascence | 1 | 1 | 1
LCLS-II | 1 | 7

## Slide 7: NCRs & D3s by Year
Chart: NCRs by Year
| 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
NCRs P1 | 2 | 124 | 693 | 403 | 163 | 222 | 396 | 102 | 96 | 5
NCRs P2 | 1 | 23 | 1 | 14 | 316 | 879 | 152 | 154 | 36 | 206 | 870 | 498
Chart: D3s By Year
| 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
D3s P1 | 28 | 68 | 55 | 3
D3s P2 | 2 | 132 | 332 | 54 | 39 | 6 | 16 | 60 | 101

## Slide 8: NCR Project View
Visual Status of NCRs (open/close, numbers)
  Listing of NCRs by Traveler ID
Helps Prioritize Traveler/Components with the most issues
Drill-down links to Traveler status Query

## Slide 9: NCR Management (QA/Team Level)
NCRs: Non-Conformance Report
  Listing of NCRs, open/close status, related travelers
    Typically found with inspections, but any traveler can apply a NCR
  Linked to specific NCR & Traveler for “Drill Down”
Sort on Disposition, travelers, etc. to Management the NCRs
Drill-down links to individual Travelers

## Slide 10: Travelers Open/Close by Month

## Slide 11: Travelers by Workcenters

## Slide 12: Quality Results Pareto on Parts & Assemblies NCR & Traveler Status for LCLS-II Cryomodule
LCLS-II QA/QC Workshop
Anne McEwen
19-Sep-2017

## Slide 13: Significant NCRs – Reported to SLAC
Condensed for Presentation purposes from the list sent August 31 to SLAC & FERMI
NCR 1085 for CM-6 Venting NCR to be added to next report
LCLS-II 1.3 GHz Cryomodule Significant Non-Conformance Dashboard |  |  |  |  |  |  |  |  |  |  |  |  | 
G | On track, moving to closure |  |  |  |  |  |  |  |  |  |  |  | 
Y | Issues identified, solution being worked |  |  |  |  |  |  |  |  |  |  |  | 
R | Problematic, Project Management attention required - Insufficient Data |  |  |  |  |  |  |  |  |  |  |  | 
Laboratory: Jefferson Lab |  |  |  |  |  |  |  |  |  | Condensed from report of August2017 |  |  | 
NCR# | Color Code Status | Component/ System Name | Serial # | Name of Supplier/ Vendor | Problem or Discrepancy | Responsible Technical Lead | Date of Detection | Location of NCR Detection (Vendor, Lab Shops, etc.) | Expected Date of Closure | Comments | Close Date | Name of Closer | Prototype or Production
566 589 | R | Dressed Cavity | 0202 0280 | Zanon | E max below spec of 19 MV/m | Palczewski/ Daly | 10/27/2016 11/22/2016 | JLab Vertical Test Area | TBD | Project Mgmt Attention Required. |  |  | Production
603 | R | Dressed Cavity | 0208 | Zanon | Low Qo 2e10 | Palczewski/ Daly | 7/10/17 |  | TBD |  |  |  | Production
823 | Y | Dressed Cavity | 0024 | RI | FE onset at 6.5MV/m, lower than spec which is >17.5MV/m. | Palczewski/ Daly | 4/17/17 |  | TBD | A scratch was found on the iris. Cavity is being returned to vendor. |  |  | Production
893 916 | R | Dressed Cavity (NX-B) | 0063 0083 | RI | Q0(16MV) below the spec of 2.5e10 | Palczewski/ Daly | 5/18/2017 5/31/2017 |  | TBD | Project Mgmt Attention Required. |  |  | Production
930 950 | R | Dressed Cavity (NX-A) | 0104 0109 | RI | Q0(16MV) below the spec of 2.5e10 | Palczewski/ Daly | 6/16/17 |  | TBD |  |  |  | Production
1002 | R | Dressed Cavity (NX-B950) | 0099 | RI | Emax below spec of 19 MV/m (18.8) | Palczewski/ Daly | 8/10/17 |  | TBD |  |  |  | Production
841 | Y | CM Final Assembly | CM02 | VAT | Leaky gate valve found during final assembly of CM2 | K. Wilson | 4/28/17 | Work Station 5 | TBD | Technical discussions have begun with Fermilab and VAT. |  |  | Production
331 | R | pCM | J1.3-01 | JLab | Cavities 1, 5, 6 & 7 HOM A < 5E11 Cavities 5, 7 & 8 HOM B < 5E11. Cavity 6 FE Onset @ 12MV/m. Cavity 2, 6, 7 & 8 couplers could not be adjusted to proper setting 4.0E7. | Drury | 8/25/17 | CMTF | TBD | Project Mgmt Attention Required. |  |  | Prototype

## Slide 14: NCR Status by month
pCM (CM-1) NCRs are almost all closed
Production NCRs
% NCRs closed continues to increase

## Slide 15: L2PROTOTYPE Open/Closed by Work center
L2PRO-CM-ACTS
(8) Open NCRs for pCM
Cavities 1, 5, 6 & 7 HOM A lower than 5E11
Cavities 5, 7 & 8 HOM B lower than 5E11
Cavity 8 coupler not 4.0E7
Cavity 7 coupler not 4.0E7
Cavity 6 coupler not 4.0E7
Cavity 2 coupler not 4.0E7
Cavity 6 FEOnset 12MV/m
Reported monthly
SRF-QB Management

## Slide 16: L2PRODUCTION Open/Closed by Work center
80 NCRs Closed in Last Month
9 CAV-INSP-CAV closed
14 FPC closed
6 FeedThrus closed (FPFT & BPMFT)
1 RFIN closed
11 VTRF closed
11 CM closed
15 BLBP closed
3 BLBU closed
10 BLXD closed
Reported monthly
SRF-QB Management

## Slide 17: “Prototype” Cryomodule – CM-1 : NCR View

## Slide 18: Production Cryomodule NCR Project View

## Slide 19: Open “Production” NCRs – Blue are “on Hold”
Chart: 
| L2PRD-CST-INSP-BLBP | L2PRD-CAV-VTRF | L2PRD-CM-INSP-FPCW | L2PRD-CAV-INSP-FPFT | L2PRD-CST-INSP-BLXU | L2PRD-CAV-INSP-CAV | L2PRD-CST-INSP-BLBU | L2PRD-CST-INSP-BLBS | L2PRD-CST-INSP-BLXD | L2PRD-CAV-RECV-CAV | L2PRD-CAV-RECV-FPC | L2PRD-CM-INSP-VV | L2PRD-CM-INSP-UCM | L2PRD-CST-INSP-BPMFT | L2PRD-CAV-INSP-FPC | L2PRD-CM-ASSY-FNAL | L2PRD-CAV-INSP-HMFT
Hold/Modify | 62 | 9 | 1 | 10 | 9 | 3 | 3 | 1 | 3 | 1
Hold/Re-measure | 2 | 7 | 1 | 1 | 1
Proceed to next WorkCenter | 22 | 10 | 1 | 1
No Disposition | 4 | 25 | 15 | 3 | 4 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 1
Parts “on Hold” (Blue) are typically often waiting until needed for re-work

## Slide 20: L2PRODUCTION Open NCR Age
Many NCRs 6 m-1 year are “on Hold” until needed

## Slide 21: NCRs Initiated to First Response
Reported monthly
SRF-QB Management

## Slide 22: Production NCRs Time to Closure
35 15 26 16 7 2
Last week
pCM NCRs are almost all closed, Production chart below (CM-2 on)

## Slide 23: JLAB Traveler Status

## Slide 24: pCM Travelers - by Month &work Center
pCM Travelers closed except
ACTS = Acceptance Test (CMTF)

## Slide 25: Production Travelers by month& work center
Travelers being closed as work is completed

## Slide 26: Summary

## Slide 27: Samples of LCLS II Status Boards & Drilldowns

## Slide 28: Summary
Quality Tools are supporting the Project
  Continuously improving the Reporting functions
QC Results
  NCRs are being address and closed
  Significant NCRs are reported monthly to both SLAC & Fermi Lab

## Slide 29: BACK Up Slides
LCLS-II QA/QC Workshop
19-Sep-2017

## Slide 30: L2PRD Traveler Names & Titles *
Traveler Name | Author | Traveler Title | Traveler Abstract
L2PRD-CST-INSP-BLBP | Katherine Wilson | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | Traveler defines inspection process for cavity string PrCM bellows
L2PRD-CST-INSP-BLBS | Katherine Wilson | LCLS-II Cavity String Weldment Bellows Short Inspection Traveler | Traveler defines inspection process for cavity string short bellows
L2PRD-CST-INSP-BLBU | Katherine Wilson | LCLS-II Cavity String Weldment Upstream Bellows Inspection Traveler | Traveler defines inspection process for cavity string upstream bellows
L2PRD-CST-INSP-BLXD | Katherine Wilson | LCLS-II Cavity String Weldment Extension-DS Inspection Traveler | Traveler defines inspection process for cavity string bellows/spool pieces
L2PRD-CST-INSP-BLXU | Katherine Wilson | LCLS-II Cavity String Weldment Extension-US Inspection Traveler | Traveler defines inspection process for cavity string bellows/spool pieces
L2PRD-CST-INSP-BPMFT | HyeKyoung Park | BPM Feedthrough Incoming Inspection Traveler | Incoming inspection traveler for LCLS-II production BPM feedthrough
L2PRD-CAV-INSP-CAV | Katherine Wilson | L2PRD LCLS-II Cavity Receiving Inspection | Incoming Inspection of Dressed LCLS-II Production Cavities.
L2PRD-CAV-RECV-CAV |  | L2PRD Dressed Cavity Inventory Traveler | Inventory receipt traveler for the L2PRD Dressed Cavity
L2PRD-CAV-VTRF | Kirk Davis | LCLSII (Production Cryomodule) Vertical cavity Testing | Cryogenic RF testing of 1300MHz 9-cell cavities for LCLSII Production Cryomodules
L2PRD-CM-ASSY-FNAL | John Fischer | LCLS2 Production Cryomodule Final Assembly Traveler | This traveler details the assembly and in-process quality control inspections of the LCLS2 Final Assembly. All work will be completed in the Cryomodule Assembly areas. The scope of work begins with a completed Vacuum Vessel Assembly on the cantilevered tooling and ending with a Cryomodule ready to enter the CMTF.
L2PRD-CAV-INSP-FPFT | HyeKyoung Park | LCLS-II Field Probe Feedthru Receiving Inspection | LCLS-II Field Probe feedthru receiving inspection traveler, visual inspection, dimensional checks, cold shock/cycle test, and leak test
L2PRD-CAV-INSP-HMFT | HyeKyoung Park | LCLS-II HOM Feedthru Receiving Inspection | LCLS-II HOM feed thru receiving inspection traveler, visual inspection, dimensional checks, cold shock/cycle test, and leak test
L2PRD-CAV-INSP-FPC | HyeKyoung Park | Inspection FPC- Fundamental Power Coupler | Covers FPCs incoming inspection and acceptance tests at JLAB
L2PRD-CAV-RECV-FPC | M. Stirbet | L2PRD FPC receiving (Fundamental Power Coupler ) | Covers LCLSII FPC receiving traveler
L2PRD-CM-INSP-FPCW | M. Stirbet | LCLS-II warm FPC incoming Inspection | Covers FPCs incoming inspection and acceptance tests at JLAB
L2PRD-CM-INSP-UCM | Gary Cheng | LCLS-II Upper Cold Mass Incoming Inspection | This traveler is to be used for the incoming inspection for the LCLS-II production cryomodule Upper Cold Mass (UCM).
L2PRD-CM-INSP-VV | Gary Cheng | Receiving Inspection of LCLS-II Production Cryomodule Vacuum Vessel | This traveler is for inspection of LCLS-II Production Cryomodule Vacuum Vessel
* Limited to Travelers with open NCRs as of 18Sep2017

## Slide 31: Significant NCRs – Reported to SLAC (August 2017)
LCLS-II 1.3 GHz Cryomodule Significant Non-Conformance Dashboard |  |  |  |  |  |  |  |  |  |  |  |  | 
G | On track, moving to closure |  |  |  |  |  |  |  |  |  |  |  | 
Y | Issues identified, solution being worked |  |  |  |  |  |  |  |  |  |  |  | 
R | Problematic, Project Management attention required - Insufficent Data |  |  |  |  |  |  |  |  |  |  |  | 
Laboratory: Jefferson Lab |  |  |  |  |  |  |  |  |  | Data Month of: August 2017 |  |  | 
NCR# | Color Code Status | Component/ System Name | Serial # | Name of Supplier/ Vendor | Problem or Discrepancy | Responsible Technical Lead | Date of Detection | Location of NCR Detection (Vendor, Lab Shops, etc.) | Expected Date of Closure | Comments | Close Date | Name of Closer | Prototype or Production
566 | R | Dressed Cavity | 0202 | Zanon | At 2K Emax is 14.9 MV/m, lower than spec which is 19 MV/m. No Q0 measurement available at 16 MV/m either. | Palczewski/ Daly | 10/27/16 | JLab Vertical Test Area | TBD | Project Mgmt Attention Required. |  |  | Production
589 | R | Dressed Cavity | 0201 | Zanon | Final 2K run, Emax 16.6MV/m, lower than spec (19MV/m). | Palczewski/ Daly | 11/22/16 |  |  |  |  |  | 
603 | R | Dressed Cavity | 0208 | Zanon | Low Qo 2e10 | Palczewski/ Daly | 7/10/17 |  |  |  |  |  | 
823 | Y | Dressed Cavity | 0024 | RI | FE onset at 6.5MV/m, lower than spec which is >17.5MV/m. | Palczewski/ Daly | 4/17/17 |  |  | A scratch was found on the iris. Cavity is being returned to vendor. |  |  | 
841 | Y | CM Final Assembly | CM02 | VAT | Leaky gate valve found during final assembly of CM2 | K. Wilson | 4/28/17 | Work Station 5 |  | Technical discussions have begun with Fermilab and VAT. |  |  | 
893 | R | Dressed Cavity (NX-B) | 0063 | RI | Q0(16MV) was 2.1e10, below the specification of 2.5e10 | Palczewski/ Daly | 5/18/17 | JLab Vertical Test Area |  | Project Mgmt Attention Required. |  |  | 
916 | R | Dressed Cavity (NX-B) | 0083 | RI | Initial Q0(16) measured 1.87e+10, below the specification of 2.5e10 | Palczewski/ Daly | 5/31/17 |  |  |  |  |  | 
930 | R | Dressed Cavity (NX-A) | 0104 | RI | Q0(16)Measured 2.20e+10, below spec 2.5e10 | Palczewski/ Daly | 6/16/17 |  |  |  |  |  | 
950 | R | Dressed Cavity (NX-A) | 0109 | RI | Q0 at 16MV/m was 2.38e10, lower than spec which is 2.5e10. | Palczewski/ Daly | 6/28/17 |  |  |  |  |  | 
1002 | R | Dressed Cavity (NX-B950) | 0099 | RI | Cavity did not make it to 19 MV/m. It only made it to 18.8 +/- 1 MV/m | Palczewski/ Daly | 8/10/17 |  |  |  |  |  | 
331 | R | pCM | J1.3-01 | JLab | Cavities 1, 5, 6 & 7 HOM A lower than 5E11. Cavities 5, 7 & 8 HOM B lower than 5E11. Cavity 6 FE Onset @ 12MV/m. Cavity 2, 6, 7 & 8 couplers could not be adjusted to proper setting 4.0E7. | Drury | 8/25/17 | CMTF |  |  |  |  | Prototype

## Slide 32: NCRs - Pareto of issues for Production
Bellows & Spools - includes Scratches, Pits, Dings, Roughness (Profilometer ) , Plating, Stains , Oxidization , Residues (Not checked dimensionally)
Probes (Field HOM, BPM) : Scratches , Dimensional
Cavities & Helium Vessels : some Dimensional issues, mainly VTRF Performance (VTA Test) occasional RF Failure (test not started), Cavity Shock Sensors (shipping)
Vacuum Vessels : Scratches and paint on flanges
Mag Shield – Dents, scratches, incomplete welds

## Slide 33: Back Up Slides LCLS II Quality Reports & Documents
LCLS-II QA/QC Workshop
19-Sep-2017

## Slide 34: LCLS II Status Boards and Drilldowns

## Slide 35: LCLS II Traveler Reports

## Slide 36: LCLS II NCR Reports