## Sheet1
1 | Single-phase APA
1.1 | TPC Simulation and software
1.1.1 | Simulations
1.1.1.1 | Overall TPC simulation (electric field, electron lifetimes, diffusion)
1.1.1.2 | Simulation of signal shapes on APA wires
1.1.1.3 | Development of a realistic simulation (noise, missing wires, running conditions...)
1.1.2 | Database design for TPC construction
1.1.3 | Data monitoring code (slow control?)
1.2 | APA Design
1.2.1 | Validation of APA (+CPA, field cage,…) design in terms of requirements and performance based on ProtoDUNE data
1.2.1.1 | Validation of APA wire spacing,wire orientation, etc.
1.2.1.2 | Specifications on wire voltages, wire tension, alignment criteria, allowed number of non-working wires
1.2.2 | Interfaces with other subsystems
1.2.2.1 | Interface requirements with cryostat (DSS)
1.2.2.2 | Interface requirements with TPC cold electronics (cabling,…)
1.2.2.3 | Interface requirements with photon detectors
1.2.3 | Frames
1.2.3.1 | Design evaluation
1.2.4 | Wire and mesh
1.2.4.1 | Evaluation of wire/mesh material and size
1.2.5 | Combs
1.2.5.1 | Design evaluation
1.2.6 | Tooth Strips
1.2.6.1 | Design evaluation
1.2.7 | X, V, U and G Layer Boards
1.2.7.1 | Design evaluation
1.2.8 | CR Boards
1.2.8.1 | Design evaluation
1.2.9 | Interface Boards
1.2.9.1 | Design evaluation
1.2.10 | SHV Boards
1.2.10.1 | Design evaluation
1.2.11 | Support hardware (yoke, CE brackets)
1.2.11.1 | Design evaluation
1.2.12 | Detector Support Structure (DSS)
1.2.12.1 | Design
1.2.13 | Set QA requirements for APA production
1.2.14 | Editing of Technical Proposal
1.2.15 | Editing of TDR chapter
1.3 | APA Engineering and Tooling
1.3.1 | System engineering
1.3.1.1 | Internal Interface Specifications (among APA components)
1.3.1.2 | External Interface Specifications (with other subsystems)
1.3.1.3 | FEA analyses for single and assembled APAs, in warm and cold conditions
1.3.1.4 | FEA analyses for handling and transportation of APAs
1.3.2 | ProductionPlanning
1.3.2.1 | Set requirements on site infrastructure
1.3.2.2 | Site selection for APA production
1.3.2.3 | Develop a plan for production at multiple sites
1.3.2.4 | Develop safety procedures for production
1.3.3 | QA Plan
1.3.3.1 | Material certification
1.3.3.2 | Specification of procedures and tests
1.3.3.3 | Specification of acceptance criteria
1.3.4 | QC Plan
1.3.4.1 | Evaluate current assembly procedure and travelers
1.3.5 | Winder
1.3.5.1 | Design evaluation & incremental improvements
1.3.5.2 | Winder fabrication for multiple sites
1.3.6 | Process cart
1.3.6.1 | Fabrication for multiple sites
1.3.7 | Tooth strip bonding jigs
1.3.7.1 | Fabrication for multiple sites
1.3.8 | Tension measurements tool
1.3.8.1 | Choice of measurement techniques
1.3.8.2 | Fabrication for multiple sites
1.3.9 | Electrical test hardware
1.3.9.1 | Continuity test setup
1.3.9.2 | Leakage current test setup
1.3.9.3 | Fabrication/procurement for multiple sites
1.3.10 | Cryogenic testing hardware
1.3.10.1 | Evaluate design and requirements
1.3.10.2 | Fabrication
1.3.10.3 | Operation (integration facility?)
1.3.11 | Shipping Box and diagnostics
1.3.11.1 | Evaluate and update ProtoDUNE design
1.3.11.2 | Fabrication for multiple sites
1.4 | APA Production
1.4.1 | Frames
1.4.1.1 | Material sourcing and procurement for 150 units
1.4.1.2 | Assembly/inspection procedure and traveler
1.4.1.3 | Production of 150 units
1.4.1.4 | Survey and acceptance
1.4.2 | Wire and mesh (incl. tooling and installation)
1.4.2.1 | Wire: material sourcing and procurement for xxx m
1.4.2.2 | Mesh: material sourcing and procurement for 300 units
1.4.2.3 | Tooling design improvements
1.4.2.4 | Mesh installation
1.4.3 | Combs (including tooling and installation)
1.4.3.1 | Material sourcing and procurement for xxx units
1.4.3.2 | Tooling production
1.4.3.3 | Comb installation
1.4.4 | Tooth Strips
1.4.4.1 | Procurement for xxx units
1.4.4.2 | Inspection/Processing
1.4.5 | X Layer Boards
1.4.5.1 | Procurement for xxx units
1.4.5.2 | Inspection/Processing
1.4.6 | V Layer Boards
1.4.6.1 | Procurement for xxx units
1.4.6.2 | Inspection/Processing
1.4.7 | U Layer Boards
1.4.7.1 | Procurement for xxx units
1.4.7.2 | Inspection/Processing
1.4.8 | G Layer Boards
1.4.8.1 | Procurement for xxx units
1.4.8.2 | Inspection/processing
1.4.9 | CR Boards
1.4.9.1 | Procurement for xxx units
1.4.9.2 | Inspection/Processing
1.4.9.3 | Test Stand Development
1.4.9.4 | Testing
1.4.9.5 | Cleaning
1.4.10 | Interface Boards
1.4.10.1 | Procurement for xxx units
1.4.10.2 | Inspection/Processing
1.4.11 | SHV Boards
1.4.11.1 | Procurement for xxx units
1.4.11.2 | Inspection/Processing
1.4.12 | Support hardware (yoke, CE brackets)
1.4.12.1 | Material sourcing and procurement
1.4.12.2 | Fabrication
1.4.13 | Detector Dupport Structure (DSS)
1.4.13.1 | Procurement/Fabrication
1.4.13.2 | Engineering analysis/FEA in warm and cold conditions
1.4.14 | Assemble production lines
1.4.14.1 | Factory # xx assembly line # xy
1.4.15 | APA production sequence for 150 APAs
1.4.15.1 | APA # 001 at Factory # xx assembly line # xy
1.5 | APA Integration and Installation
1.5.1 | Shipping
1.5.1.1 | APA shipping plan
1.5.1.2 | APA shipping sequence
1.5.2 | Integration
1.5.2.1 | Develop integration plan
1.5.2.1.1 | Choice of integration facility
1.5.2.2 | APA Integration with photon detectors and cold electronics
1.5.3 | Installation at SURF
1.5.3.1 | Develop installation plan for DSS
1.5.3.2 | Develop installation plan for APAs
1.5.3.3 | Develop safety procedures for installation
1.5.3.4 | Fabricate custom installation hardware
1.5.3.5 | APA inspection and QC at SURF
1.5.3.6 | Installation
1.5.3.6.1 | Installation of DSS
1.5.3.6.2 | Installation sequence for 150 APAs
1.5.3.7 | APAs survey after installation
1.6 | TPC Calibration
1.6.1 | Development of Calibration requirements and techniques
1.6.2 | Calibration systems
1.6.2.1 | Specifications
1.6.2.2 | Design
1.6.2.3 | Fabrication
1.6.2.4 | Installation/Commissioning
1.6.3 | Calibration software/database