## Feuil1
WBS Element | WBS Element name | WBS dictionary | Institutions | Deliverable Reference
1 | DP Electronics - Hardware Components
1.1 | FE Cryogenic ASIC
1.1.1 | FE Cryogenic ASIC design
1.1.1.1 | FE Cryogenic ASIC design (existing design for first DP module) | Design of analog FE cryogenic ASIC | IPNL | A-1-i
1.1.1.2 | FE Cryogenic ASIC design (2nd DP module) | Design of analog FE cryogenic ASIC, possible developments for second 10 kton DP module | IPNL,KEK,NITKC,IU | A-1-i
1.1.2 | FE Cryogenic ASIC production
1.1.2.1 | FE Cryogenic ASIC production (IPNL) | Production of analog FE cryogenic ASICs, production site #1 | IPNL | A-1-ii
1.1.2.2 | FE Cryogenic ASIC production (KEK) | Production of analog FE cryogenic ASICs, production site #2, depending on funding | KEK,NITKC,IU | A-1-ii
1.1.3 | FE Cryogenic ASIC testing
1.1.3.1 | FE Cryogenic ASIC testing (IPNL) | Testing of analog FE cryogenic ASICs, testing site #1 | IPNL | A-1-iii
1.1.3.2 | FE Cryogenic ASIC testing (KEK) | Testing of analog FE cryogenic ASICs, testing site #2 | KEK,NITKC,IU | A-1-iii
1.1.3.3 | FE Cryogenic ASIC testing (SMU) | Testing of analog FE cryogenic ASICs, testing site #3 | SMU | A-1-iii
1.2 | FE Cryogenic Cards
1.2.1 | FE cryogenic cards design
1.2.1.1 | FE cryogenic cards design (existing design for first DP module) | Design of the analog FE cryogenic cards (64 channels) | IPNL | A-2-i
1.2.1.2 | FE cryogenic cards design (2nd DP module) | Design of the analog FE cryogenic cards (64 channels), possible developments for second 10 kton DP module | IPNL,KEK,NITKC,IU,SMU | A-2-i
1.2.2 | FE cryogenic cards production
1.2.2.1 | FE cryogenic cards production (IPNL) | Production of analog FE cryogenic cards (64 channels), Production site #1 | IPNL | A-2-ii
1.2.2.2 | FE cryogenic cards production (KEK) | Production of analog FE cryogenic cards (64 channels), Production site #2, depending on funding | KEK,NITKC,IU | A-2-ii
1.2.3 | FE cryogenic cards testing
1.2.3.1 | FE cryogenic cards testing (IPNL) | Testing of analog FE cryogenic cards (64 channels), Testing site #1 | IPNL | A-2-iii
1.2.3.2 | FE cryogenic cards testing KEK) | Testing of analog FE cryogenic cards (64 channels), Testing site #2 | KEK,NITKC,IU | A-2-iii
1.2.3.3 | FE cryogenic cards testing (SMU) | Testing of analog FE cryogenic cards (64 channels), Testing site #3 | SMU | A-2-iii
1.3 | SFT
1.3.1 | SFT Internal Cabling
1.3.1.1 | SFT internal cabling prod. | Production of cold flanges, cables on insertion blades of Signal Feedthroughs (SFT) chimneys | KEK,NITKC,IU | A-3-ii
1.3.1.2 | SFT internal cabling test. | Testing of cold flanges, cables on insertion blades of Signal Feedthroughs (SFT) chimneys | KEK,NITKC,IU | A-3-iii
1.3.2 | SFT warm flanges
1.3.2.1 | SFT warm flanges design | Design of warm flanges of SFT chimneys: printed circuit board including interface to internal cabling, connections to uTCA DAQ and to LV power supply and slow control | IPNL,KEK,NITKC,IU | A-4-i
1.3.2.2 | SFT warm flanges production | Production of warm flanges PCBs of SFT chimneys | KEK,NITKC,IU | A-4-ii
1.3.2.3 | SFT warm flanges testing | Testing of warm flanges PCBs of SFT chimneys | KEK,NITKC,IU | A-4-iii
1.3.3 | SFT Chimneys
1.3.3.1 | SFT chimneys design | Design of Signal Feedthrough Chimenys: vacuum tight vessel, warm and cold flanges mechanics, blades, blades insertion mechanism |  | A-5-i
1.3.3.2 | SFT chimneys fabrication | Production of Signal Feedthrough Chimenys: vacuum tight vessel, warm and cold flanges mechanics, blades, blades insertion mechanism |  | A-5-ii
1.3.3.3 | SFT chimneys assembly | Assembly of chimneys mechanics with warm and cold flanges PCBs |  | A-5-iii
1.3.3.4 | SFT chimneys testing | Testing of SFT chimneys, tightness, blades insertion |  | A-5-iv
1.3.3.5 | SFT chimneys installation | Installation of SFT chimneys on the cryostat penetrations |  | A-5-v
1.3.4 | SFT cabling to uTCA
1.3.4.1 | SFT cabling to uTCA design | Shielded, high density differential signal cables from SFT chimneys to uTCA crates, selection of cables and validation | IPNL | A-6-i
1.3.4.2 | SFT cabling to uTCA proc. | Signal cables from SFT chimneys to uTCA crates, cables procurement |  | A-6-ii
1.3.4.3 | SFT cabling to uTCA testing | Signal cables from SFT chimneys to uTCA crates, cables testing, QA/QC |  | A-6-iii
1.4 | Analog FE external cabling
1.4.1 | Analog FE external cabling design | Cabling of LV power supply, ASIC slow control and pulsing system to SFT warm flanges, selection of cables and validation | IPNL | A-7-i
1.4.2 | Analog FE external cabling proc. | SFT warm flanges cables procurement |  | A-7-ii
1.4.3 | Analog FE external cabling testing | SFT warm flanges cables testing, QA/QC |  | A-7-iii
1.4 | uTCA
1.5.1 | uTCA crates infrastructure
1.5.1.1 | uTCA crates infrastructure design | Selection and validation of uTCA crates, fan units, power units and MCH swicthes | IPNL | A-8-i
1.5.1.2 | uTCA crates infrastructure proc. | Procurement of uTCA crates, fan units, power units and MCH swicthes | IPNL,… | A-8-ii
1.5.1.3 | uTCA crates infrastructure test. | Testing of uTCA crates after installation at SURF |  | A-8-iii
1.5.2 | uTCA digitization cards
1.5.2.1 | uTCA digitization cards design | Design of uTCA AMC cards for the charge readout digitization | IPNL | A-9-i
1.5.2.2 | uTCA digitization cards firmw. | Firmware development for the FPGA on the uTCA AMC cards for the charge readout digitization handling the FE DAQ functions | IPNL | A-9-ii
1.5.2.3 | uTCA digitization cards prod. (IPNL) | Production of the uTCA AMC cards for the charge readout digitization, production site #1 | IPNL | A-9-iii
1.5.2.4 | uTCA digitization cards prod. (KEK) | Production of the uTCA AMC cards for the charge readout digitization, production site #2, depending on funding | KEK,NITKC,IU | A-9-iii
1.5.2.5 | uTCA digitization cards test. (IPNL) | Testing of the uTCA AMC cards for the charge readout digitization, testing site #1 | IPNL | A-9-iv
1.5.2.6 | uTCA digitization cards test. (KEK) | Testing of the uTCA AMC cards for the charge readout digitization, testing site #2 | KEK,NITKC,IU | A-9-iv
1.5.3 | uTCA WR slave nodes
1.5.3.1 | uTCA WR slave nodes design | Design of White Rabbit slave node cards for timing/triggers distribution to the uTCA crates | IPNL | A-10-i
1.5.3.2 | uTCA WR slave nodes prod. (IPNL) | Production of White Rabbit slave node cards for timing/triggers distribution to the uTCA crates, prod site #1 | IPNL | A-10-ii
1.5.3.3 | uTCA WR slave nodes prod. (KEK) | Production of White Rabbit slave node cards for timing/triggers distribution to the uTCA crates, prod site #2, depending on funding | KEK,NITKC,IU | A-10-ii
1.5.3.4 | uTCA WR slave nodes testing. (IPNL) | Testing of White Rabbit slave node cards for timing/triggers distribution to the uTCA crates, testing site #1, connected to AMC tests | IPNL | A-10-iii
1.5.3.5 | uTCA WR slave nodes testing. (KEK) | Testing of White Rabbit slave node cards for timing/triggers distribution to the uTCA crates, testing site #2, connected to AMC tests | KEK,NITKC,IU | A-10-iii
1.6 | LV Power Supplies
1.6.1 | LV power supplies design | Selection and validation of low voltage power supplies for analog FE | IPNL,KEK,NITKC,IU | A-11-i
1.6.2 | LV power supplies proc. | Procurement of low voltage power supplies |  | A-11-ii
1.6.3 | LV power supplies testing | Testing of low voltage power supplies and of filter boxes (connected to procurement) |  | A-11-iii
1.7 | LRO FE Electronics
1.7.1 | LRO FE electronics connection | Design and production of interface between PMTs and FE | APC, LAPP | A-12-i
1.7.2 | LRO FE electronics analog | Development and design of the analog section of the FE cards | APC | A-12-ii
1.7.3 | LRO FE electronics digital | Development and design of the digital section of the FE cards | APC, LAPP | A-12-iii
1.7.4 | LRO FE electronics uTCA int. | Design of the integration in the uTCA backplane | APC, LAPP | A-12-iv
1.7.5 | LRO FE electronics components | Selection of cards components and procurement | APC, LAPP | A-12-v
1.7.6 | LRO FE electronics cards prod. | Production and testing of the uTCA cards | APC, LAPP | A-12-vi
1.7.7 | LRO FE electronics trig. firmware | Programming of the FPGA to provide triggers and fast signals treatment | APC, LAPP | A-12-vii
1.7.8 | LRO FE electronics DAQ | Programming of the interface to uTCA backplane and DAQ | APC, LAPP | A-12-viii
1.7.9 | LRO FE electronics timing | Synchronization with White Rabbit | APC, LAPP | A-12-ix
1.8 | Infrastructure
1.8.1 | Infrastructure routing plan | Develop Cables Routing Plan (optical fibers for White Rabbit and data, LV, calibration and controls, power for uTCA crates) |  | A-13-i
1.8.2 | Infra. LV distribution
1.8.2.1 | Infra. LV distribution design | Design LV filtering/distribution boxes and cable support structures |  | A-13-ii
1.8.2.2 | Infra. LV distribution prod. | Fabricate LV filtering/distribution boxes and cable support structures |  | A-13-iii
1.8.3 | Infra installation plan | Develop General Installation Plan |  | A-13-iv
1.8.4 | Infra LV PS integration | Integration of Low Voltage power supplies |  | A-13-v
1.8.5 | Infra. Analog FE installation | Installation of FE electronics + blades in the SFT chimneys (SURF) | IPNL,KEK,NITKC,IU, SMU +… | A-13-vi
1.8.6 | Infra LRO FE installation | Installation of light readout FE electronics AMC cards in the uTCA crates | APC, LAPP, + … | A-13-vii
1.8.7 | Infra uTCA installation | Installation of uTCA crates + MCHs + AMCs + WR slaves (SURF) |  | A-13-viii
1.8.8 | Infra AMC installation | Installation of charge readout FE electronics AMC cards in the uTCA crates (SURF) | IPNL,KEK,NITKC,IU, +… | A-13-ix
1.8.9 | Infra uTCA analog cabling | Cabling of uTCA crates to warm flanges for the connection of the analog signals (SURF) |  | A-13-x
1.8.10 | Infra LV cabling | Cabling of low voltages, calibration signals and slow controls to chimneys (SURF) |  | A-13-xi
1.8.11 | Infra fibers cabling | Cabling of optical fibers (data links and White Rabbit links) to DAQ backend (SURF) |  | A-13-xii
1.8.12 | Infra installation tests | Test electronics/cables (SURF) | IPNL,KEK,NITKC,IU, APC, LAPP, SMU +… | A-13-xiii
2 | DP Electronics - Software
2.1 | Simulation
2.1.1 | Simulation code analog
2.1.1.1 | Simulation code analog (IPNL) | Simulation code for analog signal processing, charge readout | IPNL,KEK,NITKC,IU | B-1-i
2.1.1.2 | Simulation code analog (APC) | Simulation code for analog signal processing, LRO | APC, LAPP | B-1-i
2.1.2 | Simulation code digital
2.1.2.1 | Simulation code digital (IPNL) | Simulation code for digital signal processing, charge readout | IPNL,KEK,NITKC,IU | B-1-ii
2.1.2.2 | Simulation code digital (APC) | Simulation code for digital signal processing, LRO | APC, LAPP | B-1-ii
2.2 | Calibration
2.2.1 | Calibration control | Run control software |  | B-2-i
2.2.2 | Calibration software | Analysis software |  | B-2-ii
2.2.3 | Calibration DB | Calibration database |  | B-2-iii
2.3 | DB for Hardware QA/QC
2.3.1 | Hardware DB QA | QA/QC documentation (connection with components testing) | IPNL,KEK,NITKC,IU, LAPP, APC, SMU+ … | B-3-i
2.3.2 | Hardware DB Tracking | Components tracking (connection with components production and testing) | IPNL,KEK,NITKC,IU, LAPP, APC, SMU,+ … | B-3-ii
2.4 | Data collection monitoring
2.4.1 | Data collection config | Hardware initialization/configuration code | IPNL, APC, LAPP | B-4-i
2.4.2 | Data collection harware monitor | Hardware monitoring code |  | B-4-ii
2.5 | Data monitoring code | Data monitoring code |  | B-5
3 | DP Electronics - Physics
3.1 | Physics analog FE requirements | Validation of Cold Electronics Requirements with respect to Physics Performance | IPNL,KEK,NITKC,IU,SMU | C-1
3.2 | Physics analog FE validation | Cold Electronics Performance Validation via ProtoDUNE Data Analysis | IPNL,KEK,NITKC,IU | C-2
3.3 | Physics TDR | Editing of TDR chapter | IPNL,KEK,NITKC,IU, LAPP, APC, SMU + … | C-3
4 | DP Electronics - Integration
4.1 | Grounding plan | Detector grounding and shielding Plan | IPNL,KEK,NITKC,IU | D-1
4.2 | ITF | Integration test facility design |  | D-2-i
4.2.1 | ITF design
4.2.2 | ITF fabrication | Integration test facility procurement |  | D-2-ii
4.2.3 | ITF operation | Integration test facility operation |  | D-2-iii