## Sheet1
1 | Single-phase APA
1.1 | TPC Simulation and software
1.1.1 | Simulations
1.1.1.1 | Overall TPC simulation (electric field, electron lifetimes, diffusion)
1.1.1.2 | Simulation of signal shapes on APA wires
1.1.1.3 | Development of a realistic simulation (noise, missing wires, running conditions...)
1.1.2 | Database design for TPC construction
1.1.3 | Data monitoring code (slow control?)
1.2 | APA Design
1.2.1 | Validation of APA (+CPA, field cage,…) design in terms of requirements and performance based on ProtoDUNE data
1.2.1.1 | Validation of APA wire spacing,wire orientation, etc.
1.2.1.2 | Specifications on wire voltages, wire tension, alignment criteria, allowed number of non-working wires
1.2.2 | Interfaces with other subsystems
1.2.2.1 | Interface requirements with cryostat (DSS)
1.2.2.2 | Interface requirements with TPC cold electronics (cabling,…)
1.2.2.3 | Interface requirements with photon detectors
1.2.3 | Frames
1.2.3.1 | Design evaluation
1.2.4 | Wire and mesh
1.2.4.1 | Evaluation of wire/mesh material and size
1.2.5 | Combs
1.2.5.1 | Design evaluation
1.2.6 | Tooth Strips
1.2.6.1 | Design evaluation
1.2.7 | X, V, U and G Layer Boards
1.2.7.1 | Design evaluation
1.2.8 | CR Boards
1.2.8.1 | Design evaluation
1.2.9 | Interface Boards
1.2.9.1 | Design evaluation
1.2.10 | SHV Boards
1.2.10.1 | Design evaluation
1.2.11 | Support hardware (yoke, CE brackets)
1.2.11.1 | Design evaluation
1.2.12 | Interface with Detector Support Structure (DSS) design team
1.2.12.1 | Evaluation of the design in terms of alignment requirements
1.2.13 | Set QA requirements for APA production
1.2.14 | Editing of Technical Proposal
1.2.15 | Editing of TDR chapter
1.3 | APA Engineering
1.3.1 | System engineering
1.3.1.1 | Internal Interface Specifications (among APA components)
1.3.1.2 | External Interface Specifications (with other subsystems)
1.3.1.3 | FEA analyses for single and assembled APAs, in warm and cold conditions
1.3.1.4 | FEA analyses for handling and transportation of APAs
1.3.2 | ProductionPlanning
1.3.2.1 | Set requirements on site infrastructure
1.3.2.2 | Site selection for APA production
1.3.2.3 | Develop a plan for production at multiple sites
1.3.2.4 | Develop safety procedures for production
1.3.3 | QA Plan
1.3.3.1 | Material certification
1.3.3.2 | Specification of procedures and tests
1.3.3.3 | Specification of acceptance criteria
1.3.4 | QC Plan
1.3.4.1 | Evaluate current assembly procedure and travelers
1.4 | APA Tooling
1.4.1 | Winder
1.4.1.1 | Design evaluation & incremental improvements
1.4.1.2 | Winder fabrication for multiple sites
1.4.2 | Process cart
1.4.2.1 | Fabrication for multiple sites
1.4.3 | Tooth strip bonding jigs
1.4.3.1 | Fabrication for multiple sites
1.4.4 | Tension measurements tool
1.4.4.1 | Choice of measurement techniques
1.4.4.2 | Fabrication for multiple sites
1.4.5 | Electrical test hardware
1.4.5.1 | Continuity test setup
1.4.5.2 | Leakage current test setup
1.4.5.3 | Fabrication/procurement for multiple sites
1.4.6 | Cryogenic testing hardware
1.4.6.1 | Evaluate design and requirements
1.4.6.2 | Fabrication
1.4.6.3 | Operation (integration facility?)
1.4.7 | Shipping Box and diagnostics
1.4.7.1 | Evaluate and update ProtoDUNE design
1.4.7.2 | Fabrication for multiple sites
1.5 | APA Components Production
1.5.1 | Frames
1.5.1.1 | Frames Module 1
1.5.1.1.1 | Material sourcing and procurement for 150 units
1.5.1.1.2 | Assembly/inspection procedure and traveler
1.5.1.1.3 | Production of 150 units
1.5.1.1.4 | Survey and acceptance
1.5.1.2 | Frames Module 2
1.5.1.2.1 | Material sourcing and procurement for 150 units
1.5.1.2.2 | Assembly/inspection procedure and traveler
1.5.1.2.3 | Production of 150 units
1.5.1.2.4 | Survey and acceptance
1.5.2 | Wire and mesh (incl. tooling and installation)
1.5.2.1 | Wire and Mesh Module 1
1.5.2.1.1 | Wire: material sourcing and procurement for xxx m
1.5.2.1.2 | Mesh: material sourcing and procurement for 300 units
1.5.2.1.3 | Tooling design improvements
1.5.2.1.4 | Mesh installation
1.5.2.2 | Wire and Mesh Module 2
1.5.2.2.1 | Wire: material sourcing and procurement for xxx m
1.5.2.2.2 | Mesh: material sourcing and procurement for 300 units
1.5.2.2.3 | Mesh installation
1.5.3 | Combs (including tooling and installation)
1.5.3.1 | Combs Module 1
1.5.3.1.1 | Material sourcing and procurement for xxx units
1.5.3.1.2 | Tooling production
1.5.3.1.3 | Comb installation
1.5.3.2 | Combs Module 2
1.5.3.2.1 | Material sourcing and procurement for xxx units
1.5.3.2.2 | Comb installation
1.5.4 | Tooth Strips
1.5.4.1 | Tooth Strips Module 1
1.5.4.1.1 | Procurement for xxx units
1.5.4.1.2 | Inspection/Processing
1.5.4.2 | Tooth Strips Module 2
1.5.4.2.1 | Procurement for xxx units
1.5.4.2.2 | Inspection/Processing
1.5.5 | X Layer Boards
1.5.5.1 | X Layer Boards Module 1
1.5.5.1.1 | Procurement for xxx units
1.5.5.1.2 | Inspection/Processing
1.5.5.2 | X Layer Boards Module 2
1.5.5.2.1 | Procurement for xxx units
1.5.5.2.2 | Inspection/Processing
1.5.6 | V Layer Boards
1.5.6.1 | V Layer Boards Module 1
1.5.6.1.1 | Procurement for xxx units
1.5.6.1.2 | Inspection/Processing
1.5.6.2 | V Layer Boards Module 2
1.5.6.2.1 | Procurement for xxx units
1.5.6.2.2 | Inspection/Processing
1.5.7 | U Layer Boards
1.5.7.1 | U Layer Boards Module 1
1.5.7.1.1 | Procurement for xxx units
1.5.7.1.2 | Inspection/Processing
1.5.7.2 | U Layer Boards Module 2
1.5.7.2.1 | Procurement for xxx units
1.5.7.2.2 | Inspection/Processing
1.5.8 | G Layer Boards
1.5.8.1 | G Layer Boards Module 1
1.5.8.1.1 | Procurement for xxx units
1.5.8.1.2 | Inspection/processing
1.5.8.2 | G Layer Boards Module 2
1.5.8.2.1 | Procurement for xxx units
1.5.8.2.2 | Inspection/processing
1.5.9 | CR Boards
1.5.9.1 | Test stand Development
1.5.9.2 | CR Boards Module 1
1.5.9.2.1 | Procurement for xxx units
1.5.9.2.2 | Inspection/Processing
1.5.9.2.3 | Testing
1.5.9.2.4 | Cleaning
1.5.9.3 | CR Boards Module 2
1.5.9.3.1 | Procurement for xxx units
1.5.9.3.2 | Inspection/Processing
1.5.9.3.3 | Testing
1.5.9.3.4 | Cleaning
1.5.10 | Interface Boards
1.5.10.1 | Interface Boards Module 1
1.5.10.1.1 | Procurement for xxx units
1.5.10.1.2 | Inspection/Processing
1.5.10.2 | Interface Boards Module 2
1.5.10.2.1 | Procurement for xxx units
1.5.10.2.2 | Inspection/Processing
1.5.11 | SHV Boards
1.5.11.1 | SHV Boards Module 1
1.5.11.1.1 | Procurement for xxx units
1.5.11.1.2 | Inspection/Processing
1.5.11.2 | SHV Boards Module 2
1.5.11.2.1 | Procurement for xxx units
1.5.11.2.2 | Inspection/Processing
1.5.12 | Support hardware (yoke, CE brackets)
1.5.12.1 | Support Hardware Module 1
1.5.12.1.1 | Material sourcing and procurement
1.5.12.1.2 | Fabrication
1.5.12.2 | Support Hardware Module 2
1.5.12.2.1 | Material sourcing and procurement
1.5.12.2.2 | Fabrication
1.6 | APA Assembly
1.6.1 | APA Assembly for Module 1
1.6.1.1 | Designate Production Management Team
1.6.1.2 | Factory UK
1.6.1.2.1 | Production at Factory UK
1.6.1.2.1.1 | Assemble production line(s)
1.6.1.2.1.2 | APA production sequence at assembly line #xx
1.6.1.2.2 | Shipping from Factory UK to Integration Facility
1.6.1.2.2.1 | APA shipping plan
1.6.1.2.2.2 | APA shipping sequence
1.6.1.3 | Factory US
1.6.1.3.1 | Production at Factory US
1.6.1.3.1.1 | Assemble production line(s)
1.6.1.3.1.2 | APA production sequence at assembly line #xx
1.6.1.3.2 | Shipping from Factory US to Integration Facility
1.6.1.3.2.1 | APA shipping plan
1.6.1.3.2.2 | APA shipping sequence
1.6.2 | APA Assembly for Module 2
1.6.2.1 | Designate Production Management Team
1.6.2.2 | Factory UK
1.6.2.2.1 | Production at Factory UK
1.6.2.2.1.1 | Assemble production line(s)
1.6.2.2.1.2 | APA production sequence at assembly line #xx
1.6.2.2.2 | Shipping from Factory UK to Integration Facility
1.6.2.2.2.1 | APA shipping plan
1.6.2.2.2.2 | APA shipping sequence
1.6.2.3 | Factory US
1.6.2.3.1 | Production at Factory US
1.6.2.3.1.1 | Assemble production line(s)
1.6.2.3.1.2 | APA production sequence at assembly line #xx
1.6.2.3.2 | Shipping from Factory US to Integration Facility
1.6.2.3.2.1 | APA shipping plan
1.6.2.3.2.2 | APA shipping sequence
1.7 | APA Integration
1.7.1 | Develop integration plan
1.7.1.1 | Selection of integration facility
1.7.1.2 | Fabricate custom integration hardware
1.7.2 | APA Integration with photon detectors and cold electronics
1.7.2.1 | Integration Module 1
1.7.2.1.1 | APA inspection and QC
1.7.2.1.2 | APA Integration sequence
1.7.2.2 | Integration Module 2
1.7.2.2.1 | APA inspection and QC
1.7.2.2.2 | APA Integration sequence
1.7.3 | Shipping to SURF
1.7.3.1 | Shipping Module 1
1.7.3.1.1 | APA shipping plan
1.7.3.1.2 | APA shipping sequence
1.7.3.2 | Shipping Module 2
1.7.3.2.1 | APA shipping plan
1.7.3.2.2 | APA shipping sequence
1.8 | APA Installation at SURF
1.8.1 | Develop installation plan for APAs
1.8.2 | Develop safety procedures for installation
1.8.3 | Fabricate custom installation hardware
1.8.4 | Installation Module 1
1.8.4.1 | APA inspection at SURF
1.8.4.2 | Installation sequence for 150 APAs
1.8.4.3 | APAs survey after installation
1.8.5 | Installation Module 2
1.8.5.1 | APA inspection at SURF
1.8.5.2 | Installation sequence for 150 APAs
1.8.5.3 | APAs survey after installation
1.9 | TPC Calibration
1.9.1 | Development of Calibration requirements and techniques
1.9.2 | Calibration systems
1.9.2.1 | Specifications
1.9.2.2 | Design
1.9.3 | Calibration Module 1
1.9.3.1 | Fabrication
1.9.3.2 | Installation/Commissioning
1.9.4 | Calibration Module 2
1.9.4.1 | Fabrication
1.9.4.2 | Installation/Commissioning
1.9.5 | Calibration software/database