## Slide 1: FAST Update
Darren Crawford
0900 Scheduling Meeting
29 September 2017

## Slide 2: FAST Update
Division sign-offs occurred on Monday.
The ORC walk-through occurred Wednesday and final signatures occurred yesterday.
The drive laser system was brought online and 263 nm UV laser was established to the photocathode.
The RF Gun modulator has an undershoot circuit issue. EE Support personnel will investigate this morning.
We ran out of helium inventory during cooldown. A delivery arrived yesterday. We have liquid at 5 K in CC1, CC2 and CM2.
Yesterday, the refurbished Kinney skid developed an oil leak and was turned off. The repair estimate is 2 days. We need the skid to bring cavities to 2 K.

## Slide 3: FAST Update
Plans are to establish photoelectrons to the Faraday Cup later today. We need the Run Conditions and Beam Envelope documents.
Once all cavities are at 2 K cold conditioning begins.
50 MeV beam and 300 MeV beam commission will then follow.