## Slide 1
Cons Gattuso
09:00 Meeting
9/29/17

## Slide 2: Power Outage for Next Week (Oct 2nd )
Monday Oct 2nd
  MS1 Service building, including M01
Tuesday Oct 3rd
  MS2 Service building including M02
Wednesday Oct 4th
  MS3 Service building including M03 and M04
Thursday Oct. 5th
  AM: MP9, MS7 Service buildings, and PK120
  PM: MW9

## Slide 3: Week of Oct 2nd
Next Week
  Return back to operational key core set for the following
    Enclosure B
    F-Sector
    8 GeV
  Safety System Testing
    Switchyard
      C, D and E
      Enclosure B
      F-Man holes
      G2
      F-Sector
  Get Major LCW systems on to operational levels
    Booster/SY/MI ect.

## Slide 4: Week of Oct 9th
  Safety System Testing
    Linac/NTF
    Booster
    8 GeV Line
    BNB
      MI12A/B
Complete/Verify Enclosure cleaning
  Walkthroughs have been completed for the following (machine personnel)
    Linac, Booster, 8 GeV line, F-Sector, C D and E, Prevault/Pretarget, transport (all 3 section), MI-31 stub
  Needs to be cleaned
    MI/ Muon Rings/M4 extraction Line/NuMI enclosure
  Re-core to operational cores
    MI/NuMI

## Slide 5: Week of Oct 16th
Complete Cleaning of any remaining enclosure that need to be cleaned
Complete remaining System Testing
Out of all enclosure by 16:00 hrs Friday Oct 20th