## Slide 1
Marty Murphy
AD 09:00 Scheduling Meeting
29 September 2017
NuMI Shutdown Activities – Week 12

## Slide 2: Week-12 Jobs:
Week-12
  MI-65:
    Controls work on underdrain treatment skid in progress
    Multistack chiller is operational; waiting for insulator.
  Target hall
    Installed cooling coil in Target Pile fan system
    Replaced cracked Bellville washers on stripline hardware
    Cleaned enclosure, remove remaining rad. waste, etc.
    Drain cleaning complete.
  Pretarget Area:
    Drain cleaning complete.

## Slide 3: To-do List:
High pot strip-line; need help from EE-Support
Get PBTC & Hydrogen Peroxide systems operational – next week
Insulate pipe on multistack chiller system - Wednesday
PM multistack chiller – Prism
Continue construction of C0 storage facility
pH test of Decay Pipe under drains
Swap charging supply for Horn-1
Complete controls work on newly installed target pile air flow & temperature sensors.
Repair two sticky door handles in Pre-target & TH walkways.
Complete drain cleaning in DP & Absorber
Replace small HX in Absorber (4-hour job)