## Slide 1
Teri Dykhuis
PIP-II Director’s Review
10-12 October 2017
Environment, Safety, Health & Quality (ESH&Q) Strategy

## Slide 2: Outline
Vision/Commitment
Documentation
NEPA
Summary

## Slide 3: About me
Role on Project
  PIP-II Associate Project Manager/ESH&Q
  PIP-II NEPA Subproject Manager
Relevant Experience
  ESH Specialist/ESH&Q Section for 17 year
  Fermilab NEPA Program Manager; integrally involved in all NEPA related activities at Fermilab for the past 17 years
  ESH Professional for 31 years
  Environmental Engineer

## Slide 4: ESH&Q Vision/Commitment
Project team is committed to construct PIP-II in a safe, environmentally respectful, and cost efficient manner that meets our stakeholder’s needs
  Maintain a safe workplace for our workers, subcontractors, site occupants and guests
  Protect human health within our boundaries
  Achieve and maintain compliance with all applicable ESH&Q requirements

## Slide 5: ESH&Q Documentation
Documents that support the project’s current state of ESH&Q development and are necessary for CD-1 per DOE Order 413.3B: Program and Project Management for the Acquisition of Capital Assets
  Preliminary Security and Vulnerability Report (Docdb #143)
  Integrated ESH&Q Management Plan (Docdb #141)
  Preliminary Hazards Analysis Report (Docdb #140)
  Quality Assurance Program (Docdb #142)
Charge #4

## Slide 6: ESH&Q Documentation
  There are no unique security issues presented by the PIP-II Project; the activities planned are unclassified and no safeguards and security issues are forseen
  The PIP-II Project will comply with DOE and Fermilab Unclassified Foreign Visits and assignment program
  PIP-II will be executed as a construction project within the Fermilab, FRA, and DOE framework
  All PIP-II buildings will be located at Fermilab and will follow Facility Site Access requirements
Preliminary Security Vulnerability Assessment

## Slide 7: ESH&Q Documentation
  All work associated with the project will be conducted in a manner that ensures protection of the workers, the public, and the environment
  The Project will utilize an Integrated Safety Management System (ISMS) to integrate safety systematically into work activities
  Line managers, supported by the ESH&Q organization, will provide consistent guidance and enforcement of the ESH&Q program that governs the activities of workers at Fermilab and collaborator locations
  NEPA Compliance
  The Project Conventional Facilities will be constructed utilizing the federal Guiding Principles for High Performance and Sustainable Buildings
  Design reviews and safety assessments of facility systems and operations will be conducted during preliminary and final design to minimize waste generation and evaluate opportunities for pollution prevention
Integrated Environment, Safety and Health Management

## Slide 8: ESH&Q Documentation
  The PHA process was initiated by developing a Conceptual Design Baseline Hazards List:
  Construction
  Natural Phenomena
  Environmental
  Waste
  Fire
  Electricity
  Noise/Vibration/Thermal/Mechanical
  Cryogenic/Oxygen Deficiency
  Confined Space
  Ionizing Radiation Exposure, inside of the accelerator or beamline enclosure
  Chemical/Hazardous Material
  Accelerator/Beamline Hazards
  Ionizing Radiation Hazards, outside accelerator or beamline endlosure
  Lasers & other Non-ionizing Radiation Hazards
  Material Handling
Preliminary Hazard Analysis

## Slide 9: ESH&Q Documentation
  Construction Hazards
  Site Clearing
  Excavation
  Vertical/Horizontal Conveyance Systems
  Confined Space
  Heavy Equipment
  Work at Elevations (steel erection, roofing)
  Material Handling (rigging)
  Utility interfaces (electrical, chilled water, ICW, natural gas)
  Slips/trips/falls
  Weather related conditions
  Scaffolding
  Transition to Operations
  Radiation Generating Devices
Preliminary Hazard Analysis for Site-Wide Construction

## Slide 10: ESH&Q Documentation
  Hazard Initiator(s): Inadequate review/understanding of hazards, disregard of safety procedures, defective/inadequate equipment, weather impacts, and schedule pressures.
  Hazard Consequence: Personnel injury, fatality, equipment damage, schedule delays.
  Risk Assessment Prior to Mitigation = High
  Probability = Occasional
  Risk Category = High
  Risk Assessment Following Mitigation = High
  Probability = Remote
  Risk Category = Moderate
Preliminary Hazard Analysis for Site-Wide Construction

## Slide 11: ESH&Q Documentation
  MITIGATING FACTORS (Design):
  Engineered and approved excavation and tunneling system
  Engineered and approved fall protection system
  Incorporation of permanent fall protection systems into facility roof systems
  Use of modern code compliant equipment with required safety controls
  MITIGATING FACTORS (Operational):
  Strict adherence to OSHA Construction Standards
  OSHAS 18001 Hazard Control Requirements (flowed down to subs)
  Contractor Required Health and Safety Plan (flowed down to subs)
  Pre-qualification of contractors and subs based upon EMR, DART and TRC rates
  Independent third party inspections of construction safety program
  Dedicated on site construction safety professionals
  Phase hazards analysis for high risk activities (site clearing, elevated work, etc.)
  Pre-excavation search for utilities and other legacy systems
  Contractor safety incentive program
  Frequent communication with contractor and subs on ESH&Q (plan of day, tool box)
  Major construction equipment inspected prior to arriving on site
Preliminary Hazard Analysis for Site-Wide Construction

## Slide 12: ESH&Q Documentation
  Resources available for development of the PHAR included Fermilab staff, PIP-II L2 Managers and lessons learned from the DOE accelerator community
  The identified hazards were further developed in the PHAR by considering the proposed ESH&Q design enhancements as the design evolved
  The risks associated with the hazards were reanalyzed and in certain cases operational controls to develop a post-mitigation risk category were also included
Preliminary Hazard Analysis

## Slide 13: ESH&Q Documentation
  Focus of the PHAR is to qualitatively evaluate each hazard area by identifying the initiator hazard and its consequences, establishing a pre-mitigation risk category, recognizing design features to mitigate that risk and then establishing a post mitigation risk category
  The hazard evaluation process is a qualitative assessment of potential impacts in terms of hazards, initiators, likelihood estimates, preventive or mitigating features and public, environmental, and worker consequence estimates. The results of these evaluations confirm that the potential risks from operations and maintenance are acceptable
  The post-mitigation risk category conveys a realistic assessment of the residual risk posed by the PIP-II facility and became a critical input to the preliminary design effort
Preliminary Hazard Analysis

## Slide 14: ESH&Q Documentation
Preliminary Hazard Analysis
Pre- and post-mitigation risk category for each of the 15 hazard types found with PIP-II
PHA Hazard Identifier | Hazard | Pre-Mitigation Risk Category | Post Mitigation Risk Category
PIP-II PHA-1 | Construction | High | Moderate
PIP-II PHA-2 | Natural Phenomena | Low | Routine
PIP-II PHA-3 | Environmental | Moderate | Low
PIP-II PHA-4 | Waste | Moderate | Low
PIP-II PHA-5 | Fire | Moderate | Low
PIP-II PHA-6 | Electrical | High | Moderate
PIP-II PHA-7 | Noise, Vibration, Thermal, Mechanical | Moderate | Low
PIP-II PHA-8 | Cryogenic & Oxygen Deficiency | High | Moderate
PIP-II PHA-9 | Confined space | Moderate | Low
PIP-II PHA-10 | Ionizing Radiation exposure, inside accelerator enclosure | High | Moderate
PIP-II PHA-11 | Chemical | Moderate | Low
PIP-II PHA-12 | Accelerator/Beamline | Moderate | Low
PIP-II PHA-13 | Ionizing Radiation exposure, outside accelerator enclosure | High | Moderate
PIP-II PHA-14 | Non-Ionizing Radiation | Moderate | Low
PIP-II PHA-15 | Material Handling | High | Moderate
Table 6‑1: Risk Assessment Summary

## Slide 15: ESH&Q Documentation
  Conclusion
  Currently nine of the risk categories have been mitigated to “Low or below” and six remain at a “Moderate” level; the latter include construction, electrical, ionizing radiation inside/outside, cryogenics, and material handling.
  It is the PIP-II design objective to reduce hazards to no more than minor on-site and negligible off-site impacts to people and the environment during construction and operations
Preliminary Hazard Analysis

## Slide 16: ESH&Q Documentation
  The PIP-II Project Office is responsible for ensuring the quality of all items fabricated for PIP-II and must ensure that the project structure and organization are appropriate for effectively carrying out this mission
  In addition, Fermilab and Division Quality Assurance Policies and Procedures are followed for work being conducted within Fermilab Divisions for PIP-II
  PIP-II management at all levels shall regularly evaluate achievement relative to performance requirements and shall appropriately validate or update performance requirements and expectations to ensure quality
Quality Assurance Program (QAP)

## Slide 17: Requirements
DOE Order 413.3B: Program and Project Management for the Acquisition of Capital Assets
10 CFR Part 1021 DOE NEPA Implementing Procedures
Deliverables
CD-1
  Complete a National Environmental Policy Act (NEPA) Strategy by securing a determination (e.g., Environmental Assessment) from DOE/FSO, as required by DOE O 451.1B.
CD-2
  Issue the final Environmental Impact Statement or Environmental Assessment and Finding of No Significant Impact, as required by DOE O 451.1B.
NEPA Strategy

## Slide 18: Progress to date
NEPA Environmental Evaluation was completed and submitted to DOE FSO on 8/18/2017
A final NEPA determination supporting the completion of an Environmental Assessment was issued by DOE-FSO on 8/25/2017
Teri Dykhuis (PIP-II NEPA Project Manager) is coordinating the effort to ensure completion of the Environmental Evaluation (DOE Document = DOE/FSO-2072)
The PIP-II NEPA strategy is to conduct an Environmental Assessment that will cover all PIP-II activities
This approach is similar to the one used for LBNF, and NOvA
Charge #4
NEPA Strategy

## Slide 19: Work yet to be completed (for CD-2)
Procurement has released RFP to a DOE approved list of NEPA subcontractors utilizing a project provided SOW
NEPA subcontractor will be selected
Kick off meeting will be conducted
Subcontractor will develop a schedule to complete the EA
  EA determines whether there would be no significant impact and if an EIS is or is not required
  If no EIS, then a Finding of No Significent Impact (FONSI) will be developed by the DOE FSO and made available to the general public and Project Stakeholders
The NEPA process will be completed by CD-2 or before any construction work (estimated 6-8 months for EA completion)
Charge #4
NEPA Strategy

## Slide 20: Cost Summary
EA Cost Estimate
  $250 K
  Estimate based upon past project EAs
  Ultimate cost will depend upon subcontractor bids and effective process management
Charge #2
NEPA Strategy

## Slide 21: ESH&Q
NEPA EA
  EA not just about assessing impacts to the natural environment
  EA assesses all impacts to the ‘human environment’ which includes human health and built surroundings
NEPA EA Subcontractor will abide by all Fermilab ESH&Q Requirements at all times
Charge #4
NEPA Strategy

## Slide 22: Summary
Is the NEPA Strategy being properly addressed given the project’s current state of development?
  NEPA determination has been made - Environmental Assessment
  Experienced ES&H professionals assigned to the PIP-II Project and PIP-II NEPA subproject
  FNAL and PIP-II management are actively engaged
  The NEPA process will be completed by CD-2 or before any construction work (estimated 6-8 months for EA completion, from time of initiation)
NEPA Strategy

## Slide 23: ESH&Q Strategy
Are ESH&Q and ISM aspects being properly addressed given the project’s current state of development?
  All CD-1 documentation has been developed
  NEPA determination in place – EA
  Experienced ESH&Q professional assigned to the Project
  Hazard analyses and work planning are integral to the safety process
  PIP-II management is actively engaged
  ESH&Q is integrated to support design and construction
  FNAL has extensive construction safety experience
  Lessons Learned continue to be integrated into ongoing project planning
  CD-2 Documentation in process
  All work is similar to work performed at the Lab previously
Summary