## Slide 1
Thomas R. Powers
PIP-II Director’s Review
10-12 October 2017
Procurement

## Slide 2: Outline
Procurement Functions
Operations
Responsibilities
Cycle Times
Advanced Procurement Planning and Communications
Procurement Obligations
Summary

## Slide 3: About Me:
Procurement Manager – PIP-II
Relevant experience:
  FNAL Procurement Supervisor – Construction Group
  Procurement Manager – US HL-LHC AUP
  SBN Procurement Liaison
  Former LBNF Procurement Manger
  27 Years of Procurement Management

## Slide 4: Procurement Functions
Support the PIP-II Project by providing subcontracting services in a helpful, effective, and timely manner.
This includes a strong emphasis on advance acquisition planning for large, and complex procurement actions.
  Support Procurement Requirements from Initial Development to Closeout
  Adhere to a Best Value Philosophy

## Slide 5: Procurement Functions
Procurement Administrator Responsible
“From Cradle to Grave”:
  Planning
  Developing
  Negotiating
  Awarding
  Administration
  Close-Out

## Slide 6: Procurement Operations
Procedural Requirements based on:
  FRA Prime Contract
  Commercially Accepted Practices
  DOE Acquisition Regulations
  Federal Acquisition Regulations
  DOE Property Management Regulations

## Slide 7: Procurement Responsibilities
Staffing Resources
  Initial support to be augmented by existing Procurement Manager associated with the project team
    Supplemented by existing specialized procurement support, as required
      Lab and University
      Fabrication
      Construction
      Standard Commercial Items
  Future direct support of the PIP-II project team by the Procurement Manager will be on a part time (50%) basis

## Slide 8: Procurement Responsibilities
Procurement Staff Responsibilities
  Weekly and Ad-Hoc project team meetings
  Provide guidance and support to the PIP-II project team
  Communication with Fermilab Procurement Manager, and Acquisition Officer
  Reach out to other DOE Science Laboratories and facilities
  Review of major procurement project schedule on an ongoing basis
  Metrics on Procurement Performance

## Slide 9: Procurement Cycle Times

## Slide 10: Advanced Procurement Planning and Communications
Advanced Procurement Plans are required for acquisitions greater than $500K, and also for acquisitions greater than $100K that are on the critical path, have extended procurement periods, or unique requirements
Acquisition Plans are required for acquisitions greater than $10M
Procurement schedules include consideration for procurement methods and approval requirements
Close Communication with Project and Technical Staff
Communication with Procurement Counterparts from partner and other DOE Laboratories will take place as required

## Slide 11: Advanced Procurement Plans

## Slide 12: Fiscal Year Counts by Procurement Type
Procurement Classification | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | Total
Major |  | 1 | 4 | 1 | 1 |  |  |  | 7
Significant |  | 4 | 1 | 3 | 9 | 1 | 3 |  | 21
Critical | 15 | 10 | 3 | 7 | 9 | 2 | 1 |  | 47
Total | 15 | 15 | 8 | 11 | 19 | 3 | 4 | 0 | 75

## Slide 13: PIP-II Major Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
Conventional Facilities |  | 
CF – SitePrep – CoS: Site Prep Construction Subcontract - ConstrPh | 6/19 | 18,429,000
CF – CryoBldg – CoS: Cryo Plant Construction Subcontract - ConstrPh | 3/20 | 12,906,000
CF – UtilityBldg – CoS: Utility Plant Construction Subcontract - ConstrPh | 9/20 | 5,980,000
CF – HighBay – CoS: High Bay Bldg Construction Subcontract - ConstrPh | 4/20 | 12,939,000
CF – LTunnel – CoS: Linac Tunnel Construction Subcontract - ConstrPh | 10/20 | 8,918,000
CF – LGallery – CoS: Linac Gallery Construction Subcontract - ConstrPh | 8/21 | 13,549,000
CF – BTL – CoS: Beam Transfer Line Enclosure Subcontract - ConstrPh | 4/22 | 8,771,000

## Slide 14: PIP-II Significant Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
SSR1 |  | 
Linac - SSR1 - 2ndCM - BCAV - Cav - 9CavProdCONTR (FV) - ConstrPh | 5/19 | 618,710
Linac - SSR1 - 2ndCM - DCAV - 9CouplProdCONTR (FV) - ConstrPh | 6/19 | 592,448
SSR2 |  | 
Linac – SSR2 –1stCM – BCAV – Cav – 20NbProdCONTR (FV) – ConstrPh (for 4 Pre-Prod + 16 Prod Cavities) | 2/20 | 1,965,000
Linac – SSR2 – 2nd-7thCM – BCAV – Cav – 16CavProdCONTR (FV) – ConstrPh | 8/22 | 1,572,000
Linac – SSR2 – 2nd-7thCM – DCAV – 14CouplProdCONTR (FV) – ConstrPh | 4/22 | 825,300
Linac - SSR2 – 2nd-7thCM - DCAV – 16HeVProdCONTR - ConstrPh | 7/22 | 786,000
Linac - SSR2 - 2nd-7thCM - INT - CMComp - 6MagnShCONTR - ConstrPh | 1/24 | 589,500
Linac - SSR2 - 2nd-7thCM - INT - CMComp - 6VacuumVCONTR (FV) - ConstrPh | 1/24 | 884,250
HB650 |  | 
Linac - HB650 - 1stCM - DCAV - 8CouplProdCONTR (FV) – ConstrPh | 9/19 | 510,900
Linac - HB650 - 2nd-4thCM - BCAV - 10NbProdCONTR (FV) - ConstrPh | 1/19 | 736,875
Linac - HB650 - 2nd-4thCM - BCAV - Cav - 10CavProdCONTR (FV) - ConstrPh | 1/22 | 982,500
Linac - HB650 - 2nd-4thCM - DCAV - 8CouplProdCONTR (FV) - ConstrPh | 7/21 | 510,900
Linac - HB650 - 2nd-4thCM - DCAV - 18MagShCONTR - ConstrPh | 6/21 | 618,975

## Slide 15: PIP-II Significant Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
RF Power |  | 
Linac - RF - PIP-II/325MHz - 20kWRFDistCONTR - ConstrPh | 7/21 | 707,000
Linac - RF - PIP-II/650MHz - 33CircProdCONTR (FV) - ConstrPh | 7/22 | 583,605
Linac - RF - PIP-II/650MHz - 40kWRFDistCONTR - ConstrPh | 11/21 | 1,455,300
Linac - RF - PIP-II/650MHz - 21CircProdCONTR (FV) - ConstrPh | 7/23 | 589,500
Linac - RF - PIP-II/650MHz - 70kWRFDistnCONTR - ConstrPh | 3/22 | 1,099,200
Cryogenics |  | 
Linac – CRYO - PIP-IICDS: PIP-II CDS Contract (FV) - ConstrPh | 3/22 | 3,629,112
Linac - CRYO - PIP-IICryoP – InstCONTR (FV) - ConstrPh | 1/22 | 4,863,413
Conventional Facilities |  | 
CF – BoosterConn – CoS: Booster Connection Construction Subcontract - ConstrPh | 4/24 | 4,147,000

## Slide 16: PIP-II Critical Procurements >$100K
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
WFE |  | 
Linac - WFE – IS – ISrc2CONTR - ConstrPh | 1/21 | 201,331
Linac - WFE – MEBT – forPIP-II – 5BunchCavProdCONTR - ConstrPh | 1/21 | 400,000
SSR1 |  | 
Linac - SSR1 - 2ndCM - BCAV - Cav - 9NbProdCONTR (FV) - ConstrPh | 4/18 | 497,833
Linac - SSR1 - 2ndCM - DCAV – 9TunersProdCONTR (FV) - ConstrPh | 1/19 | 265,275
Linac - SSR1 - 2ndCM - DCAV - 9HeVProdCONTR - ConstrPh | 1/19 | 451,950
Linac - SSR1 - 2ndCM - STRING - FocElem - 4SolProdCONTR - ConstrPh | 9/19 | 178,422
Linac - SSR1 - 2ndCM - INT - CMComp - 1VVProdCONTR (FV) - ConstrPh | 5/20 | 147,375
SSR2 |  | 
Linac - SSR2 - 1stCM - BCAV - Cav – 2NbProtCONTR (FV) – R&DPh | 7/18 | 196,500
Linac - SSR2 - 1stCM - BCAV - Cav – 2CavProtCONTR (FV) – R&DPh | 7/19 | 196,500
Linac - SSR2 - 1stCM - BCAV - Cav – 4CavProdCONTR (FV) – ConstrPh | 3/21 | 393,000
Linac - SSR2 - 1stCM - DCAV – 2CouplProtCONTR (FV) – R&DPh | 10/17 | 117,900
Linac - SSR2 - 1stCM - DCAV – 6CouplProdCONTR (FV) – ConstrPh | 3/22 | 353,700
Linac - SSR2 - 1stCM - DCAV – 5TunersProdCONTR- ConstrPh | 3/22 | 176,850
Linac - SSR2 - 1stCM - DCAV – 4HeVProdCONTR – ConstrPh | 3/22 | 196,500
Linac - SSR2 - 1stCM - STRING - FocElem - 4SolenCONTR - ConstrPh | 7/22 | 142,560
Linac - SSR2 - 1stCM - INT - CMComp – 1VVCONTR (FV) –ConstrPh | 1/23 | 147,375
Linac - SSR2 – 2nd-7thCM - DCAV – 14TunersProdCONTR- ConstrPh | 3/22 | 412,650
Linac - SSR2 - 2nd-7thCM - COLDMASS - CMComp - 6ThShCONTR - ConstrPh | 1/24 | 206,325

## Slide 17: PIP-II Critical Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
RF Power |  | 
Linac - RF – PIP2IT – HWR/162.5MHz - 7of7kWSSAprodCONTR – R&DPh | 1/18 | 425,098
Linac - RF – PIP2IT - SSR1/325MHz - 9CircProdCONTR (FV) – R&DPh | 2/19 | 125,000
Linac - RF - TI - CMTS/650MHz - 6CircProdCONTR (FV) – R&DPh | 2/19 | 141,480
Linac - RF - PIP-II/325MHz - 7kWRFDistnCONTR - ConstrPh | 1/22 | 256,000
Linac - RF - PIP-II/325MHz - 30CircProdCONTR (FV) - ConstrPh | 1/22 | 294,750
Cryogenics |  | 
Linac – CRYO – PIP2ITCDS – CavTL – R&DPh | 3/22 | 384,157

## Slide 18: PIP-II Critical Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
RF Power |  | 
Linac - RF – PIP2IT – HWR/162.5MHz - 7of7kWSSAprodCONTR – R&DPh | 1/18 | 425,098
Linac - RF – PIP2IT – HWR/162.5MHz – 5CircProdCONTR (FV) – R&DPh | 1/18 | 36,050
Linac - RF – PIP2IT - SSR1/325MHz - 9CircProdCONTR (FV) – R&DPh | 2/19 | 125,000
Linac - RF - PIP2IT - SSR2/325MHz - 5CircProdCONTR (FV) - ConstrPh | 2/19 | 90,000
Linac - RF - TI - CMTS/650MHz - 6CircProdCONTR (FV) – R&DPh | 2/19 | 141,480
Linac - RF - PIP-II/162.5MHz – 7kWRFDistrCONTR – ConstrPh | 1/22 | 72,000
Linac - RF - PIP-II/325MHz - 8CircProdCONTR (FV) - ConstrPh | 1/22 | 78,600
Linac - RF - PIP-II/325MHz - 7kWRFDistnCONTR - ConstrPh | 1/22 | 256,000
Linac - RF - PIP-II/325MHz - 30CircProdCONTR (FV) - ConstrPh | 1/22 | 294,750
Cryogenics |  | 
Linac – CRYO – PIP2ITCDS – CavTL – R&DPh | 3/22 | 384,157

## Slide 19: PIP-II Foreign Procurements
Activity Name | Scheduled PO Issue Date | Budgeted Cost ($FY16)
SSR1 |  | 
Linac - SSR1 - 2ndCM - BCAV - Cav - 9CavProdCONTR (FV) - ConstrPh | 5/19 | 618,710
SSR2 |  | 
Linac – SSR2 – 1stCM – BCAV – Cav – 20NbProdCONTR (FV) – ConstrPh (for 4 Pre-Prod + 16 Prod Cavities) | 2/20 | 1,965,000
Linac – SSR2 – 2nd-7thCM – BCAV – Cav – 16CavProdCONTR (FV) – ConstrPh | 8/22 | 1,572,000
Linac – SSR2 – 2nd-7thCM – DCAV – 14CouplProdCONTR (FV) – ConstrPh | 4/22 | 825,300
Linac - SSR2 - 2nd-7thCM - INT - CMComp - 6VacuumVCONTR (FV) - ConstrPh | 1/24 | 884,250
HB650 |  | 
Linac - HB650 - 1stCM - DCAV - 8CouplProdCONTR (FV) – ConstrPh | 9/19 | 510,900
Linac - HB650 - 2nd-4thCM - BCAV - 10NbProdCONTR (FV) - ConstrPh | 1/19 | 736,875
Linac - HB650 - 2nd-4thCM - BCAV - Cav - 10CavProdCONTR (FV) - ConstrPh | 1/22 | 982,500
Linac - HB650 - 2nd-4thCM - DCAV - 8CouplProdCONTR (FV) - ConstrPh | 7/21 | 510,900
RF Power |  | 
Linac - RF - PIP-II/650MHz - 33CircProdCONTR (FV) - ConstrPh | 6/23 | 583,605
Linac - RF - PIP-II/650MHz - 21CircProdCONTR (FV) - ConstrPh | 5/24 | 589,500
Cryogenics |  | 
Linac – CRYO - PIP-IICDS: PIP-II CDS Contract (FV) - ConstrPh | 3/22 | 3,629,112
Linac - CRYO - PIP-IICryoP – InstCONTR (FV) - ConstrPh | 1/22 | 4,863,413

## Slide 20: Summary
Messages:
  Procurement policies and procedures are well established
  Procurement staff have experience in procurement of the supply, fabrication, and construction requirements of this project
  The procurement department is motivated, qualified, and ready to deliver
  We are ready for CD-1 and look forward to your feedback
  Thank you for your attention

## Slide 21: END