## IPR Recommendations
Review ID | Review Title | Review Category | Review Sub-category | Led By | Performed On | Start Date | End Date | Review Description | Project | Item ID | Item Title | Item Type | Date Found | Due Date | Open | Close Date | Found In | Risk Level | Hazard Severity | Mishap Probability | Item Description | Building | Causal Code Code | Causal Code Description | Causal Narrative | Unsafe Behavior or Condition | Management System | Preventive Action | Responsible Org | Responsible Party | Approval Date | Scheduled Date | Comments | AP/R ID | Action Plan / Response Title | AP/R Owner | AP/R Owner Org | AP/R Developer | AP/R Developer Org | AP/R Manager | AP/R Manager Org | Start Date | End Date | Scheduled Date | Close Date | Response / Action Plan Resolution | Status | Action Plan Description | Milestone Sequence # | Milestone | Scheduled Date | Close Date | Disposition
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96350 | 01 - Charge Element 1 - Neutrino beam studies | Recommendation | 2016-11-15 | 2017-06-01 | N | 2017-06-01 |  | Uncategorized | N/A | Does Not Apply | Ensure sufficient time and resources are available to obtain maximum benefit form the existing high power neutrino beam operations as it pertains to the PIP-II program. | [5 empty] | Project |  | Accelerator Division | Lebedev, Valeri | 2017-06-01 | 2017-06-01 |  | 77288 | Intensity growth for neutrino experiments | Lebedev, Valeri | Accelerator Division | Lebedev, Valeri | Accelerator Division | Lebedev, Valeri | Accelerator Division |  |  | 2017-06-01 | 2017-06-01 | 700 kW in the MI is achieved. Further increase of power is part of PIP-I+ and is going to proceed within next few years. It will address majority of problems required to be resolved in the PIP-II era. |  | 1. We are going to use the experience of running at 700KW beam power to identify any potential limitations to intensity in BOOSTER/RR/MI. 2. Basing on this experience we develop a plan to increase the beam intensity and power.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96352 | 02 - Charge Element 2 - Finalize the agreements with the partner institutes to fully define the division of responsibilities by CD-2. The Acquisition Strategy needed for CD-1 may require some of this information. | Recommendation | 2016-11-15 | 2018-05-01 | Y |  |  | Uncategorized | N/A | Does Not Apply | Finalize the agreements with the partner institutes to fully define the division of responsibilities by CD-2. The Acquisition Strategy needed for CD-1 may require some of this information. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen |  | 2018-05-01 |  | 77328 | Definition of In-kind contributions | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-03-31 |  |  |  | The Joint R&D Project Document (JPD) formalizes responsibilities among Fermilab and the Indian DAE laboratories for the R&D Phase. The PIP-II Resource Loaded Schedule will incorporate the scope and delivery dates included in the JPD. Deliverables for the construction phase will not be formalized prior to CD-1. The Assumptions Document prepared for CD-1 will document the current best projection of international in-kind contributions to the construction phase. The India/DAE has been advised of these assumptions. We have proposed to India/DAE and Italy/INFN that discussion of construction deliverables begin after the CD-1 Review, with a goal of formalizing at least 6 months in advance of CD-2. This recommendation cannot be fully addressed until after CD-1.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96353 | 03 - Cost & Schedule - The project needs to complete the CD-1 planning related to the schedule, risk and uncertainty analysis, cost, and identification of needed scope to validate the ability to meet the planned critical milestones and funding profile. | Recommendation | 2016-11-15 | 2017-11-14 | Y |  |  | Uncategorized | N/A | Does Not Apply | The project needs to complete the CD-1 planning related to the schedule, risk and uncertainty analysis, cost, and identification of needed scope to validate the ability to meet the planned critical milestones and funding profile. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul |  | 2017-11-14 |  | 77291 | ICR preparations | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-03-31 |  |  |  | Risk manager has been assigned, with planned schedule for filling in registry and coordinating with APM for Planning & Reporting on RLS. We will judge progress on March 31 and see if holding to schedule for 2017 IPR.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96353 | 03 - Cost & Schedule - The project needs to complete the CD-1 planning related to the schedule, risk and uncertainty analysis, cost, and identification of needed scope to validate the ability to meet the planned critical milestones and funding profile. | Recommendation | 2016-11-15 | 2017-11-14 | Y |  |  | Uncategorized | N/A | Does Not Apply | The project needs to complete the CD-1 planning related to the schedule, risk and uncertainty analysis, cost, and identification of needed scope to validate the ability to meet the planned critical milestones and funding profile. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul |  | 2017-11-14 |  | 78227 | Revised schedule for the CD-1 reviews | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-11-14 |  |  |  | With uncertainty in funding profile, revised schedule for CD-1 reviews
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96354 | 04 - Cost & Schedule - Prior to the CD-1 ICR, ensure that the Alternatives Analysis addresses the GAO best practices guide for Alternatives Analysis or provide justifications for deviations. | Recommendation | 2016-11-15 | 2017-05-26 | N | 2016-12-17 |  | Uncategorized | N/A | Does Not Apply | Prior to the CD-1 ICR, ensure that the Alternatives Analysis addresses the GAO best practices guide for Alternatives Analysis or provide justifications for deviations. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul | 2016-12-17 | 2017-05-26 |  | 77289 | Formulation of response to GAO best practices | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-01-03 | 2016-12-17 | Responses complete 17 Dec 2016 |  | DOE Program Manager will compile responses to the GAO best practices guide.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96355 | 05 - Cost & Schedule - In the next three months, evaluate the remaining work and resource needs to ensure a successful CD-1 and ICR can be accomplished within the project¿s proposed dates. | Recommendation | 2016-11-15 | 2017-05-26 | N | 2017-05-15 |  | Uncategorized | N/A | Does Not Apply | In the next three months, evaluate the remaining work and resource needs to ensure a successful CD-1 and ICR can be accomplished within the project¿s proposed dates. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul | 2017-05-15 | 2017-05-26 |  | 77290 | Strategy to CD-1 | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-03-31 | 2017-05-15 | Working with OPSS, the Directorate, and OHEP, we have adjusted the schedule to match needs and resources. |  | Assigned necessary work. Will judge progress by the end of March to see if need to adjust schedule
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96356 | 06 - Cost & Schedule - Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | Recommendation | 2016-11-15 | 2017-09-15 | Y |  |  | Uncategorized | N/A | Does Not Apply | Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul |  | 2017-09-15 |  | 77292 | Documentation schedule complete | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-06-30 |  |  |  | Made assignments for writing and developed a plan for completing necessary documentation in advance of reviews.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96356 | 06 - Cost & Schedule - Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | Recommendation | 2016-11-15 | 2017-09-15 | Y |  |  | Uncategorized | N/A | Does Not Apply | Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul |  | 2017-09-15 |  | 78348 | Postponed until September | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-09-15 |  |  |  | On course for completion, other priorities took precedence
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96356 | 06 - Cost & Schedule - Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | Recommendation | 2016-11-15 | 2017-09-15 | Y |  |  | Uncategorized | N/A | Does Not Apply | Complete all documentation required for the ICR and CD-1 review, such as the Acquisition Strategy, PPEP, and RMP. | [5 empty] | Project |  | Accelerator Division | Derwent, Paul |  | 2017-09-15 |  | 78650 | Close | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division | Derwent, Paul | Accelerator Division |  |  | 2017-09-12 | 2017-09-12 | On track and will be complete for the Director's Review in October
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96357 | 07 - Mgmt & ES&H - As soon as possible establish a risk management tool to strengthen the risk management process to ensure that risks are reported consistently (cost slip, in-kinds to be included). Use the tool! | Recommendation | 2016-11-15 | 2017-06-01 | N | 2017-05-31 |  | Uncategorized | N/A | Does Not Apply | As soon as possible establish a risk management tool to strengthen the risk management process to ensure that risks are reported consistently (cost slip, in-kinds to be included). Use the tool! | [5 empty] | Project |  | Accelerator Division | Mishra, C. Shekhar | 2017-05-31 | 2017-06-01 |  | 78220 | Risk Register and Workshop | Mishra, C. Shekhar | Accelerator Division | Mishra, C. Shekhar | Accelerator Division | Mishra, C. Shekhar | Accelerator Division |  |  | 2017-06-01 | 2017-05-31 | Prepared Risk Management Plan, Finalized Risk Register after Risk Workshop with Subject Matter Experts |  | Prepared Risk management plan and carryout the plan.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96358 | 08 - Mgmt & ES&H - Actively address issues that arise in the international collaborations. | Recommendation | 2016-11-15 | 2017-05-26 | N | 2017-08-02 |  | Uncategorized | N/A | Does Not Apply | Actively address issues that arise in the international collaborations. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen | 2017-08-02 | 2017-05-26 |  | 77329 | International Collaboration Issues | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-04-30 | 2017-08-02 | The semi-annual IIFC meeting was held at BARC in January 2017. The fall meeting is planned in conjunction with the DOE IPR. The PIP-II Project Manager holds a weekly teleconference with his counterparts at RRCAT and BARC. This meeting actively tracks all current issues and results in action items as needed. The weekly SPM/SPC teleconferences have been rescheduled to make more convenient of Indian participants. They currently take place at 06:30 (CDT)/ 17:00 (IST). This will persist until the clock change in November. |  | We will continue to pay close attention to the collaboration with India/DAE and Italy/INFN. This includes regularly scheduled teleconferences and information exchanges at both the management and engineering level. These activities will continue indefinitely. We will hold a IIFC meeting at BARC in January 2017. Once all action items from that meeting are addressed we will regard this item as closed.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96359 | 09 - Mgmt & ES&H - Use the risk registry to re-evaluate the Project and R&D program such that the Project reaches major milestones (CD milestones) as fast as possible. | Recommendation | 2016-11-15 | 2017-06-02 | Y |  |  | Uncategorized | N/A | Does Not Apply | Use the risk registry to re-evaluate the Project and R&D program such that the Project reaches major milestones (CD milestones) as fast as possible. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen |  | 2017-06-02 |  | 77330 | CD Schedule Optimization | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-06-01 |  |  |  | This evaluation will be integrated into development and finalization of the RLS, risk registry, and contingency analysis in advance of the Director's Review scheduled for this summer.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96360 | 10 - Mgmt & ES&H - Agree with the program the appropriate level of risk assumed at each CD step. Present a plan for this at the next review. | Recommendation | 2016-11-15 | 2017-10-12 | Y |  |  | Uncategorized | N/A | Does Not Apply | Agree with the program the appropriate level of risk assumed at each CD step. Present a plan for this at the next review. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen |  | 2017-10-12 |  | 78656 | Risk Planning | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-10-12 |  |  |  | Review the risk register with DOE and incorporate into risk presentation at the review
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96360 | 10 - Mgmt & ES&H - Agree with the program the appropriate level of risk assumed at each CD step. Present a plan for this at the next review. | Recommendation | 2016-11-15 | 2017-10-12 | Y |  |  | Uncategorized | N/A | Does Not Apply | Agree with the program the appropriate level of risk assumed at each CD step. Present a plan for this at the next review. | [5 empty] | Project |  | Accelerator Division | Mishra, C. Shekhar |  | 2017-10-12
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96361 | 11 - Mgmt & ES&H - Develop a key assumptions document prior to CD-1. | Recommendation | 2016-11-15 | 2017-02-28 | N | 2017-03-17 |  | Uncategorized | N/A | Does Not Apply | Develop a key assumptions document prior to CD-1. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen | 2017-03-17 | 2017-02-28 |  | 77622 | Assumptions Document | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-02-28 | 2017-03-17 | The Assumptions Document was approved by the Fermilab Directorate on March 16. The Assumptions Document is located in the PIP-II document database, Document #144. |  | Develop the PIP-II Assumptions Document and secure Directorate approval
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96362 | 12 - Mgmt & ES&H - Develop a MOU with Fermilab Leadership that outlines the projects needs prior to CD-1. | Recommendation | 2016-11-15 | 2017-05-26 | Y |  |  | Uncategorized | N/A | Does Not Apply | Develop a MOU with Fermilab Leadership that outlines the projects needs prior to CD-1. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen |  | 2017-05-26 |  | 77623 | Lab MOU | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-05-26 |  |  |  | The MOU will be based on the Assumptions Document. Work will commence following approval of the Assumptions Document.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96363 | 13 - Mgmt & ES&H - Contingency development should be informed and verified by BOE and risk analysis at CD-1. | Recommendation | 2016-11-15 | 2017-06-01 | Y |  |  | Uncategorized | N/A | Does Not Apply | Contingency development should be informed and verified by BOE and risk analysis at CD-1. | [5 empty] | Project |  | Accelerator Division | Lari, Luisella |  | 2017-06-01
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96364 | 14 - Mgmt & ES&H - Revise the IIFC joint R&D document prior to January 31, 2017. | Recommendation | 2016-11-15 | 2017-05-26 | Y |  |  | Uncategorized | N/A | Does Not Apply | Revise the IIFC joint R&D document prior to January 31, 2017. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen |  | 2017-05-26 |  | 77308 | Finalize Addenda I & II | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-02-28 |  |  |  | The IIFC meeting in January 2017 will review proposed changes in deliverables dates and responsibilities as codified in Addenda I and II. We have established February 15, 2017 as the target date for finalization and approval.
46466 | DOE Independent Project Review of PIP II | Project Activities | DOE Project Review | DEPARTMENT OF ENERGY |  | 2016-11-15 | 2016-11-16 |  | PIP II | 96365 | 15 - Mgmt & ES&H - Consider leading the export licensing and IP-right issues and make it a standard part of your in-kind collaboration strategy to ensure uniformity during execution of contracts. Establish overall coordination support (regulatory issues | Recommendation | 2016-11-15 | 2017-10-02 | N | 2017-09-13 |  | Uncategorized | N/A | Does Not Apply | Consider leading the export licensing and IP-right issues and make it a standard part of your in-kind collaboration strategy to ensure uniformity during execution of contracts. Establish overall coordination support (regulatory issues, logistics) for in-kind contracts by the project. | [5 empty] | Project |  | Accelerator Division | Holmes, Stephen | 2017-09-13 | 2017-10-02 |  | 78657 | Export Licensing | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division | Holmes, Stephen | Accelerator Division |  |  | 2017-10-02 | 2017-09-13 | We have identified a distributor who will apply for an export license for the MOSFET required for BARC fabrication of the 325 MHz RF amplifiers required during the R&D phase. We procured an export license to allow adding BARC to the Fermilab VxWorks license. (This was not exercised when BARC decided not to procure VxWorks.) We initiated discussion with the international office within DOE/SC on approaches to Dept of Commerce for the purpose of providing special treatment for export licensing to BARC as part of PIP-II. This is in process. |  | The primary export issues concern BARC, who appear on the Dept of Commerce Entities List. During the R&D phase we will handle export issues on a case-by-case basis. For the longer term we will discuss with DOE/SC the possibility of securing some sort of special treatment for export licensing for components going to BARC as part of the PIP-II collaboration.