## PIP-II R&D Risks
RI-ID | Title | Probability | Probability Score | P * Impact (k$) | P * Impact (months) | Start Date | Expiration Date
RT-121-03-12-001 | Resonance control and field regulation | 40% | 4 (H) | 700 | 6 | 4346600% | 4565800%
RT-121-03-09-011 | Pulsed and CW cryomodule operating modes cause cryogenic or mechanical instabilities | 50% | 4 (H) | 688 | 3.335 | 4264400% | 4483500%
RT-121-03-07-002 | SSR1 CM (1) Performance at PIP2IT does not meet technical requirements | 40% | 4 (H) | 433 | 2.8 | 4340500% | 4355600%
RT-121-03-12-004 | IIFC LLRF hardware/software does not meet acceptance criteria | 50% | 4 (H) | 400 | 3.75 | 4328200% | 4410500%
RT-121-03-10-002 | HB650 CM (1) Performance at CMTF does not meet technical requirements | 40% | 4 (H) | 333 | 2.8 | 4434800% | 4453000%
RT-121-01-02-001 | Delay in access to SRF testing and fabrication infrastructure | 50% | 4 (H) | 317 | 3.835 | 4264400% | 4373900%
RT-121-03-04-002 | Unable to maintain proper vacuum between MEBT absorber and SRF | 50% | 4 (H) | 217 | 3.25 | 4373900% | 4392200%
RT-121-03-04-004 | MEBT scrapers unable to absorb amount of beam loss | 50% | 4 (H) | 150 | 4.5 | 4294800% | 4392200%
RT-121-03-11-002 | SRF Pre-Production Input Coupler Failure | 50% | 4 (H) | 140 | 3.125 | 4255700% | 4520500%
RT-121-03-11-005 | Minor Modifications Required for IIFC RF Power Amps | 50% | 4 (H) | 63 | 4 | 4337300% | 4593000%
RT-121-03-11-001 | 162.5 MHz, 7 kW RF amplifier procurement delayed | 60% | 4 (H) | 45 | 3.6 | 4279400% | 4300800%
RT-121-03-11-010 | Failure of High Power Circulator | 50% | 4 (H) | 15 | 3 | 4373800% | 4593000%
RT-121-03-11-011 | Failure of 650 MHz IOT Amplifiers | 50% | 4 (H) | 6 | 3.5 | 4288700% | 4352400%
RT-121-03-18-003 | Integration of instrumentation into MPS | 50% | 4 (H) | 0 | 3 | 4264400% | 4410500%
RT-121-03-04-001 | MEBT kickers performance is unsatisfactory | 50% | 4 (H) | 500 | 3 | 4276000% | 4373800%
RT-121-03-02-001 | Re-design ion source vacuum chamber | 50% | 4 (H) | 8 | 2 | 4410500% | 4556600%
RT-121-03-02-003 | Ion source performance does not allow efficient transmission through HWR | 25% | 3 (M) | 44 | 4.5 | 4278200% | 4392200%
RT-121-02-03-002 | Insufficient IIFC Documentation | 25% | 3 (M) | 15 | 0.4175 | 4337300% | 4629500%
RT-121-03-06-001 | HWR Cryomodule does not meet technical performance requirements | 20% | 2 (L) | 217 | 2.4 | 4310100% | 4349600%
RT-121-03-04-003 | MEBT Absorber does not meet performance requirement | 20% | 2 (L) | 90 | 2.4 | 4373900% | 4392200%
RT-121-03-01-001 | PIP2IT does not meet overall requirement at CD-3 | 10% | 2 (L) | 55 | 1.2 | 4264400% | 4410500%
RT-121-03-10-001 | HB650 Cryomodule assembly and integration | 10% | 2 (L) | 50 | 0.6 | 4337400% | 4410500%
RT-121-02-05-005 | Significant hydrofluoric acid spill or personnel exposure during SRF cavity processing | 10% | 2 (L) | 28 | 0.633 | 4281400% | 4546300%
RT-121-01-02-002 | Failure of SRF cavity processing equipment | 10% | 2 (L) | 20 | 0.383 | 4283000% | 4593000%
RT-121-03-02-002 | LEBT bending magnet deteriorates the beam emittance | 20% | 2 (L) | 3 | 2.4 | 4280000% | 4392200%
RT-121-03-12-003 | RF interlocks fail to protect SSA-Coupler-Cavity | 10% | 2 (L) | 23 | 0.35 | 4246100% | 4465200%
RT-121-03-15-002 | Design/construction of a QPM system for superconducting solenoid and correction elements | 20% | 2 (L) | 6 | 0.6 | 4278600% | 4337200%
RT-121-03-15-001 | Cold magnet power supply procurement delay | 20% | 2 (L) | 1 | 0.2 | 4301000% | 4556600%
RT-121-03-03-001 | RFQ resonant frequency does not meet specifications | 5% | 1 (VL) | 1 | 0 | 4278200% | 4410500%