## Slide 1
Steve Holmes
PIP-II Director’s Review
10-12 October 2017
International Collaboration
Project Management Breakout Session

## Slide 2: Outline
Context
Goals
IIFC Organization
Strategy
Challenges
Summary

## Slide 3: Context/India
India Institutions and Fermilab Collaboration (IIFC) formed in 2009 to pursue R&D on technologies for high intensity superconducting proton accelerators:
  BARC
  IUAC
  RRCAT
  VECC
Governed by US-India agreements:
  DAE authorized to commit up to $200M
  (in-kind) for R&D + construction deliverables
R&D phase
  Deliverables described in the “Joint Project Document for the R&D Phase of the IIFC under the Framework of Project Annex-I to the Implementing Agreement between DAE and DOE”
Construction phase deliverables to be formalized in advance of CD-2
U.S.-India S&T Agreement
Implementing Agreement
Annex I
Joint Project Documents

## Slide 4: Context/Europe
Italy/INFN
  INFN/Milano will fabricate two LB650 dressed cavities prototypes
  Integrated with Fermilab and VECC to come to common design
  Formalizing INFN LB650 cavities construction phase contribution
UK/STFC
  Recently announced $88M (£65M, core accounting) contribution to LBNF/DUNE
  Developing a plan for devoting a portion to PIP-II construction phase, with focus on HB650 cavities & cryomodules
CEA/Saclay
  Discussion on assembling LB650 cryomodules based on cavities from INFN and/or VECC

## Slide 5: Context
PIP-II Cost Estimate is based on the following assumptions with respect to international deliverables:
 | Component Fraction Provided | 
Component | India/DAE | Other Int’l
Dressed Cavities |  | 
SSR2 | 50% | 
LB650 | 50% | 50%
HB650 | 50% | 
Cryomodules |  | 
LB650 |  | 100%
Linac Warm Magnets | 100% | 
RF Amplifiers |  | 
325 MHz | 100% | 
650 MHz | 100% | 
Controls Hardware | 50% | 
LLRF, RFPI Hardware | 100% | 
Instrumentation | 50% | 
Cryoplant | 100% | 
From Assumptions Document: PIP-II-doc-144

## Slide 6: Goals
R&D Phase
  Develop capabilities, infrastructure, and working relationships at Fermilab and international partner labs and allied vendors to support construction of the PIP-II linac
  Develop capabilities and infrastructure in DAE labs and allied vendors to support successful construction of high intensity proton accelerators in India
Construction Phase
  Construct and commission PIP-II with a significant India/DAE in-kind contribution, and significant engagement of DAE staff
  Construct and commission PIP-II with a significant European in-kind contribution, and significant engagement of European staff
Challenges
  Success requires consistent attention and guidance from management
  Constructive interaction at the technical level is essential in making this work

## Slide 7: IIFC Organization
Scope and deliverables schedule for R&D phase are governed by the Joint R&D document
  Signed by S. Basu and J. Siegrist
High level management via two Principal Coordinators, supported by two Technical Coordinators
  TC weekly teleconference
Technical integration of work via Fermilab SPMs and Indian SPCs
  SPM/SPC bi-weekly teleconferences
Semi-annual meetings initiated
  January/July 2016/January 2017 (all at BARC)

## Slide 8: SPC/SPM Assignments
Within Fermilab SPMs are typically level 3 managers within PIP-II Project

## Slide 9: Mapping onto PIP-II/Strategy
Assignments based on consideration of:
  DAE, INFN, STFC technology interests
  PIP-II risk mitigation strategies
R&D phase scope of work reflects vision of construction phase deliverables
  Development and testing of prototypes
  Development of infrastructure
  Engineering documentation
DAE interests
  Primary interest is acquiring capabilities, intellectual and physical, to construct high power proton accelerators domestically
  Result: DAE is engaged in all critical systems
INFN, STFC, and CEA interests
  Contributing to early realization of full capabilities of PIP-II to support MW+ neutrino program
  Building/enhancing domestic capabilities in SRF technologies

## Slide 10: Mapping onto PIP-II
The DAE laboratories are completely integrated into nearly all aspects of the PIP-II superconducting linac
INFN and STFC are more limited
IIFC areas of collaborative development include:
  Superconducting radio frequency accelerating modules
  Radio frequency power sources and RF controls
  Super- and normal-conducting magnets
  Cryogenic Plant
  Beam diagnostics
  Controls
IIFC
STFC
INFN
Notes: Offset IIFC arrows

## Slide 11: Major IIFC Deliverables
  * Scope to be formalized in advance of CD-2
System/Component | DAE R&D Deliverable | Construction Deliverable*
SSR1 | 2 dressed cavities | NA
SSR2 | 2 dressed cavities | 
LB650 | 2 dressed cavities | 
HB650 | 4 dressed cavities | 
SC solenoids | 4 magnets (SSR2) | 
Warm magnets | All PIP2IT/MEBT magnets 2 focusing magnets (650) | 
RF Power Sources/325 | 9 sources (SSR1) | 
RF Power Sources/650 | 7 sources (HB650) | 
LLRF/RFPI | 4 systems (SSR1,2xHTS-2, CMTF) | 
HTS-2 | 2 test stands (FNAL & RRCAT) | 
LHe Cryoplant |  | 

## Slide 12: Integration in R&D Program
DAE is strongly integrated into the R&D phase
  SSR1 cryomodule to be constructed of 6-7 (Fermilab) + 1-2 (IUAC/BARC) cavities
  HB650 cavity to be constructed of 4 (Fermilab) + 2 (RRCAT) cavities
  325 MHz 7 kW SSRF amplifiers from BARC are required to power the SSR1 CM at PIP2IT
    RFPI boards from BARC will be used in this system
  650 MHz 40 kW SSRF amplifiers from RRCAT are required to power the HB650 CM at CMTS
  RFPI boards from BARC will be us
INFN
  Have completed LB650 cavity electromagnetic design
    In close coordination with VECC and Fermilab
  Approved by Fermilab and proceeding to mechanical design

## Slide 13: Construction Phase
DAE is authorized to provide deliverables worth up to $200M (in-kind) for PIP-II
  R&D + Construction phases
  Cryogenic Plant procurement by BARC is currently underway
    Bidding two plants, with intention of one coming to Fermilab
    Capable of supporting CW operations
  Balance of construction deliverables is not yet formalized, but we believe it will conform closely to the table on slide 11
A draft agreement covering both R&D and construction phase deliverables from INFN is currently providing basis for discussion
  LB650 dressed cavities
Discussions just initiated with STFC on scope of construction phase deliverables
  HB650 cavities
Discussions with CEA on possible construction phase deliverable have taken place among the technical managers
  LB650 cryomodule assembly
Agreements need to be completed and formalized in advance of CD-2

## Slide 14: Progress to Date
DAE has delivered:
  Complete set of focusing quadrupoles and correction dipoles required for the PIP2IT MEBT
  Two SSR1 bare cavities
  3 kW SSRF amplifier
  RFPI board
DAE in process:
  Prototype 5-cell HB650 cavity
  325 MHz 7 kW SSRF amplifiers
  650 MHz 40 kW SSRF amplifiers
  SSR2 cavity design
  LB650 5-cell cavity design and fabrication
  LB650 cryomodule design
INFN in process:
  LB650 cavity design and fabrication

## Slide 15: Risks
Two entries in the risk register related to international contributions are categorized as Enterprise Risk, i.e. belong to DOE/HEP & Fermilab; not included in risk analysis:
  RT-121-01-01-001: Failure to reach agreement on international in-kind contributions
  RT-121-01-01-002: Delay in formalizing international in-kind contributions
International risks belonging to the project:
  RT-121-02-01-002: In-kind contributions do not meet codes, standards and/or acceptance criteria
  RT-121-02-03-002: Insufficient IIFC documentation
  RT-121-02-01-005: Effect of US Funding delay of "In-Kind" design effort
  RT-121-03-11-005: Minor modifications required for IIFC RF power amplifiers
  RT-121-03-12-004: IIFC LLRF hardware/software does not meet acceptance criteria

## Slide 16: Challenges
PIP-II, as far as I am aware, is the first attempt by DOE to construct a domestic accelerator incorporating international in-kind contributions
  Creates a set of generic challenges in how to organize and manage
  India also creates a number of specific challenges…
Conducting a collaboration between institutions separated by 11 time zones and 8000 miles
  Communications/information flow
  Visits/visas
Export regulations and Third-part IP
  India is classified as a “sensitive country” with BARC subject to special scrutiny by the Department of Commerce
Differences in engineering and management cultures also need to be recognized
  Many discussions on what “design” means
  Control of documentation
  (Fermilab processes codified in Fermilab Engineering Manual)

## Slide 17: Moving Forward (1)
Most important: Establish and maintain confidence among the partners
Several things have been particularly successful (my opinion)
  FRS/TRS
    Establish basic requirements, including interfaces to other systems
    Generally involve significant discussion and iteration
    Signed off by both Fermilab and DAE lab
  Guest engineers/scientists
    See following slides
  Weekly teleconferences
    SPM/SPC
      Integration of INFN into the LB650 teleconference
    TC/TC

## Slide 18: Visitor Program

## Slide 19: Visitor Program
We have hosted six DAE engineers/scientist over the last two years
Our goal for these visits is to provide an experience that is both professionally and personally fulfilling
Assignments
  PIP2IT
  SRF
  LLRF (2)
  Cryogenics (2)
Provide direct support to efforts at Fermilab
Provide interface to home laboratories
Upon return they will be in unique position to facilitate interactions between Fermilab and DAE labs, as well as to carry home knowledge & experience
In process of identifying second cohort, to arrive early 2018

## Slide 20: Moving Forward (2)
Areas requiring management attention:
Management of shared engineering documentation
Cryoplant
  Procurement initiated by DAE – (very) long lead item
Export licensing
  Involves multiple agency interactions: Dept of Commerce, DOE, (State)
Intellectual Property
  Especially third-party
SPC/SPM interactions
  This is the foundation of everything we do together
Formalization of construction phase deliverables in advance of CD-2

## Slide 21: Summary
International engagement on multiple fronts
  IIFC has been going for eight years
  INFN has joined in the last year and STFC has announced intention
R&D deliverables are starting to arrive at Fermilab
  MEBT magnets, SSR1 cavities, RFPI boards
Design efforts underway on multiple fronts
Based on jointly approved FRS and TRS
DAE staff at Fermilab for extended visits have had significant positive impact
Challenges remain, but all sides are committed to making this work

## Slide 22: END