## Slide 1
Alex Chen
PIP-II Director’s Review
10-12 October 2017
121.3.12 Warm Units for LB650 and HB650
Breakout Session: Linac Accelerator Support Systems, Installation and Commissioning

## Slide 2: Outline
Requirements
Conceptual Design, Maturity
Scope/Deliverables
Interfaces
Technical Progress to Date
ESH&Q
Risk
Cost
Schedule
Summary

## Slide 3: About Me:
Roles on PIP2
  L3 Manager for Vacuum Systems
  L3 Manager for 650 Warm Units
  Vacuum lead for PIP2IT
Other Fermilab Experience:
  20 Years of mechanical design and vacuum support on Booster, Tevatron etc.
  2 years L4 managers for both Vacuum and Magnet Installation of LBNF Primary Beamline
  2 years Mechanical Lead for HINS
  AD/MSD vacuum group leader

## Slide 4: WBS L3 System Requirements
Warm Unit is the warm insertion in between CMs; it is composed of magnets for focusing and correction, BPM or other beam instrumentation, and beamtube with vacuum pump and gauges.
Magnets
  a quadrupole doublet, and X, Y steering correctors
  Minimum Beam Aperture: 44mm
  individually fiducilized
  magnetic axes of both quadrupoles in a doublet are aligned within ±0.1 mm and ±0.5 mrad
  dipole corrector is aligned within ±0.5 mm and ±3 mrad
BPM
  a two-coordinate 4-button BPM
  Limited space: 95mm Dia. 70mm Long
Charge #1

## Slide 5: WBS L3 System Requirements
Vacuum
  2” beam tube
  Low particulate Vacuum with <1x10-9 Torr residual gas
  Maximize pumping port sizes within the limit of space
  Provide adequate conductance for pumping CM
  Cold Cathode gauge to avoid hot filament
  Bakeble to 150C
FRS: ED0004853
Charge #1

## Slide 6: Conceptual Design
Charge #1
Interface between LB650 and HB650 sections:

## Slide 7: Conceptual Design
Magnet conceptual Design by Vikas Teotia, BARC
Charge #1
600
400
35
500
350
180
400
Quadrupole
Dipole Corrector
Quadrupole
Magnetic field profile in the beam aperture
3-D Model and Magnetic field
Distribution in the yoke

## Slide 8: Conceptual Design
Centroid trajectory corrections by Dipole Correctors
Charge #1
Arun Saini

## Slide 9: Conceptual Design
Magnet doublet conceptual design
  The upper components of the quadrupoles and dipole corrector are dismountable without breaking vacuum for vacuum chamber assembly, leak check, BPM repairs, possible 120oC bake, and for assembling / disassembling of neighboring components Drawings/3D models (layouts, exploded views, sections) annotated with WBS numbers
  The mounting system provides a rigid alignment of the magnets and allows an adjustment of their transverse positions with a resolution of 0.05 mm and the total travel range of ±2 mm.
  Engineering analyses were done
    TRS: ED0003401
    FRS: ED0003403
    RA: ED0005885
Charge #1

## Slide 10: Conceptual Design
Charge #1
Vacuum
  Conceptual Design established
  Key components estimated
BPM design is the scope of Beam Instrumentation

## Slide 11: Scope and Deliverables
11 warm units for LB650, and 9 for HB650
Assumed India Deliverables
    Magnet Doublets with magnetic mapping wrt fiducials
    The details concerning deliverables and schedule will be finalized by CD-2.”
Entire warm unit will be assembled on a single supporting girder.
The individual warm unit will be vacuum certified before tunnel installation
Charge #1

## Slide 12: Interfaces
  650 Warm Unit will interface with:
    Beam Instrumentation: BPM imbedded in between magnet, and integrated with beam tube
    CM: end flanges of beam tube connect to gate valves at the end of CMs
    Vacuum design is integrated into VACUUM SYSTEMS
    Installation: tunnel installation and commissioning
    Accelerator lattice: Insertion length, beam aperture, and magnetic parameters
    Magnet Power Supply: electrical connection
    infrastructure, use of cleaning facility, cleanroom, slow pumping cart
    Control: PLC and ACNET
  Planned interface control documents for all above
Charge #1

## Slide 13: Interface Matrix (Warm Unit)
 | Warm Front End WBS 121.3.3 | HWR WBS 121.3.4 | SSR1 WBS 121.3.5 | SSR2 WBS 121.3.6 | LB650 WBS 121.3.7 | HB650 WBS 121.3.8 | RF Power WBS 121.3.9 | RF Integration WBS 121.3.10 | Cryo Systems WBS 121.3.11 | Warm Units WBS 121.3.12
Warm Front End WBS 121.3.3 |  |  |  |  |  |  |  |  |  | 
HWR WBS 121.3.4 | ED0002529 |  |  |  |  |  |  |  |  | 
SSR1 WBS 121.3.5 |  |  |  |  |  |  |  |  |  | 
SSR2 WBS 121.3.6 |  |  |  |  |  |  |  |  |  | 
LB650 WBS 121.3.7 |  |  |  |  |  |  |  |  |  | 
HB650 WBS 121.3.8 |  |  |  |  |  |  |  |  |  | 
RF Power WBS 121.3.9 | Y | ED0002529 | ED0004129 |  |  |  |  |  |  | 
RF Integration WBS 121.3.10 |  |  | ED0004129 |  |  |  | ED0004290 |  |  | 
 | Y |  |  |  |  |  | ED0005489 |  |  | 
Cryo Systems WBS 121.3.11 |  | ED0002529 | ED0004129 | Y | Y | Y |  |  |  | 
Warm Units WBS 121.3.12 |  |  |  |  | ED0003441 | ED0003441 |  |  |  | 
Magnet PS WBS 121.3.13 |  | ED0002529 | ED0004129 | Y |  |  |  |  |  | ED0003441
Beam Transfer Line WBS 121.3.14 |  |  |  |  |  |  |  |  |  | ED0003441
Beam Absorber WBS 121.3.15 |  |  |  |  |  |  |  |  |  | 
Beam Instrum. WBS 121.3.16 | Y | ED0002529 | ED0004129 |  |  |  | Y | Y |  | ED0003441
Control Sys. WBS 121.3.17 |  | ED0002529 | ED0004129 |  |  |  | ED0004290 | Y |  | 
 | Y | Y | Y | Y | Y | Y | ED0005489 | Y | Y | Y
Vacuum WBS 121.3.18 | Y | ED0002529 | ED0004129 | Y | Y | Y |  |  | Y | Y
General Supt. Serv. WBS 121.3.19 |  |  |  |  |  |  |  |  |  | 
Safety Systems WBS 121.3.20 | Y |  |  |  |  |  |  |  | Y | 
Test Infrastructure WBS 121.3.21 |  | ED0002529 | ED0004129 |  | Y | Y | Y | Y |  | 
Instal., Integ., Com. WBS 121.3.22 |  | ED0002529 | ED0004129 |  |  |  |  |  | Y | ED0003441
 |  | F10051442 | F10051442 | F10051442 | F10051442 | F10051442 |  |  |  | 
Booster WBS 121.4.1 |  |  |  |  |  |  |  |  |  | 
RR/MI WBS 121.4.2 |  |  |  |  |  |  |  |  |  | 
Conv. Facilities WBS 121.5 |  | ED0002529 | ED0004129 |  |  |  |  |  |  | 
 | Y | F10051442 | F10051442 | F10051442 | F10051442 | F10051442 |  |  | Y | 
Charge #1

## Slide 14: Progress to date
Magnets
  TRS, FRS and RA completed
  Design beyond the conceptual level
  Engineering analyses have covered magnetic field, thermal,
Vacuum
  Concept established
Integration:
  Concept established
FRS established (ED0004583)
Cost was estimated
Interface Documentation to be created
Charge #1

## Slide 15: Design Review Plan
  Prelimary Design review
  Final Design Review
  Following Div/Dept review procedures
  Procurement Readiness Reviews where appropriate
Charge #3

## Slide 16: ESH&Q
  Following project ISM and QA plans (docdb #141 and 142)
  Hazard Analysis for tasks
  QA/QC activity such as:
    Flowdown to vendors/collaborators
    Specific Test procedures or protocols in development
Charge #4

## Slide 17: BOE Summary
Charge #2
WBS Number | Title | Docdb #
121.3.12.2 | Linac Warm Unit PM and Coordination | 902
121.3.12.3 | Linac Warm Unit Design | 905
121.3.12.4 | Linac LB650 Warm Units | 911
121.3.12.5 | Linac HB650 Warm Units | 914

## Slide 18: Cost Summary
Total Cost $2.2M
Estimate uncertainty assigned according project guidance
Charge #2

## Slide 19: Cost Drivers and Estimate Maturity
M&S cost relatively low due to in-kind contribution
Charge #2
P6 Base Costs = BOE + Overheads + Escalation

## Slide 20: Cost Profile – P6 Base Cost Only
MS cost peaks before Labor
Significant Labor effort for cleanroom assembly
Charge #2
P6 Base Costs = BOE + Overheads + Escalation
Chart: Annual Costs ($000)
| FY19 | FY20 | FY21 | FY22 | FY23
Labor | 130.938 | 168.292 | 144.232 | 345.726 | 82.518
Material | 0 | 166.442 | 519.353 | 2.916 | 0
Cumulative Tot. | 130.938 | 465.672 | 1129.257 | 1477.899 | 1560.417

## Slide 21: Labor Profile – P6 Hours/FTE
Engineering effort is heavy during design phase
Tech effort is heavy during construction
Charge #2
Chart: Annual FTE
| FY19 | FY20 | FY21 | FY22 | FY23
Engineer | 0.53 | 0.56 | 0.24 | 0.33 | 0.12
Technician | 0 | 0 | 0 | 1.46 | 0.71

## Slide 22: Schedule – LB650 and HB650 Warm Units
Charge #2

## Slide 23: Schedule
Charge #2

## Slide 24: Summary
  Requirements for Warm Units are defined
  Conceptual design completed and can meets the requirements
  Cost, schedule, and risks are understood
  Sincerely look forward to your feedback
  Thank you

## Slide 25: END