## Slide 1
Cons Gattuso
Summer Shutdown Status
10/9/17

## Slide 2: Linac LRF3 Marx Installation
Marx Modulator
This week
  Connection being made into the controls system
  Safety system testing will occur this week
Next week
  Commission of the LLRF side of the station
  High level to follow

## Slide 3: Main Injector/Recycler
MI
  Replace MI RF station 4 ~95% Done
    ~1.5-2 weeks
  Ion pump maintience ~90% Done
    ~1-2 Weeks
  8 Gev line
    Ion pump replacement ~100% Done
      ~1-2 weeks
    Vacuum leak check~100% Done
      ~1-2 Weeks
    Multi wire replacement (2)
      ~1 Week -Cancelled
  General maintience for MI/RR ~80% Done
    ~2-3 weeks
      Tunnel and service building
  Replace the beam pipe in Q504 -95% Done
    Vacuum leak on BPM feed through
  Switching Flourinert in the MI-10 and 60 kicker systems 100% Done
    Replacing FC-77 to FC-40
RR
  TSP upgrade from 106-229 -~100% done
    10-11 weeks
  Aperture improvement at the RR 402 and 520 locations
    ~3 weeks at the 402 – ~40%Done
    ~1.5 weeks at the 520 ~100% Done
  Recycler Abort lamberstons replacement
    ~3 weeks at the 402
  Recycler Sextupole stand change out ~100% Done
    ~3 weeks
  New Pinger installation in the 10 region ~95% Done
  Rebuilding and putting back into operations RRRF Anode power supply ~50% Done

## Slide 4: RR-40/Abort Before

## Slide 5
LCW Header relocation Completed
Lambertson stands installed and load tested
Installation schedule to occur Wednesday

## Slide 6
Upstream beam pipe
Installed and aligned
Welding will start Tuesday

## Slide 7: Muon Campus Work
  Mu2e work
    M4 line installation ( first half to absorber)
      Stand and magnet 95% complete
      Cable pulls/termination installation (7-9 weeks) 100% complete
  In support of g-2
    Delivery ring straight section 60% complete
      D30 Injection septa (1-2 weeks) -90% complete
      Removal and reinstallation of ring for the M4 line installation ~ 2 days 30% complete
      D10 Straight PWC/IC removed for repair, Installation will occur tomorrow
      D50 Straight Section ( will be done at the same time as the abort line)
    Abort line
      Extraction septa
        Take delivery this week
    Instrumentation Repair 75% complete
      PWC and IC’s ~ 10-12 weeks
    Beam Pipe Aperture Inspection 90% complete

## Slide 8: Switchyard
4 inch Aluminum header leak

## Slide 9: 2017 Shutdown Pocket Dosimeter Reports – Week 11
Chart: Cumulative Effective Dose per Week of Shutdown
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
 | 0 | 280 | 487 | 687 | 1037 | 1265 | 1496 | 2160 | 2539 | 2966 | 3265 | 3598 | 4024 | 0 | 0 | 0
4,024 person-mrem
147 people reported some dose, with average dose of 27.37 mrem
SHUTDOWN SO FAR:

## Slide 10
Chart: Number of Rad. Workers in a Range of Shutdown Cumulative Effective Doses
| 1 - 25 | 26 - 50 | 51 - 75 | 76 - 100 | 101 - 125 | 126 - 150 | 151 - 175 | 176 - 200 | 201 - 225 | 226 - 250
 | 99 | 23 | 10 | 9 | 3 | 1 | 0 | 1 | 1 | 0

## Slide 11: Week of Oct 9th (this week)
Safety System Testing
  Completed today
    Linac/NTF
    Booster
    Prevault/Pretarget, transport (all 3 section)
  Tuesday
    NuMI enclosures
  Later in the week
    MI12 A/B
    8 GeV line
    Meson enclosure
    F-Sector, Transfer Hall, CDE and J
Complete/Verify Enclosure cleaning
  Needs to be cleaned
    Main Injector, Muon Campus Rings and M4 extraction Line

## Slide 12: Week of Oct 9th (this week)
  Get Major LCW systems on to operational levels
    Booster
      Slowly raising pressure and flow to operational levels
    MI
      Monday
        MI RF LCW system is up and running
        NuMI closed loop system is up an running
      Tuesday
        Fill and pressurize system
      Wednesday
        Turn on Ring Wide LCW and Pond pumps
    Switchyard
      Monday
        Complete Enclosure C repairs
      Tuesday
        Fill and pressurize system
      Wednesday
        Turn on the Switchyard system and balance flows and pressure

## Slide 13: Next week
Complete Cleaning
  Main Injector
  Muon Campus
Complete remaining System Testing
Out of all enclosure by 16:00 hrs Friday Oct 20th

## Slide 14: Shutdown Duration Drivers
Linac Marx Modulator installation
  Station 2 upgrade commissioning underway
  Production 1 moved to LRF3 location
    Commissioning process
Main Injector
  Recycler Abort Lamberstons
Muon Campus Work in general
  Additional crews will be added
  Re-structing the workflow