## Slide 1
Paul Derwent
PIP-II PMG
18 October 2017
Status of ICR

## Slide 2: Independent Cost Review
Kicked off week of October 2
  Michael Fenn (DOE/OPM) is lead
  Adam Bihary (DOE/FSO) is Point of Contact between review team and project team
  Paul Derwent is project POC
List of documents requested to be available at the start
Created a web site dedicated to ICR documents
  Requests for additional documents/information
On site review 4-7 December
  Overview presentations
  Drill Downs in agreed upon areas
  Closeout report
Final Report February/March time frame

## Slide 3
Description | Required | Notes
CD-0 Documents (e.g., Mission Need Statement, Approval of Mission Need) | Yes | 
Mission Need Statement, signed copy | Yes | 
Program Requirements Document | Yes | In the MNS
System requirements document | Yes, If used | see the FRS
Conceptual Design Report to include: | Yes | 
Alternative Analysis | Yes | AoA Document & Selection Memo
Life-Cycle Cost Analysis |  | In the AS
Evaluation Criteria |  | see AoA Document
Hazard Analysis | Yes | PHAR
NEPA Documentation | Yes | EENF & NEPA Determination
Project Execution Plan / Project Management Plan | Yes | 
Project Schedule (Critical Path/Near Critical Path Schedule - resource loaded) | Yes | Technically limited by 10/2
Cost Estimate | Yes | in progress
Contingency & Cost Range determinations |  | TBD
Cost and schedule basis documents, including assumptions | Yes | BOE's
Assumptions Document & Lab Interface Documents |  | Lab Interface documents in work
Risk Analysis Report, Risk Management Plan, Risk Register for both Federal and Contractor Risk | Yes | RMP & Risk Register complete, and Risk analysis pending

## Slide 4
Acquisition Strategy | Yes | 
Acquisition Plan | If Complete | N/A
Civil / Structural / Architectural Plans | If available | 
P&IDs | If available | N/A at this time
Plot Plans | If available | 
Heat and Mass Balance | If available | N/A
Cost estimate backup, including vendor quotations, parametric formulas, engineering calculations, and historical costs. | Yes | in the BOE's
Proposed Code of Record | Yes | N/A
WBS | Yes | 
WBS Dictionary | Yes | Yes
Constraints for each work package or activity | Yes | See Assumptions Doc & BOEs
Summary project milestone schedule and CD Strategy | Yes | PPEP
Design Review Reports and comment resolutions | Yes | P2MAC Review
Constructability Reviews | If available | N/A at this time
Value Management Plan / Value Engineering Report | Yes | see PPEP
Project Data Sheets | Yes | N/A at this time
Proposed Project Funding Profile | Yes | PPEP
Regulatory Agreement Documentation | Yes | N/A
Description | Required | Notes

## Slide 5
Conceptual Safety Design Report identifying significant project risk and safety features | Yes | PHAR
Preliminary Security Vulnerability Assessment | If available | 
Start-up Testing and Turnover planning documents and other operational readiness plans | If available | N/A at this time
Federal and Contractor organization charts and staffing plans | Yes | PPEP and PMP
Overhead, Fee, Fringe Agreements/Plans | Yes | Guidance From FRA Finance
Tailoring Strategy (if required) | Yes | PPEP
Lessons Learned that support Estimate | As applied | Presentation at ICR Face to Face
P6 Schedule (native & pdf) |  | Technically limited by 10/2
Milestone Chart |  | Technically limited by 10/2
Description | Required | Notes