## Sheet1
Week of
| 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11
| 2017-11-20: Thksgv; 2017-12-04: ICR, IIFC; 2017-12-11: IPR | Responsible | Comments
Receive IPR Funding Profile from HEP | [9 empty] | Mike P | bar: 2017-10-16
Identify UK in-kind scope | 2017-10-16: XXXXX | Steve, Allan, Jim | Teleconference with Peter Mcintosh set for 10/20
Characterize CEA position on in-kind cont. | 2017-10-23: XXXXX | Steve
Document UK in-kind impact on TPC | 2017-10-23: XXXXX; 2017-10-30: XXXXX | Steve, Allan, Jim | Documented analysis in docdb
Activate MI/RR BOEs | [9 empty] | Paul | These should be good to go now | bar: 2017-10-16
Incorporate MI/RR scope into P6 | 2017-10-16: XXXXX | Luisella | Should be straight-forward: planning packages
Rebalance Est Uncertainty for CF | 2017-10-16: XXXXX | Steve D | Everthing is 20.0%
Adjust BOEs for new funding profile (primarily LOE) | 2017-11-06: XXXXX | Paul | Mostly standing army. P6 will calculate additional inflation directly.
Adjust P6 for new funding profile | 2017-10-16: XXXXX; 2017-10-23: XXXXX; 2017-10-30: XXXXX; 2017-11-06: XXXXX; 2017-11-13: XXXXX | Luisella | Start moving tasks with lots of float first
Reconcile BOEs with P6 | 2017-11-06: XXXXX; 2017-11-13: XXXXX | Chris
Document schedule assumptions that developed the international milestones | [10 empty] | Consolidate with Int'l risk mitigation?
Fix P6 schedule logic errors | 2017-10-16: XXXXX; 2017-10-23: XXXXX; 2017-10-30: XXXXX; 2017-11-06: XXXXX | Luisella | Correcting the logic ties to CDs is probably most important
Post supporting documents in BOEs | 2017-10-30: XXXXX; 2017-11-06: XXXXX | Allan, Jim
Assign colors of money in P6 | [10 empty] | Lower priority
Resource Leveling? | [10 empty] | Lower priority
TPC Calculation | 2017-11-13: XXXXX | Chris
Clean up risk register | 2017-10-16: XXXXX; 2017-10-23: XXXXX; 2017-10-30: XXXXX; 2017-11-06: XXXXX | Shekhar
Assign Risks to Activities? | [10 empty] | Are we concerned at all about running the MC on the full schedule?
Risk Monte Carlo | 2017-10-23: XXXXX; 2017-11-13: XXXXX | Shekhar | 25 working days until BOEs , RLS, and Risk Register updated
CD-4 Float Analysis | [10 empty] | Just using MC will not be enough. In parallel, apply the estimate uncertainties only to task on critical path.
Benchmarking? | 2017-11-13: XXXXX | Steve | Can we redo any benchmarking to other projects? CM assembly to LCLS-II, overall comparison to SNS….
Risk Mitigation Strategy for Int'l Deliverables | 2017-10-30: XXXXX | Steve, Allan, Jim
Update DOE IPR Recommendations | 2017-11-06: XXXXX | Steve
Update P2MAC Recommendation | 2017-10-30: XXXXX | Valeri
Update Director's Review Recommendations | 2017-11-13: XXXXX | Steve
CAM Orientation | 2017-11-13: XXXXX | Richard, Dean | EVMS Orientation for all review speakers and/or L3Ms (2-3 hour session)
Preliminary CAM Assignments | [9 empty] | Steve, Paul
Finalize documentation
Proj Man Plan | 2017-10-30: XXXXX | Steve | Finalize
PIP-II - Fermilab Interface Document | 2017-11-06: XXXXX | Steve
Assumptions Document | 2017-11-06: XXXXX | Steve | Requires mods
QAP | 2017-10-23: XXXXX | Teri, Allan, Jim
Risk Management Plan | 2017-10-30: XXXXX | Shekhar | Requires mods
Acquisition Strategy | [9 empty] | Adam, Paul | This is very tight schedule wise | bar: 2017-11-20
PPEP | [9 empty] | Adam, Paul | This is very tight schedule wise | bar: 2017-11-20
Propose IPR Agenda | [9 empty] | Adam, Steve | bar: 2017-11-06
Financial, Schedule Slides to speakers | 2017-11-20: XXX | Luisella, Chris
IPR Dry Runs | 2017-11-27: XXXXX | Steve, Paul, Jim, Allan, Ioanis, Steve
ICR Drill-down Dry Runs | 2017-11-27: XXXXX | Dean
Talks posted | [10 empty] | 33 working days until talks posted | No float on this! | bar: 2017-12-04
Define Scope of International Participation in the Review | 2017-11-06: XXXXX; 2017-11-13: XXXXX | Steve