## Slide 1
Cons Gattuso
Summer Shutdown Status
10/23/17

## Slide 2: Linac and Booster
Beam signs were scheduled for 14:30 hrs. this afternoon
  Linac has 2-3 days of studies and commissioning that will occur
  Booster has 3-4 days of studies and commission that will occur

## Slide 3: BNB beam
8 Gev Line
  Ready to go
MI12A/B and target Hall
  Ready to go
MI/RR
  MI-10 section
    MI LCW water leaks (completed by Wednesday)
      MI 126 Downstream Quad Manifold
      MI 102 Downstream Quad Manifold
      MI 848 Upstream Fitting Leak

## Slide 4: MI Work Remaining
MI
  RR 40 Lamberston installation
    Beam pipe shielding
    Replace a damage BPM feed through
      Fix in place
  MI20-62 section
    MI307 Injunction kicker B failure
      ~2 days to replace
        ~600-700 person mr to complete this task
    LCW leaks (3-4 days)
      MI/RR-402 New MLAW Magnet
      MI 400 Area Lambertson Magnet Leak
      MI 637 Dipole Upper Bus leak
      MI 428 Quad Magnet Leak
      MI 503 Quad Magnet Leak

## Slide 5: RR BPM 302 location

## Slide 6: MI307 Injection Kickers

## Slide 7: Muon Campus Work
  Delivery ring straight section 80% complete
    D30 Injection septa -95% complete
      Testing of the system,
    Removal and reinstallation of ring for the M4 line installation ~ 2 days 30% complete
  Abort line 80% complete
    Extraction septa
      Installed under vacuum, leak check remaining
      Electrical connections and water
  Instrumentation Repair 90% complete
    M5 line installation has completed
      Waiting on alignment
  M3 line correction element installation 80% complete
    Corrector installation 4 of 5 done
    Last corrector most difficult installation
  This Week
    Install abort septa cable
    Final walk throughs
    Power supply commissioning
  Oct 30th – Beam start up

## Slide 8: Injection Septa

## Slide 9: Abort Septa

## Slide 10: M3 line corrector

## Slide 11: M5 line PWC

## Slide 12: Schedule
This week
  Install Abort Septa
  Tunnel cleaning
  Return to safety system keys by Friday
  Safety System tests Friday
  Install abort septa cable
  Final walk throughs
  Power supply commissioning
Oct 30th – Beam start up

## Slide 13: 2017 Shutdown Pocket Dosimeter Reports – Week 13
Chart: Cumulative Effective Dose per Week of Shutdown
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
 | 0 | 280 | 487 | 687 | 1037 | 1265 | 1496 | 2160 | 2539 | 2966 | 3272 | 3628 | 4069 | 4463 | 4785
4,4785 person-mrem
157 people reported some dose, with average dose of 30.48 mrem
SHUTDOWN SO FAR:

## Slide 14
Chart: Number of Rad. Workers in a Range of Shutdown Cumulative Effective Doses
| 1 - 25 | 26 - 50 | 51 - 75 | 76 - 100 | 101 - 125 | 126 - 150 | 151 - 175 | 176 - 200 | 201 - 225 | 226 - 250 | 251 - 275
 | 104 | 24 | 10 | 10 | 2 | 5 | 0 | 0 | 0 | 1 | 1

## Slide 15: Week this week
Linac
  Beam commissioning
Booster
  Beam commissioning
MI/RR (out of the tunnel by Thursday)
  40 lamberstons installation
    BPM replacement
  LCW leak repairs
  Start commissioning RF system
BNB
  ready for beam
NuMI
  Power outage on Wednesday
  Ready for Beam scans (week of October 30th)
SY
  MS2 water system commissioning

## Slide 16: Shutdown Duration Drivers
Linac Marx Modulator installation
  Station 2 upgrade commissioning underway
  Production 1 moved to LRF3 location
    Commissioning process
Main Injector
  Recycler Abort Lamberstons
Muon Campus Work in general
  Additional crews will be added
  Re-structing the workflow