## Sheet1
Date Completed
Deliverable | APA | Comments
Complete response to Design Review
Final Drawings |  | Issued and approved by PSL
Calculations |  | Issued and approved by PSL
Bill of Material |  | Issued and approved by PSL
Printed Circuit Board Documentation |  | Issued and approved by PSL
QC Plan
Inspection, Test and Integration Procedures
Manufacturing Travelers
APA frames | 2017-08-01
APA#1 X-plane tensions | 2017-09-01
APA#1 V-plane tensions | 2017-10-01
Test Reports
Software Verification and Validation Documentation
Nonconforming Items Documentation
APA frame 2mm short | 2017-10-01
Missing pin - hence wire | 2017-10-01
Supplier Documentation
Portabello Frame Dossier | 2017-08-01
Welder Qualifications
Steven Daggett - BS EN ISO 17637:2011 | 2014-04-01
Qualified Weld Procedure Specifications
Personnel Training and qualification
Dan Salibury - STFC Elec Tech
Diego Garcia Gamez - Manchester Post Doc
Slawomir Kubecki - Manchester Mech Tech
Mathew Henderson - Liverpool Elec Tech
Liam Boynton- Liverpool Elec Apprentice
Final Production Plans
Manufacturing Procedures | 2017-03-01
Handling, Storage and Packaging Procedures
Shipping Plan
APA#1 | 2017-12-01
Hazard Analysis Documentation
APA Assembly | 2017-03-01
Cold tank delivery and operation proceedure | 2017-05-01
Final Prototypes