## Slide 1: CD0 Range to CD1 Range
 |  | FY13 base year | FY16 base year
WBS @ L2 | Title | November 2016 Estimate | November 2017 Estimate
121.2 | Project Management | $55 | $52
121.3 | Linac | $190 | $284
121.4 | Rings Upgrade | $48 | $36
121.5 | Conventional Facilities | $89 | $140
Base Total |  | $382 | $513
Contingency |  | $134 | 
Estimate |  |  | $113
Risk |  |  | $78
Total Contingency |  | $134 | $191
Point Estimate To Complete |  | $516 | $704
Actuals |  | $- | $32
UK contribution |  | $- | $(15)
Total |  | $516 | $721
Cost Range Lower |  | -10% | -10%
Cost Range Upper |  | 26% | 20%
Base Cost: Direct + Overhead + Escalation
Entries are in $M
2016 Estimate contingency was top down 35%
2017 Estimate Contingency is 22.1% Estimate Uncertainty, 15.2% Risk Analysis

## Slide 2: Changes
Project Management:
  had people paid on project (ESH&Q, Admin, IT) now part of overhead pool (20 FTEs fewer, so it went down)
Linac:
  LCLS-II
    Lessons Learned from the actual experience
    Built 5 CMs
  Better understanding of In Kind Oversight requirements
    Engineering, Purchasing, Fabrication
    Visits, Reviews, Travel
  LB650
    CD0 In kind contribution, estimated the total, then set DOE cost to zero
    $11.3M in CD1, $11M is labor
      PM & Coordination
      Design effort
      Testing all 11 CMs

## Slide 3: Changes
Rings Upgrades
  Scope moved forward to support current program (gt system)
Conventional Facilities
  Conceptual design to understand requirements
  Parametric estimates -> A/E Construction estimates
  Site Prep:
 | 2015 Estimate | 2017 Estimate
Cryo Plant | 4000 | 23245
Utility Plant | 9650 | 7995
High Bay | 7650 | 21275
Tunnel | 10725 | 19935
Gallery | 23000 | 32905
Transfer Line | 12000 | 14435
Booster Conn |  | 7750
Total | 67025 | 127540
Site Prep & Utilities | $17,086,800 | $27,683,281
Floor Sizes

## Slide 4: Changes
Escalation:
  CD0 estimate 2013 Base Year, escalated to FY20 (assumed midpoint)
  CD1 estimate 2016 Base Year, escalated to year work performed (by Primavera P6)
    Cost weight mid point FY22.5 -> 2 years at 3.1% labor, 2.0% M&S
    ~5% or scale of $20M