## Slide 1: Understanding FNAL Earned Value Management Processes Using Flow Diagrams and Visuals
Presenter’s Name: Rich Marcum, OPSS Project Controls Manager
Meeting Title : EVMS Training – Process Flow Charts and Visuals
10 February 2016

## Slide 2: EVMS Official Definition
An Earned Value Management System (EVMS) is the overall methodology that organizations use to plan, manage, control, and analyze the cost and schedule performance of projects. It encompasses organizational policies, business processes, automation support, standards, and accountability for results.
ANSI-EIA Standard 748

## Slide 3: Earned Value Management System - Simplified
Earned Value Management System
Management of People (Who)
Management of Project Deliverables (What)
Management Processes (How)

## Slide 4: EVM Principles
Organize
Plan
Authorize
Execute
Monitor
Control
Control
Plan
Organize
Monitor
Execute
Authorize

## Slide 5: EVMS Responsibility seen from 40,000 Feet
Total Project Cost
Performance Measurement Baseline / Budget at Completion
Control Accounts
Work Packages
Planning Packages
RESPONSIBILITY
BUDGET ELEMENT
CUSTOMER
PROJECT MANAGER
CONTROL ACCOUNT MANAGER
Contingency
Undistributed Budget
Management Reserve
CAM Summary Responsibilities on Next Slide

## Slide 6: Control Account Manager (CAM) Responsibilities
Oversite & Planning
Establish Baseline Schedule
Establish Baseline Budget
Execution of Work Scope
Manage Risk
Monitor and Analyze
Control Scope Creep
Report and Communicate
SCOPE
High Level Overview of Responsibilities
Notes: Plan:
Develop Estimates
Develop Schedule
Execute Plan
Control Change (scope creep)
Control Risks

## Slide 7: EVMS Elements

## Slide 8
EVM Gold Card – EVMS Terminology/Definitions
This block has been modified to better Represent FNAL

## Slide 9
EVM Gold Card – EVMS Calculations

## Slide 10
EVM Gold Card – EVMS Terminology/Definitions

## Slide 11: Terminology
Components necessary for determining and analyzing earned value performance:
  Planned Value - cost of work that was planned to be accomplished
    Plan
    Budget
    BCWS - Budgeted Cost of Work Scheduled
    Science Related Terminology – Target or Theory
  Earned Value - calculated cost of work that was accomplished
    BCWP - Budgeted Cost of Work Performed
    Science Related Terminology – Results or Outcome
  Actual Value - actual amount it cost to perform the work
    Actuals
    Incurred
    ACWP - Actual Cost of Work Performed

## Slide 12: More EVM Terminology
Control Account (CA)
  Lowest WBS element assigned to a single focal point to plan and control scope / schedule / budget
Budget at Completion (BAC)
  Total planned cost for the project
Performance Measurement Baseline (PMB)
  Integrates Scope, Schedule, Cost, Resources, Technical Milestones
  Project time-phased budget plan
  Used to benchmark cost and schedule performance of project
Scope
(Work)
Schedule
(Time)
Budget
(Cost)

## Slide 13: More EVM Terminology
Variance
  Deviation from the Baseline (planned) cost or schedule
  Positive Variances are Favorable
  Negative Variances are Unfavorable
Total Project Cost (TPC)
  Total Cost of Performing Project’s Scope of Work from inception to close.
Resource Loaded Schedule (RLS)
  Logical Timeline of Scope to work and Resources to perform the work (Labor & M&S)
Performance Measurement Technique (PMT)
  Use to measure how much work scope is performed
Estimate Uncertainty (EU)
  FNAL standard used to calculate contingency based on estimate quality

## Slide 14
Control Account (Key Element Touched by All Procedures)
Marriage of OBS and WBS (Who & What)
CA Related to most EVMS Guidelines as it relates to RAM, Schedule, WBS, WAD, Etc.
Further Details Next 2 Slides (Planning & Authorization Flow chart and Data Flow)

## Slide 15
Responsibility Assignment Matrix – RAM (12.PM-001)
Who & What
RAM Related to EVMS Guidelines 2, 3, 5, 9 & 18

## Slide 16: Establish Baseline – Data Flow Traceability
Scope
Establishes boundaries of project work scope and deliverables
Estimate
Answers what will be the base cost of performing Scope
P6 Schedule (Resource Loaded)
Answers how long will it take to perform scope with given base cost constraints
Establish Performance Measurement Baseline (PMB)
Pre CD-2 P6 also used for
Rates & Escalation
Data Flow build on Foundation built by WBS, OBS, RAM
Control Account is Key Control Point

## Slide 17
Schedule Traceability: Vertical & Horizontal
Vertical traceability ensures that external schedules and dependencies, including the client and subcontractor, are in sync the project schedule
Horizontal traceability ensures project interdependencies and scope, including control accounts, work packages, and planning packages are accounted for
FNAL
Summary Schedule Vertical Traceability

## Slide 18
Identify Critical Activities (Float and Critical Path)
Two Key Terms
  Activity Float
  Free - Immediate Relationship
  Total - Project Completion
  Critical Path
Float and Critical Path Details in next two Slides

## Slide 19
  Float – Difference between early dates and late dates; if difference is >0, the activity has float
Zero float – Longest path of logically related activities through network that cannot slip without impacting project duration
Total float – The amount of time an activity can be delayed before it impacts the project end date
Free float – The amount of time an activity can be delayed before it impacts the succeeding activity
Float

## Slide 20
Critical Path
  Critical path – Activities that cannot slip a day without increasing total project duration or delaying completion; if float < 1, the activity is on the critical path
  Technical Critical path – What aspect of the work is critical? IE – piece of equipment needs to be ordered early; foreign order, etc.

## Slide 21
Determine Resources for Activity
Assigned to Tasks or Activities
Resource ID Encoded
Labor
M&S
Consult with SME’s, Prior Experience, to Determine needed Resources
Reflecting Basis of Estimates (BOE)

## Slide 22: Burden Cost and Escalation
 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21
Labor | 2.9% | 3.0% | 3.2% | 3.3% | 3.4% | 3.5% | 3.6%
M&S | 1.7% | 1.9% | 1.9% | 1.9% | 2.0% | 2.0% | 2.0%
FNAL Budget Office Develops and Determines
  Escalation Rates
  Indirect Rates
The Accounting Department is responsible for developing Labor Burdens to be incorporated in Rates
Rates are Communicates to OPSS to incorporate into systems
  Input into FNALs Cost Processor (Cobra) Rate Tables
  Rate Table Changes are Communicated to Projects for Incorporation and Result in Processed of BCRs

## Slide 23: Project Life Cycle – Models
Initiation
Planning
Execution
Close-out

## Slide 24: EVMS Tools
CAMs are not expected to be experts at tools used in our EVMS. However, they must know how they are used to control their accounts.
Four primary data tools
  Primavera P6
  Excel/MS Word
  Accounting DB
  Cobra
  Three reporting tools
  Cobra
  P6
  Excel
Next 5 Slides Describe Tool Details