## Slide 1: ProtoDUNE SP (NP04) DAQ
Karol Hennessy, Giovanna Lehmann Miotto
DAQ Status overview
10 May 2018
DAQ “nations”: Netherlands, UK, US, CERN

## Slide 2: Introduction
The ProtoDUNE DAQ environment
External interfaces and constraints
DAQ logical architecture
Main DAQ components and their interaction
DAQ status
Summary

## Slide 3: Scope of the ProtoDUNE DAQ
Provide service to the detector/electronics validation
  Take and store data safely and efficiently
  Reuse existing components, experience, …
Evaluate DAQ solutions and technologies that may be suitable for DUNE
  TPC readout system
  Data storage
  Dataflow software (hardware fully COTs servers + switches)
  Control and monitoring software

## Slide 4: ProtoDUNE SP environment
Detector
  6 Anode Plane Assemblies
  TPC (15kCh @ 2 MHz)
  Photon detectors (720 SiPM/ 240 ch)
On surface
  High flux of cosmic ray particles
On SPS beam line
  charged particles 0.5 – 7 Gev/c
The rate and volume of data produced by these detectors will be substantial (O(Tb/s))

## Slide 5: DAQ in numbers
Data Production at Detector ≈ 450 Gb/s
Readout to DAQ ≈ 450 Gb/s
If continuous readout:
  Averaged bandwidth over SPS cycle (and if no data when no beam) ≈ 135 Gb/s
  Expected DAQ compression capacity ≈ x 4
    Average storage throughput ≈ 34 Gb/s
Triggered readout to control bandwidth and take selected data instead of any data
  Design figure TDR => min 25 Hz [max 100 Hz] of triggers during spill
  Corresponds to 17 Gb/s [68 Gb/s] of average storage bandwidth (4.2 Gb/s [17 Gb/s] with x4 compression)
    Peak ≈ 56 Gb/s [225 Gb/s] (14 Gb/s [56 Gb/s] with x4 compression)
Changed! 2x4.8s extractions in 32.4 s

## Slide 6: Interfaces
DAQ
Photon Detectors (SSP)
TPC (WiB)
Beam Instrumentation
CRT
SPS
Offline Computing
Spill Signal
Trg In
Trg In
Timing + Trg out
Data
Data files + metadata
Timing + Trg out
Data

## Slide 7: Constraints
Decoupling
  The DAQ needs to ensure a proper decoupling between the “online” and the “offline” worlds
    Sufficient storage space for raw data files on the DAQ side should be available to store up to 3 days worth of data taking.
    Min 135 TB required (25 Hz in spill + x4 compression), 460 TB of usable space installed
  The maximum allowed throughput from online to offline is 20 Gb/s
Grounding
  Keep all DAQ equipment on building ground
  Any link connecting the detector must be isolated -> optical
    Direct impact on readout, timing, trigger

## Slide 8: The ProtoDUNE DAQ
TPC
Off detector readout systems
Ring Buffer
Event Building
Temporary Storage
Beam Instrumentation
Trg+Timing
Photon Detectors
Off detector readout system
Summary Info
Data Compression
450 Gb/s
25 Hz in spill
EOS
Max 20 Gb/s
Event size ~70 MB (5ms window, x4 compression)
DB
Monitoring
Cosmic rays tagger

## Slide 9: ProtoDUNE software
Dataflow software is based on artDAQ developed at FNAL
  Customizable “Board Reader” application
  Event building
  Dispatching to monitoring apps
  Aggregation and storage
  Data flow control through load balancing & trigger inhibit
Control, operational monitoring, graphical UIs
  Joint COntrols Project (JCOP) toolkit developed at CERN originally for control of LHC experiments
  Uniform interface also for detector control and safety systems
Software approach
  Minimize the risks by relying on existing frameworks
  Focus effort only on experiment specific needs

## Slide 10: Readout of detectors
PDS
  On detector electronics already does data reduction and sends data over TCP/IP (-> DAQ starts at Board Reader)
TPC (point-to-point optical links from WiB)
  2 solutions being implemented
    Baseline: ATCA platform from SLAC
    Prototype alternative: ATLAS FELIX + network connected PCs
  5 APAs will be readout via ATCA boards (12800 ch), 1 APA (2560 ch) via FELIX
    2 firmware variants in electronics (WiB)
    API for transparently treating data at software level
From a software point of view the interface towards the event builder is the Board Reader application for all readout systems

## Slide 11: ProtoDUNE data flow
Board Reader
Event Builder
Event Builder
Board Reader
Board Reader
Routing Master
Trg/Timing
1
2
3
4
5
10 Gbps Ethernet
Aggregator/Storage
6

## Slide 12: ProtoDUNE trigger throttling
Board Reader
Event Builder
Event Builder
Board Reader
Board Reader
Routing Master
Trg/Timing
Aggregator/Storage
No storage space or slowed down disk writing
-> EB cannot clear events
EB cannot get rid of events
-> RM cannot assign new events
DFO full/free
-> BUSY/NBUSY
Readout full/free
-> BUSY/NBUSY
Due to the low trigger rates and the “continuous” readout mode of on-detector electronics, software throttling seems sufficient
-> hardware throttling still possible as an option
Inhibit Master

## Slide 13: EHN1 today
NP04
NP02
DAQ

## Slide 14: DAQ status - HW
NP04 control room
SSPs and DAQ patch panels
Fiber bundles to DAQ

## Slide 15: DAQ status - HW
DAQ storage
Event builder, data logger, monitoring
Cryostat fibers
Trigger board
Timing master
RCE readout
FELIX readout
Board readers
DAQ infrastructure

## Slide 16: Sub-systems status: Timing
Requirements:
  Receive spill signals and global time ✗
  Distribute clock and synchronize endpoints ✓
  Distribute internally generated triggers ✓
  Distribute externally generated triggers ✗
  Manage and track dead-time ✗
  Support multiple partitions ✓
  Drive the data flow ✓
  Respond to trigger inhibit commands ✓
  Integrate with run control ✓
  Provide operational errors and monitoring information ✓
  Provide overlay classes do decode data fragments ✓
Timing
Run Control
Data Mon
Op Mon
artDAQ
Trigger
SSP
WIB
SPS
CRT
TriggerInhibit
RCE
White Rabbit

## Slide 17: Sub-systems status: Trigger
Requirements:
  Receive spill signals ✗
  Receive BI signals ✗
  Receive CRT signals ✗
  Receive SSP signals ✓
  Form trigger decision
    Pass it to timing master for distribution ✓
  Pass data on to data flow ✗
  Generate trigger inhibit ✗
  Integrate with run control ✗
  Provide operational errors and monitoring information ✗
  Provide overlay classes do decode data fragments ✓
Trigger
Run Control
Data Mon
Op Mon
artDAQ
Timing
BI
SSP
SPS
CRT
TriggerInhibit

## Slide 18: Sub-systems status: WIB readout
Requirements:
  Take data from 30 WIBs
    5 in coldbox (RCE) ✓
    1+1 in test setup (RCE + FELIX) ✓
  Pass data on to data flow
    without compression ✓
    compressed ✗
  Continuous readout for noise studies
    3 Hz (“equiv.” 40 Hz in spill, compressed )✓
  Externally triggered with spill structure ✗
  Generate trigger inhibit ✗
  Integrate with run control ✓
  Provide operational errors and monitoring information ✓
  Provide overlay classes do decode data fragments ✓
RCE FELIX
Run Control
Data Mon
Op Mon
artDAQ
Timing
WIB
Not needed
TriggerInhibit

## Slide 19: Sub-systems status: SSP readout
Requirements:
  Take data from 24 SSPs
    Done 23 ✓
  Pass data on to data flow without compression ✓
  Continuous readout for noise studies (full wave forms)
    24 Hz ✓
  Externally triggered with spill structure ✗
  Generate trigger inhibit ✗
  Integrate with run control ✓
  Provide operational errors and monitoring information ✓
  Provide overlay classes do decode data fragments ✓
SSP Board Reader
Run Control
Data Mon
Op Mon
artDAQ
SSP
TriggerInhibit

## Slide 20: Sub-systems status: CRT readout
Development started only recently
Responsibility of CRT group
Requirements:
  Take data from CRT ✗
  Pass data on to data flow without compression ✗
  Generate trigger inhibit ✗
  Integrate with run control ✗
  Provide operational errors and monitoring information ✗
  Provide overlay classes do decode data fragments ✗
CRT Board Reader
Run Control
Data Mon
Op Mon
artDAQ
Timing
CRT
TriggerInhibit

## Slide 21: Sub-systems status: artDAQ
Requirements:
  Readout framework ✓
  Event Building ✓
  Data Storage ✓
    Files metadata creation ✓
  Data dispatching for monitoring ✓
  Load balancing and back-pressure ✗
  DAQ Configuration ✓
    Run history
  Integrate with run control ✓
  Provide operational errors and monitoring information ✓
artDAQ
Run Control
Data Mon
Op Mon
Timing
SSP Board Reader
RCE Board Reader
FELIX Board Reader
WIB Board Reader
CRT Board Reader
Trg Board Reader
TriggerInhibit

## Slide 22: Sub-systems status: Run control
Requirements:
  Start/stop processes ✓
  Coherently step through finite state machine ✓
  Distribute commands to all endpoints ✓
  Inhibit/release trigger ✓
  Create run number ✓
    And set run type ✗
  Visualize operational monitoring data ✓
  Support multiple concurrent data taking partitions ✓
  React to slow control information ✗
Run Control
Slow Control
artDAQ
Op Mon
Timing
SSP Board Reader
RCE Board Reader
FELIXBoard Reader
WIB Board Reader
CRT Board Reader
TriggerInhibit
Trg Board Reader

## Slide 23: Sub-systems status: Operational Monitoring
Requirements:
  Provide plugins to publish counters, statistics and messages in a coherent way ✓
  Gather counters/statistics data for all endpoints ✓
  Archive a selection of data for later analysis ✓
  Provide data visualization in run control framework ✓
    Further improvements planned
  Gather, archive, visualize log messages (info, warnings, errors) ✓
Operational Monitoring
Run Control
artDAQ
WIB Board Reader
Timing
SSP Board Reader
RCE Board Reader
FELIX Board Reader
Trg Board Reader
CRT Board Reader
Web viewer
TriggerInhibit

## Slide 24: Sub-systems status: Online Data Monitoring
Requirements:
  Analyse events dispatched by artDAQ
    Noise, channel maps, data verification, …
  Basic event display
  Instantaneous, integrated, historical visualization of histograms, graphs, …
Data Monitoring
Run Control
artDAQ
Op Mon
Timing data
SSP data
RCE data
FELIX data
CRT data
Trigger data
Web viewer

## Slide 25: Status of DAQ integration
Most of the hardware available at CERN
  Few more hosts being purchased to increase monitoring and data flow capacity
  Final timing master hardware expected in June
Cabling to cryostat complete
  Not fully tested
BI cables pulled, to be terminated and tested
Connection to SPS and White rabbit to be done
Status of DAQ sw/fw:
  Successfully run WIBs + RCEs + SSPs + timing with low rate continuous triggering for cold-box tests (1 APA at the time)
  Successfully run WIB + FELIX+ timing with continuous triggering on vertical slice test HW
  Successfully run SSPs + timing for all 6 APAs with periodic trigger
    Successfully received SSP trigger signals into central trigger
  Successfully established data transfer to EOS
  Successfully used run control and operational monitoring to control and monitor DAQ
  Successfully used Online monitoring during cold-box tests

## Slide 26: Summary and Outlook
The DAQ design presented/reviewed in Nov 2016 has been retained and implemented
The firmware and software components of the DAQ are in an advanced stage of development
  Still pending: data compression, integration of trigger board, trigger inhibit, load balancing
All hardware components required for the DAQ are available
  Servers, switches, interconnects, storage, ATCA based readout solution, FELIX PCIe based readout solution, preliminary timing master and fanout, central trigger board
  Few more servers will be purchased to have more head-room for monitoring and dataflow performance
Integration with the WIBs and SSPs done (still pending: CRT, BI, SPS)
Data transfer to EOS being used routinely (and stress tested during data challenges)
Continued effort to improve stability and performance of data flow
Continuous improvement and extension of online monitoring capabilities
User documentation is being written and updated continuously
The cold-box has been an essential step towards the preparation of the DAQ for NP04
  Created excellent links between detectors, daq, offline
  Tested operation models and started training the expert shifters of tomorrow!

## Slide 27
Celebrating “cold-box 5”