## Slide 1
A. Rowe, J. Steimel
IIFC Joint R&D Meeting
7-8 December 2017
Status of IIFC Activities at Fermilab

## Slide 2: Outline
Overview
SRF & Cryogenics Activities
  Cryogenics Plant
  SSR1/SSR2
  LB650/HB650
PIP2IT Activities
  Warm Front-end
  RF Amplifiers
  LLRF & RFPI
  Instrumentation
  Controls
Summary

## Slide 3: Overview
High-level R&D goals summarized as follows:
  Develop and demonstrate critical technologies for a pulsed and CW capable 800 MeV SRF LINAC
  Establish within the DAE SRF and RF capabilities to natively produce SRF LINAC elements both for PIP-II and for DAE projects.
To accomplish the above:
  Design, prototype, and test to PIP-II performance parameters all critical devices and sub-systems prior to construction start.
  SRF cavities, RF couplers, tuners - both 325 MHz spoke and 650 MHz elliptical varieties
  Cryomodule systems – 325 MHz SSR1 and 650 MHz high-beta
  RF Sources
  Develop mature set of documentation required to produce and test critical devices through the following cycle:
    CDR → FRS/TRS → PDR → FDR → PRR → ORC
    …and relevant engineering documentation to successfully pass the above reviews
Notes: PIP2IT overview slide?

## Slide 4: Cryoplant & Cryogenics System Status
Fully segmented Linac
Single cold box with turbines and cold compressors
Distribution box located in the refrigerator room
Cryogenic transferline with bayonet cans that runs parallel to the cryomodules

## Slide 5: Requirements flow down
PIP-II Conceptual Design Report
PIP-II Conceptual Design Report
Engineering Manual, Fermilab ESH&Q Manual
Cryomodules requirement documents
TC#ED0001313, TC#ED0001316, TC#ED0001829, TC#ED0001830, TC#ED0001322
Cryogenic System
Functional Requirements Specifications (TC#ED0003531)
Engineering Specifications (TC#ED0005493,5587, etc.)
Design Criteria Documents (TC#ED0004748, 6895, etc.)
Engineering Notes (TC#ED0003531,6860, 6901, etc.)
Interface Control Documents (TC#ED0006893)

## Slide 6: Cryogenic System Conceptual Design
* - Used for pulsed mode only
*

## Slide 7: Cryogenic Plant Design – Conceptual Design
Hybrid cycle design
Cold compression design
Baseline
Alternative

## Slide 8: Technical Progress to Date - Cryogenic Plant
Hybrid compression cycle
Comprehensive cryogen plant simulation model is in place.
The model was validated using similar systems actual performance parameters.

## Slide 9: Technical Progress to Date - PIP-II Cryogenic Distribution System
Developed preliminary detailed list of requirements
Defined preliminary loads, steady-state and transient modes  TC#ED0003531
Defined preliminary interfaces and boundaries  TC#ED0006893
Surveyed similar designs
Refined heat load estimates  TC#ED0003531
Interface Control Document  TC#ED0006893
Valve and Instrument List  TC#ED0006894
CDS Functional Analysis  TC#ED0006895
Bayonet Box Functional Analysis  TC#ED0006896
Cryomodule Bayonet Boxes P&ID  TC#ED0006897
Site Layout of Cryogenic Distribution Lines  TC#ED0006898
Pressure drop calculations  TC#ED0006899
Preliminary relief valves calculations  TC#ED0006900
Preliminary piping layout  TC#ED0006901

## Slide 10: Design Review Plan
Cryogenic System is subject to Project Reviews
Divi/Dept review procedures based on the Fermilab Engineering Manual
Technical reviews (PDR, FDR, PRR whenever appropriate)
PIP2IT CDS Internal Review – April 2017
  all recommendations are closed
PIP2IT Cave TL
  Preliminary Design Review – October 2017
  Final Design Review – November 2017
  Production Readiness Review – January 2018
Cryogenic Plant
  ESD review – April 2016
  BARC committee review – May 2016
  All recommendations are closed, RFP was issued December 2016
  PO likely to be released by mid 2018

## Slide 11: SSR1, SSR2: Overview
PIP-II Conceptual Design Report: DocDb# 113
 | SSR1 | SSR2
# CMs | 2 | 7
Cavities per CM | 8 | 5
Solenoids per CM | 4 | 3
CM configuration c: cavities; s: solenoids | 4x (csc) | sccsccsc
CM length (m) | 5.2 | 6.5
SSR CMs capable of operating in both pulsed and CW modes with a beam current of 2 mA avg.
SSR: Single Spoke Resonator
SSR1 cryomodule

## Slide 12: SSR1,2 Cavities and Cryomodules – Requirements & Partner Interfaces
Functional Requirement Specification (FRS) are defined and traceable in Teamcenter:
SSR1 Cryomodule/Cavities: TC# ED0001316 / TC# ED001317
SSR2 Cryomodule/Cavities: TC# ED0001829 / TC# ED0001854
Partner Interfaces.
SPC/SPM and POC direct communication through bi-weekly update meetings.
Doc transfer through Teamcenter/Librarians and Sangam
SSR1 Cavities partner: DAE-BARC/IUAC
  fabrication of two dressed cavities
SSR2 Cavities partner: DAE-BARC
  Bare and dressed cavities design and production
  Tuners design and fabrication
  Solenoids, leads and BPS design and fabrication

## Slide 13: 121.3.5 SSR1: Cavities Design Maturity
SSR1 CM1 is well beyond the conceptual design.
  10 FNAL cavities were jacketed with stainless steel vessels.
  2 DAE BARC cavities are currently receiving the He- vessel
  Current activities: qualification of jacketed cavities by cold testing at Spoke Test Cryostat (STC) to meet SSR1 cavities FRS (TC# ED0001317)
  SRF technology enabled: 12 bare SSR1 cavities (10 FNAL and 2 DAE BARC/IUAC) met PIP-II requirements in VTS.

## Slide 14: 121.3.5 SSR1: Tuner and resonance control
Prototype SSR1 tuner
Design completed and one unit was prototyped
Successfully tested at 293K and cold temperature
Production SSR1 tuner
Design completed
1 out of 10 units was received and currently used for resonance control of SSR1 cavities
Resonance control studies
  Requirements: microphonics <20 Hz
  Requirements nearly achieved….

## Slide 15: 121.3.5 SSR1: Solenoid, BPMs, couplers
Four production solenoids were successfully designed, procured and qualified.
Four production BPMs were successfully designed, procured and qualified.
Joint collaboration ANL &FNAL
TC# ED0005680
TC# ED0001264
Prototype main power couplers
Design, procurement and testing: completed
Three prototypes were procured and successfully tested
Production main power couplers
Design completed
Procurement: in progress
  The procurement of coupler antennas presented a series of technical issue that led them to be on the critical path.

## Slide 16: 121.3.5 SSR1: cavity string assembly
Free particle assembling procedure for cleanroom activity at Lab 2
SSR1
Type A
SSR1 Type B
Solenoid
BPM
SSR1 Type B
SSR1 Type B
SSR1 Type B
SSR1
Type A
SSR1
Type A
SSR1
Type A
Gate Valve
Gate Valve
20mm
Coupler (vacuum-end)
IIFC SSR1 cavity
IIFC SSR1 cavity

## Slide 17: SSR1 CM Design Maturity
SSR1 final cryomodule
FDR in Jan. 2018
Procurement: in progress
Assembly starts in Nov. 2018
SSR1 coldmass
Design: completed
Procurement: in progress
Assembly starts in July 2018
SSR1 cavity string assembly
Design: completed
Procurement: completed
Assembly starts in March 2018
SSR1 1st cryomodule
  SSR1 2nd cryomodule
  We are collecting lessons learned and list of improvements from the experience in designing and developing the SSR1 1st cryomodule.

## Slide 18: SSR2: Design Maturity
SSR2 cavities:
  RF Design Initially developed by Fermilab
  DAE (BARC) is currently working on RF and Mechanical design.
  Bare Cavity Design Status Review held at BARC Nov 7th 2017
  PDR at BARC is scheduled for March 2018
SSR2 Electric and Magnetic fields
Structural analyses performed by BARC
HOM Analysis
Multipacting Analysis
Design of SSR2 cryomodule will be based on SSR1 cryomodule (including solenoids, couplers, tuners, etc.)
SSR2 Cavity & Cryomodule development is on the critical path for the SRF Linac because it is the least mature of the SRF CMs

## Slide 19: SSR1, SSR2: Design Review Plan
Critical component design review cycle
CDR → FRS/TRS → PDR → FDR →PRR
Critical Reviews are tracked in P6 as milestones.
Non-critical components or subsystems are managed within the Division or Department review process as required by the FNAL Engineering Manual.
Design reviews planned for Partner deliverables as appropriate to ensure technical and ESH&Q requirements are met. Partner milestones identified and implemented in P6.
SSR1 1st cryomodule
  PDR, FDR and PRR of the key-components up to the string assembly were successfully held and documented.

## Slide 20: LB650/HB650 Overview
Cryomodule type | Cavities per CM | # CMs | CM length (m) | Q0 at 2K (1010)
HWR | 8 | 1 | 5.93 | 0.5
SSR1 | 8 | 2 | 5.2 | 0.6
SSR2 | 5 | 7 | 6.5 | 0.8
LB650 | 3 | 11 | 3.9 | 2.15
HB650 | 6 | 4 | 9.5 | 3
PIP-II Conceptual Design Report: DocDb # 113
Eleven βg=0.61 and four βg=0.92 650 MHz SRF cryomodules, capable of operating in both pulsed and CW modes, that provide an energy gain from 185 MeV to 800 MeV with a beam current of 2 mA average to the Beam Transfer Line.

## Slide 21: LB650/HB650 Requirements & Partner Interfaces
βg=0.61, 650 MHz Elliptical Cryomodules
CM FRS: TC# ED0001830, SRF Dressed Cavity FRS: TC# ED0001834
βg=0.92, 650 MHz Elliptical Cryomodules
CM FRS: TC# ED0001322, SRF Dressed Cavity FRS: TC# ED0001321
Partner Interfaces.
SPC/SPM and POC direct communication through bi-weekly update meetings.
Doc transfer through Teamcenter/Librarians and Sangam
LB650 partners: VECC, RRCAT, BARC
  VECC - Design, fabrication, and testing of prototoype LB650 dressed cavities
  RRCAT – Design of LB650 Cryomodule based on SSR1 and HB650
  BARC – RF coupler production
HB650 partner: RRCAT, BARC
  RRCAT - Bare and dressed cavities design and production
  RRCAT - Tuner fabrication
  BARC – RF coupler production

## Slide 22: LB650 Cavity Design/Maturity
LB650 Dressed Cavity Design through the PDR TC# ED0006010
  PDR of VECC cavity resulted in subtle alternative EM design modifications. Three designs pursued (VECC, FNAL, INFN-Lasa) were very similar in critical parameter performance.
  LB650 cavity Electromagnetic Design (INFN-Lasa) chosen.
INFN-Lasa LB650 Cavity Model
FNAL analysis of Trapped HOMs with broad beam spectrum.

## Slide 23: LB650 Cryomodule Design/Maturity
LB650 CMs
(DAE/EU Deliverable)
CM Design is DAE-deliverable: RRCAT
  Design concept based on FNAL SSR1 and preliminary HB650 CM
  CM Design maturity is conceptual.
  Design review schedule elaborated in P6.
Conceptual 3-cavity strongback/support post design based on SSR1 CM
S. Gilankar: NSCS 26 VECC Kolkata

## Slide 24: HB650 Cavity Design Status
Cavity Design Status
  βg=0.92 650 MHz bare cavity design has completed the FDR: TC# ED0003861, TRS for cavity system ED# ED0003153 is in draft form.
  Dressed cavity mechanical design is advanced, awaiting FDR of dressed cavity system.
  Design review schedule elaborated in P6.
  Performance of βg=0.90 cavities demonstrated above specification.
  Processing/Q0 recipe refinement still required.
Three of four multi-cell B.90 cavities qualified through VTS.
Q0 > 3.5 E10 @ 20 MV/m demonstrated
Minimal radiation due to FE induced X-Rays during tests up to Eacc < 25 MV/m.
5-cell B.90
*Negligible radiation < 23 MV/m
N-doped cavities
*
*

## Slide 25: HB650 RF Coupler/Tuner Design
High Power 650 MHz 120 kW RF coupler FRS, TRS TC#s ED0003645, ED0005689
  Prototypes through FDR/PRR.
  Two cold-end designs in procurement cycle, expected to arrive 04/2018
Prototype tuner – Engineering Specification TC# ED0005146
  Version 1 procured and tested at room temp. Initial testing yielded opportunity to optimize design for stiffness improvement.
Prototype 650 MHz tuner during bench testing.
EM Shielded Prototype

## Slide 26: HB650 CM Design/Maturity
HB650 Model
HB650 String Details
~10m
HB650 CM Design Status - FRS: TC# ED0001322
  Status is preliminary. 3D model is well developed. Design is currently in the analysis/design iteration phase pre-PDR.
  Design review schedule elaborated in P6.

## Slide 27: Design Review Plan
Critical component design review cycle
CDR → FRS/TRS → PDR → FDR →PRR
Critical Reviews are tracked in P6 as milestones.
Non-critical components or subsystems are managed within the Division or Department review process as required by the FNAL Engineering Manual.
Design reviews planned for Partner deliverables as appropriate to ensure technical and ESH&Q requirements are met. Partner milestones identified and implemented in P6.
Next series of reviews include PDRs of LB650 dressed cavity, LB650 cryomodule, HB650 cryomodule

## Slide 28: PIP-II LB650 CM1 Summary Schedule

## Slide 29: PIP-II LB650 CM2-11 Summary Schedule

## Slide 30: Schedule – HB650 CM1

## Slide 31: Schedule – HB650 CM2-4

## Slide 32: Presently assembled: PIP2IT WFE
30 keV, 15 mA H- Ion Source (from 5 µs to DC)
LEBT (3 – solenoids; 30º bend to accommodate 2 ion sources in PIP-II)
  Chopper to form macro-pulses
CW-compatible 2.1 MeV RFQ (produced by LBNL)
10-m long MEBT with fast chopper
  2 quadrupole doublets and 7 triplets (produced by BARC, India)
  3 bunching cavities
  Collimation system (4 sets x 4 scraper plates)
  Differential pumping system
IS + LEBT
RFQ
MEBT
Beam to dump or HWR cryomodule

## Slide 33: PIP2IT WFE Achievements
Beam at “CDR parameters” through a full-length MEBT
LEBT with un-neutralized section
RFQ reliably operating at CDR parameters
CW – compatible MEBT
Prototype elements of the fast chopping system
CW-compatible Machine Protection System
Diagnostics
And other development that will not be presented here, e.g.
  LLRF, control programs, 20 Hz operation …

## Slide 34: PIP2IT RF Power Progress to date
SigmaPhi 162.5 MHz, 75 kW amplifiers for RFQ have been operational at PIP2IT since 2014.
Comark/Technalogix 162.5 MHz, 3 kW amplifiers
    Buncher 1, 2 & 3 operational
    All five amplifiers at Fermilab
RF Distribution in place for RFQ and Buncher 1, 2 & 3.
Four McManus 162.5 MHz, 7 kW circulators arrived in May. Two are in use for Buncher 2 and Buncher 3.
First 162.5 MHz, 7 kW CW amplifier has arrived. Up to 7 more units to be procured in FY2018.

## Slide 35: Technical Progress to Date - PIP-II 325 MHz RF Power Amplifiers
Functional Requirements Specification 7kW  TC#ED0003408-A Approved
Interface Control Document 7kW  TC#ED0006356-
Approved
Technical Requirements Specification 7kW  TC#ED0003531-B Approved
1kW Module Testing Procedure  TC#ED0006484-
Approved
7kW Amplifier Testing Procedure  TC#ED0006507-
Approved
Functional Requirement Specification 20kW  TC#ED0003669-

## Slide 36: Technical Progress to Date - PIP-II 650 MHz RF Power Amplifiers
Functional Requirements Specification 40kW  TC#ED0003413-B
Interface Control Document 40kW  TC#ED0006360-
Technical Requirements Specification 40kW  TC#ED0005489-A
500W Module Testing Procedure  TC#ED0006585-
20kW Module Testing Procedure  TC#ED0006596-
Functional Requirement Specification 70kW  TC#ED0003680-

## Slide 37: PIP2IT LLRF Progress to date
Complete FNAL systems operating on the RFQ and two bunching cavities supporting CW and pulsed mode validating many design decisions
Collaborations
  Two DAE engineers on site for two years
  Weekly meetings with DAE team
  Partnership agreement with Berkeley in progress
System studies including:
  Noise and feedback analysis
  Longitudinal sensitivity analysis
  Performance analysis
  RFQ resonance control

## Slide 38: Progress to date: LLRF Systems and Chassis
Digitizer Chassis
Resonance Control Chassis
Operational LLRF at PIP2 IT(FNAL)
Seven joint FRSs Approved (two more near approval)
  TRS in process (DAE/FNAL)
8-Channel Down-Converters
  DAE version is in test
4-Channel Up-Converters
  DAE version in test
FPGA Board
  In layout
ADC-DAC FMC Module
  In Layout
Resonance Control Chassis
  Leverage from FNAL LCLS-II design and is in progress
Master Oscillator and Reference line in design

## Slide 39: Progress to date: RFPI
RFPI Hardware Prototype Delivered by DAE

## Slide 40: IIFC Collaboration Personnel
Vyaghri Lalitha Sanyasirao Sista
  Part of physicist team that operated, commissioned, and debugged linac warm front-end.
  Part of engineering team that simulated and debugged issues with RFQ.
  Created software that automatically measures beam lattice.
  Provided detailed analysis of the accuracy and precision of BPM system.

## Slide 41: IIFC Collaboration Personnel
Shailesh Khole, Deeraj Sharma
  Developed and deployed UI and algorithm for 200 Ohm and 50 Ohm kickers in PIP2IT
  Began design of digitizer and FPGA boards for PIP2 prototypes
    Included filter, noise, and circuit simulation
    Documentation and support packages for FRS/TRS and design packages
  Updated FNAL VxWorks to version 6.9 as upgrade for newer VME systems
  Created testing procedures and became familiarized with LLRF concepts

## Slide 42: PIP-II Scope and Deliverables – Beam position
Deliverables:
  Beam position monitor pickups
    89 warm 4-button pickups
    37 cold 4-plate pickups in HWR, SSR1 and SSR2
  Signal processing electronics, crates and cables
  Fermilab provides
    All cold BPMs
    12 MEBT 4-button BPMs
  We propose to have DAE provide
    R&D prototype signal processing electronics
    78 4-button warm BPM for construction
    512 channels of analog and digital electronics for construction

## Slide 43: PIP-II Scope and Deliverables – Beam loss
Deliverables:
  Beam loss monitor pickups
    115 ionization chamber pickups
    115 PMT-based scintillator pickups
    25 neutron detectors
  Signal processing electronics, crates and cables
  We propose to have DAE provide
    115 assembled and tested ionization loss monitor detectors
    115 assembled and tested PMT-based fast loss monitor detectors
    25 assembled and tested neutron detectors
    Analog and digital DAQ electronics, electronic crates and software to support basic operation of above loss monitor detectors
    HV power supplies to operate above list of loss monitor detectors

## Slide 44: Tech. Prog. to date – Beam position
Installation and testing of BPMs in PIP2IT MEBT
  4-button BPMs attached to quad magnet
  DAQ with FPGA-based electronics for CW and pulsed beam
  Analog filter & amp boards
  8 channel, 14 bit, 125 MSPS boards
4-buttom BPM

## Slide 45: Controls: PIP2IT Displays

## Slide 46: Controls: Collaboration Effort
Working with multiple SPC’s to confirm communication interface between different systems.
  Verifying the communication protocol compatibility between RF power amplifiers and FNAL ACNET control system.
  Verifying alternative crate controller operating systems to VxWorks (due to contract/cost issues).

## Slide 47: Summary

## Slide 48: END