## Sheet1
to do | what in detail | who | by when | done?
docs to be revised | list of docs in each sub area to be updated from last review | subproject managers & PCS | 2018-01-12
agenda | create agenda to match charge | EGM & JRM | 2018-01-22
talk templates | create templates for review and post and communicate | EGM & JRM | 2018-02-02
updated risk cost/schedule | 1st rerun monte carlo analysis with updated risks | ME | 2018-01-22
BCRs completed | finalize all CRs and put in all pending CRs | all | 2018-01-31
update cost/schedule | complete Jan 2018 DOE cost/schedule statusing | PCS | 2018-02-06
finalize risk cost/schedule | 2nd run monte carlo analysis | ME | 2018-02-12
revise docs | update all documents as needed | subproject managers & PCS | 2018-02-16
produce cost/schedule reports | provide all cost/schedule reports for the review including tables for talks | PCS | 2018-02-16
contingency analysis | redo contingency analysis | EGM | 2018-02-16
practice talks | dry run all talks | all | 2018-03-02
post documents | all documents posted for reviewers | all | 2018-03-06
DOE IPR | progress review | all | 20-22 Mar