## Slide 1
G. Velev
All Experimenters and Laboratory Status Meeting
22 January 2018
TD Operations Status

## Slide 2: Cryogenic Sector
Fermilab Accelerator Science and Technology (FAST)
  Warmed to 300K during IOTA completion
Meson Detector Building
  PIP-II cavity test completed
Cryomodule Test Facility
  LCLS-II F1.3-07 cryomodule testing to be complete this week
Industrial Building 1
  Stand 3: LCLS-II magnet testing
  VTS: SRF cavity R&D and LCLS-II production cavity testing
Muon Campus
  Supporting g-2 operation
Heavy Assembly Building
  Completed test run. Waiting for first Mu2e TS production solenoid to be delivered at the end of January
MuCool Test Area
  Cryogenic system is permanently shut down
  Experienced ICW supply piping damage due to frozen water

## Slide 3: SRF Sector
R&D
  Several 1-cell cavities and three 9-cell cavities were tested since last report.
    Continue to get statistics with various recipe of N-infusion.
    One notable experiment on 1-cell cavity study showed the flux trapping happen more off equators. It is counter-intuitive, a repeat test is in progress to verify the result.
    2nd 3.9 GHz heavy doping cavity showed great promise with 1.5e10, but with lower quench field (10 MV/m)
  Nb/Cu equipment relocated to new location, installation is in progress.
  Quantum computing cavities: one 2.6 GHz cavity is being tested.
LCLS-II
  1.3 GHz cavities – qualification continues
  3.9 GHz cavities - qualification continues
    3HRI02 dressed, waiting for test prep.
    3HRI03 HTS is in progress. Cavity was found locked by cavity support due to support mis-alignment. Tuner test showed one piezo locked, the other loose due to cavity went “banana”. Cavity support will be fixed and test will resume.
  CM03 repair - Dis-assembly almost finished. Cavity dis-assembly is in progress.
  CM04 pending final modification (cryo-valve gas guard, CAV1 support) before shipping to SLAC.
  CM06 was shipped to SLAC – milestone for the project.
  CM05 Test was completed. It is at ICB. FE was moderate despite an in-situ repair of a HOM feedthrough. Cryomodule met the most of the specs. The cryomodule is likely to be shipped to SLAC in January as the second.
  CM07 is at CMTF. A repeated fast cool down showed better performance at 2.5e10 vs. previous 2.2e10.
  CM08 is in WS5. helium circuit leak check is in progress.
  CM09 in WS3. HOM tuning is in progress.
  CM10 is in WS2. Attached to upper cold mass assembly. Preparing to move to ICB WS3.
  CM11 WS0 completed, WS1 started this week.
PIP-II
  Spoke cavity S113 test in STC is complited, conditionally qualified.

## Slide 4: Magnet Sector
HL- LHC, AUP – Producing coils: QXFA107 is in the impregnation stage. Short coil QXFS09 cleaning after impregnation. The production area in IB3 is being reconfigured to accommodate the rotating coil winding table and cable tensioner as backup to the Selva winding machine.
  LCLS II – test and qualification of the quadrupoles continues, SPQ122 is prepared for test completed, Quadrupoles 123-125 are in different stage of incoming inspection.
  Mu2e –
  TS prototype was removed from the dewar. Post-test inspection in progress. This prototype will be used at HAB-west for commissioning of tooling, then will be sent to IB2 for stretched wire measurements. TS production module fabrication well underway. Expected to be shipped until early February.
  PS/DS model coil still on large in-house lathe at GA, machining of the outer coil was performed last week. Insertion in the shell and then LN2 testing will take place towards the end of this week.
  AS – Refurbishment of another two IQB magnets has started. IQB310 and IQB169 were “burned” last week.
  G-2 – inner coil winding activity resumed on the g-2 Inflector
  MDP 15-17 T dipole R&D
    Outer coil 002 impregnation is complete. Some dents have been found on the coil outer surface next to midplanes; coil was declared as damaged. Modification of the impregnation tooling for outer coil 004.
    Preparation for MDP collaboration meeting.
  Miscellaneous: – New proposal on "Fast Ramping Nb3Sn Superconducting Dipole Magnet“ was prepared and submitted to DOE PAWS for Electron Ion Collider .